## schedule
Phase | Day | Shift | Time (h) | Activity | Beam | Target values
Injection and circulating 450 GeV beam | 1 | M | 8 | Injection and First turn b1 | B1, pilot | Beam thread around ring with splash events (~30 per experiment)
| 1 | A | 8 | Injection and First turn b2 | B2 pilot | Beam thread around ring with splash events
| 1 | N | 8 | SF
| 2 | M | 8 | Circulating Pilot and RF capture b2 | B2, pilot
| 2 | A | 8 | Circulating Pilot and RF capture b2 | B2, pilot | c.o establised. >5h beam lifetime
| 2 | N | 8 | SF
| 3 | M | 8 | Circulating Pilot and RF capture b1 | B1, pilot
| 3 | A | 8 | Circulating Pilot and RF capture b1 | B1, pilot | c.o establised. >5h beam lifetime
| 3 | N | 8 | SF
449 GeV tuning and essential systems | 4 | A | 8 | BCTFR, BPM setup (phases) with pilot intensity, b2 | B2, pilot | BCT, BPMs working in capture mode, lifetime measurement | Michael Ludwig, Lars, Rhodri
| 4 | A | 8 | RF further commissioning (loops, ...) b2 | B2, pilot | RF loops
| 4 | N | 8 | SF
| 5 | M | 8 | Tune, Dispersion measurements, b2 | B2, pilot | Check integer tune, measure dispersion. BBQ - only minor re-commissioning expected (tests), 1-2 half-shifts/beam | Ralph, Marek G., Stephen Jackson
| 5 | A | 8 | Orbit studies, b2 | B2, pilot | c.o corrected, energy matching done
| 5 | N | 8 | SF
| 6 | M | 8 | Chromaciticity - check trims and adjust , b2 | B2, pilot | Chromaticity corrected to ??? | Ralph, Marek G., Stephen Jackson
| 6 | A | 8 | Initial commissioning of beam dumping system, b2 | Extracted pilot, b2 | Aperture, extraction trajectory, LBDS BI
| 6 | N | 8 | SF
| 7 | M | 8 | Basic protection device and collimator setting-up - b2 | B2, pilot | TCDQ, TCTs, collimators as aperture.
| 7 | A | 8 | MPS tests: FMCM, time delays | B2, pilot | FMCM, PIC, WIC 896393, 896390, 896395
| 7 | N | 8 | BCTFR, BPM setup (phases) with pilot intensity, b1 | B1, pilot | BCT, BPMs working in capture, lifetime measurement
| 8 | M | 8 | RF further commissioning (loops, ...) b1 | B1, pilot | RF loops
| 8 | A | 8 | Tune, Dispersion measurements, b1 | B1, pilot | Integer tune oK, fractional to ???, disp, measured
| 8 | N | 8 | SF
| 9 | M | 8 | Orbit studies, b1 | B1, pilot | c.o corrected, energy matching done, local correction
| 9 | A | 8 | Chromaciticity - check trims and adjust, b1 | B1, pilot | Chromaticity measurement and trim, RF radial loop/modulation → 1-2 half-shifts/beam
| 9 | N | 8 | SF
| 10 | A | 8 | Initial commissioning of beam dumping system - b1 | Extracted pilot, b1 | Aperture, extraction trajectory, LBDS BI | BCT, BPM, BTV, BLM
| 10 | A | 8 | Basic protection device and collimator setting-up - b1 | B1, pilot | TCDQ, TCTs, collimators as aperture.
| 10 | N | 8 | SF
| 11 | M | 8 | Emitttance measurements- b1 - b2 | B1 and B2 pilots | Wires, BSRT cross checked, AGM | Ana, Guy Crockford, Thibaut,
| 11 | A | 8 | MPS: BLM thresholds - check plus thresholds and checks on beam dump BLMs | B1/B2 pilots | 896394, Decrease BLM threshold and create IL with very small beam intensity | Bernd & team
| 11 | N | 8 | SF
450 GeV two beam operation | 12 | M | 8 | Two Beam Operation setting-up - 450 GeV | 2x2, 5e9 | Two beams stored, RF cogging, Lifetime ~10 hours,Common correction, …
| 12 | A | 4 | MPS: experiments' dump tests | pilot | Dump test for each experiment, based on BCM monitor data… Combined with BLM on triplets check
| 12 | A | 4 | MPS: provoke magnet 'trip' and check adequate protection by collimators | pilot
| 12 | N | 8 | 450 GeV collision setting-up - experiments | Solenoids & dipoles ON | Commission LHCb and Alice at 450 GeV only (4 hours). Solenoids will take 4 hours for CMS, not long for Alice, and a fews hours for Atlas
| 13 | M | 8 | MPS: aperture in insertion regions, Calibration/check of triplet BLMs | pilot | See also SF
| 13 | A | 8 | 450 GeV collisions | 2x2, 2e10 | First fill during daytime
| 13 | N | 8 | 450 GeV collisions | 2x2, 2e10
Snapback and ramp to 3.5 TeV | 14 | M | 8 | Snapback- Ramp setting up - b1 | with sol. ON
| 14 | A | 8 | Snapback- Ramp setting up - b1 cont'd.
| 14 | N | 8 | 450 GeV collisions | 2x2, 5e10 | BPF has to be there, trial lumi scans (using expts. data). Look at BRAN
| 15 | M | 8 | Snapback- Ramp setting up - b1 cont'd.
| 15 | A | 8 | Protection device and collimator setting-up - b1 ramp |  | TCDQ, TCTs, collimators as aperture.
| 15 | N | 8 | 450 GeV collisions | 2x2, 5e10
| 16 | M | 8 | Snapback- Ramp setting up - b2 | with sol. ON
| 16 | A | 8 | Snapback- Ramp setting up - b2, cont'd.
| 16 | N | 8 | 450 GeV collisions | 4x4 5e10
| 17 | M | 8 | Snapback- Ramp setting up - b2, cont'd.
| 17 | A | 8 | Protection device and collimator setting-up - b2 ramp |  | TCDQ, TCTs, collimators as aperture.
| 17 | N | 8 | 450 GeV collisions | 4x4 5e10
| 18 | M | 8 | MPS and beam dumping system - extracted pilot, b1 - 0.45-1.2 TeV |  | BLM checks, energy tracking, LBDS BI
| 18 | A | 8 | MPS and beam dumping system - extracted pilot, b1 - 0.45-1.2 TeV |  | BLM checks, energy tracking, LBDS BI
3.5 TeV two beam operation | 18 | N | 8 | SF Ramp
| 19 | M | 8 | Measurements at 1.1 TeV, b1
| 19 | A | 8 | MPS and beam dumping system - extracted pilot, - 1.1 TeV, b1 |  | BLM checks, energy tracking, LBDS BI | BCT, BPM, BTV, BLM
| 19 | N | 8 | SF Ramp
| 20 | M | 8 | Measurements at 1.1 TeV, b2
| 20 | A | 8 | MPS and beam dumping system - extracted pilot, - 1.1 TeV, b2 |  | BLM checks, extraction aperture, LBDS BI | BCT, BPM, BTV, BLM
| 20 | N | 8 | SF Ramp
| 21 | M | 8 | Protection device and collimator setting-up - 1.1 TeV, b1
| 21 | A | 8 | Protection device and collimator setting-up - 1.1 TeV, b2
| 21 | N | 8 | SF Ramp
| 22 | M | 8 | Measurements at 1.1 TeV, b1
| 22 | A | 8 | Measurements at 1.1 TeV, b2
| 22 | N | 8 | SF Ramp
| 23 | M | 8 | Two Beam Operation setting-up - 1.1 TeV |  | Two beams stored, Lifetime > 5 - 10 hours
| 23 | A | 8 | Two Beam Operation setting-up - 1.1 TeV |  | Two beams stored, Lifetime > 5 - 10 hours
| 23 | N | 8 | SF Ramp
| 24 | M | 8 | 1.1 TeV collision setting-up | Solenoids ON | Beams colliding in all IR, Long.pos. O.K.
| 24 | A | 8 | 1.1 TeV collision setting-up
| 24 | N | 8 | 1.1 TeV collisions | 2x2, 5e9
SF (mostly N shifts):
Kick response measurements
|  |  |  | BPM commissioning (Capture mode) | stable, pilot | 1 - 2 nights | Rhodri, Lars, JJG
Aperture measurement
|  |  |  | Basic injection tuning - b1, b2 | B1, pilot | Basic inj. steering & matching, 3.75 (??) um e_xy
Beating measurements
|  |  |  | Cycle machine |  | 2 hours as required
Trial ramps
Tune injection protection - 450 GeV
Check beam presence flag to allow high intensity injection
Measure injection efficiency (should be around 95%)
Check losses at passive absorber, images on BTVs, trajectories
TDI setting : goal 7 σ
Collimation setting-up & protection - 450 GeV
Two Beam Operation - 450 GeV
Set up of two beam collimators (TCT, TCL) IR1, IR2, IR5, IR8
IR set up: separation bumps, SIS limits (I)
IR1,2,5,8 set up: aperture measurements with separation on
IR set up: separation bumps, SIS limits (II)
|  |  |  | Dedicated losses for R2E |  | 'dedicated' losses in order to evaluate what are 'safe limits' for direct-loss induced radiation levels to electronics.
Stable single bream for a least 4 hours (if lifetime good enough)
Stable - two uncolliding beams - 4 hours - experiments timing
Tune-PLL (though tested in the SPS) → 2-4 half-shifts/beam
|  |  |  | Continuous Q' measurement via RF frequency modulation |  | 1 - 2 shifts - try and get working before ramp commissioning
|  |  |  | Orbit feedback tests |  | 1 - 2 shifts
RF phasing:
Coarse - relative bucket and phase beam 1 & beam 2
Fine adjust: longitudinal crossing point
Adjust of crossing point in collisions
Parasitic machine development
Roman pots to 15 sigma
Before access
|  |  |  | Intrusion test. Verify signals and beam dump OK before access block in |  | 0.5 hours per beam

## Global checkout
DAY | SHIFT | Priority | TIME hours | System | TASK | Comment
1 | A | 1 | 8 | BIS | debugging with everything connected - as prequisite, plus experiments, connection to beam dump etc | Both loops close, beark loops, check PM events etc., much tried before
1 | N | 1 | 3 | WIC/FMCM | interlocked warm magnets | RD in 3 & 7
1 | N | 1 | 5 | OP | Pre-cycle and full sequence tests, RBAC operational | all circuits, RF, collimators
2 | M | 1 | 8 | PIC | Check configuration, mapping to BIS etc. | Markus Z.
2 | M | 1 |  | SIS | Orbit correctors etc. | in parallel with Markus (4 hours)
2 | A | 1 | 3 | LASS/LBDS | DSO-like test of LBDS connection to LASS: | check the timing between LASS signal, BIS loop and Dump trigger. check with Ghlain
2 | A | 1 | 2 | LBDS | At 450 GeV trims of all 8 magnet currents, up and down, to check BETS and LBDS trigger (rearm LBDS after) [16 trims & resets] | Minimum LBDS energy tracking tests with all inputs connected (4xRB, 2xMSD, 2xQ4): - this and following LDBS tasks
2 | A |  | 4 | EPC | RBIH 8733 au SR8 - tests (note this is an EIS) | in parallel with beam dump tracking which doesn't need beam permit
2 | A | 1 | 2 | LBDS | full system ramp to top energy, checking tracking of kicker power supplies.
2 | N | 1 | 8 | OP | Pre-cycle and full sequence tests, RBAC operational | Power converters, collimators, RF, Injection, Beam Instrumentation
3 | M | 1 | 2 | LBDS | at top energy, trims of all 8 magnet currents, up and down, to check BETS triggers (rearm BETS only)
3 | M | 1 | 2 | LBDS | Check of energy distribution from BETS with RBs connected. | recycle LHC and ramp to top energy, monitoring energy distribution. (combine partly with 2) [time estimate: 2 h extra for recycle?].
3 | M | 1 | 2 | LBDS | Global check of ramping of protection devices for LBDS with RF, LHC collimators and magnets | needed to make sure dump ramps with all real inputs connected. - can be done in conjunction with 3
3 | M |  | 4 | CV | Ventilation tests: air flow (speed/direction) with machine closed. | 2 to 3 teams into ring - could have been completed in W47
3 | A | 2 | 2 | OFB | Orbit feedback tests - checking RT channel control of FGCs etc. | Ralph Steinhagen/Stephen Page - already looking good
3 | A | 2 | 6 | OP | Final OP preparation for beam - interlocks, pre-cycle etc.
|  |  |  | ALARM | Systematic checks | In shadow of above & as sectors become operational
|  | TOTAL | 37 | hours | assuming 100% machine availability
|  |  | 1.5417 | days

## BI checkout
Orbit feedback tests | Link to RF channel of FGCs | First tests look good
Concentrators | Instructions & procedures
Video signals | Control and instructions | need a procedure
| Concentration | Fixed display | SDDS | Logging | Application/acquisition | Problems
BLM
BPM |  |  |  |  | YASP - OK
BPMD
BTV | [5 empty] | can't read images from equip state
RADMON
BCTFD | -
BCTDC
BCTFR
BRAN
BSRT
BSRA - AGM
WIRE SCANNER (BWS)
MULTITURN
BQBBQ
Aperture - tune - AC dipole
BQS

## LSA checkout
Settings | Import latest FIDEL model | Marek
| Generate 1.2 TeV ramp with new FIDEL model | Mike | OK - settings to be completed
| Check full decay is in place | Marek
| Snapback in place if required. | Marek
No b1, b2 corrections, default b3, b4, b5
| Pre-cycle & ramp all circuits - test in simulation | OP
| Transfer function checks | Fidel team
| Full settings check | Fidel
| Optics check from LSA settings | Gabriel
| Polarity checks - correct where necessary | Mike, ABP, Fidel
TRIM | LHC Momentum
TI8 Momentum
| YASP - optics, corrector settings zero etc. | Jorg
| Test Incorporation | OP

## Pre-flight checklist
DSO | Fully signed beam permit | Ghislain
Timing | Timing tables properly configured
Timing events logged
RBAC | Everything from LHC consoles - check operational mode
Power converters | Everything off that should be off and fixed display
Fixed display of all sectors
RT channels enabled and zero
Check that everything is logging
Settings | bumps zero
orbit corrections from injection test in
knobs
SDDS | Check storage capabilities, check SDDS logging interface
RF | RF frequencies nominal for protons
RF power off for first turn etc.
APW display
Pre-pulses and synchronization
Fixed display | What, where - the full list
Transfer lines | Standard checks - pulse lines, EIS on and under control
TCDI out
Screens out
Injection kickers | Standard settings
Beam dump | take as given
BIS | take as given if VK's around
PIC | taken as given
SBF | check
SIS | screens ongoing, to be completed first part of W47
Collimators | parking settings
Betatron cleaning TCP, TCSG, TCLA to 10 sigma
Momentum cleaning TCP, TCSG, TCLA to 10 sigma.
Tertiary collimators to 15 mm, not interlocked (ready for splash events).
TCL open to +-20 mm.
Inj. Prot.: TDI in protection setting (IR2: xxx, IR8: xxx). TCLI open at xxx sig
Dump prot.: TCDQ and TCSG@TCDQ to xxx/xxx sig.
Experiments | Mode, handshake, etc
Sequencer | Clock the fill number!

## Week 46
Status Sunday 15/11
Ongoing | PGCs | S23. S56, S78 - heat run
Ongoing | Tracking tests | S23 done. S12-S23 to do
Thursday | Beam dump to Q4/MSD | OK
Friday | Beam dump to S56/S78 & test | OK - tests look good
Friday | RF frequency ramp etc | Done
During week | Vacuum interlock tests IP1 & IP4 | To be finished in W47
Friday | S56 & S78 to 450 GeV for initial beam dump energy tracking | OK
Thursday - Friday | Ventilation tests 1,2,5,6,8 done
Friday | FMCM 10/12 to be done tonight
Friday/weekend | PGC 56, 23, 78 (watch triplets) | Good progress

## Week 47
Monday/Tuesday | PGC | Have to drive through S12, 34,34, 67, 81
When possible | OP | Extended tests on finished sectors
Monday pm | EXPERIMENTS | Moveable devices - test interlocks (including, perhaps TOTEM) |  | global tests of modes, interlocks and handshakes with experiments
Monday | RBAC | Operational and then test thoroughly
Tuesday | Vacuum - unblock | unblock the LSS4 valves on Tuesday morning somewhere between 8:30 and 10:00
Tuesday | Vacuum LSS4 - test | start the interlock testing of the vacuum valves LSS1 at 10:15 on Tuesday (assuming that the time slot is still OK with HWC) and then move to LSS4 after that. With luck we could finish both LSS1 and LSS4 by 2pm. | Alick
Tuesday | Beam dump to LASS | Intrusion test later in global machine checkout
Tuesday | SMP | BETS to SMP to TIMING system tests - 4 hours |  | If not now during global checkout
Wednesday evening | Start Global Checkout