## Slide 1: Turning on the LHC: commissioning with beam and the outlook for 2010
Mike Lamont for the LHC commissioning team

## Slide 2: Prep: beam tests through the years
2004:TI8
CNGS
TI2
2008: FIRST BEAM TO IR3
2009: FIRST IONS TO LHC
2008: FIRST BEAM TO LHC
2004: FIRST HOLE
2008: SEPT 10
2009: Sector test
2009!
2003:TT40

## Slide 3: Prep: dry runs and machine checkout
Extraction
Transfer lines
Injection
RF, injection sequence
Timing System
Beam Interlock System
Collimators
Vacuum
Interlocks, SIS
BLMs, BPMs
BTV, BCT
Beam dump
PGCs
Magnet model
Sequencer, alarms
Controls, logging, DBs
LSA, optics model, YASP
Re-phasing in the SPS:
And some serious hardware commissioning of cold circuits

## Slide 4: Beam milestones 2009 1/2
20th Nov | injection of both beam – rough RF capture
21st Nov | Beam 1 circulating
22nd Nov | Beam 2 circulating
23rd Nov | First pilot collisions at 450 GeV First trial ramp
26th Nov | Pre-cycle established – excellent reproducibility Energy matching
29th Nov | Ramp to 1.08 TeV and then 1.18 TeV
30th Nov | Solenoids on
1st – 6th Dec | Protection qualified at 450 GeV to allow "stable beams"
6th Dec | Stable beam @ 450 GeV
8th Dec | Ramp 2 beams to 1.18 TeV – first collisions
11th Dec | Stable beam collisions at 450 GeV with high bunch intensities: 4 x 2 10^10 per beam

## Slide 5: Milestones 2/2
14th Dec | Ramp 2 on 2 to 1.18 TeV - quiet beams - collisions in all four experiments
14th Dec | 16 on 16 at 450 GeV - stable beams
16th Dec | Ramped 4 on 4 to 1.18 TeV - squeezed to 7 m in IR5 - collisions in all four experiments
16th Dec | End of run
3 days - first collisions at 450 GeV
9 days - first ramp to 1.2 TeV
16 days - stable beams at 450 GeV
18 days - two beams to 1.2 GeV & first collisions
General agreement that this wasn’t bad

## Slide 6: Injection - reminder
5 x MSI septa
4 x MKI kickers
TCDD absorber
TDI collimator
Layout (point 8)
Nominal batch from the SPS: 288 bunches of 1.15 e11 protons at 450 GeV
We injected a single bunch of 2 e10

## Slide 7: Injection
Delicate process
  We will sling around a lot of beam during this process
  Complex dance of hardware, timing, RF, interlocks etc.
  Have to carefully position collimators and other protection devices to make sure we catch any losses
  Issues with BLMs triggering the beam interlock system due to fast losses during the injection process
Full program of beam based checks performed
Generally impressive, clearly benefits from experience gained during injection tests.
However, for the moment one would worry about routinely injecting unsafe beam.

## Slide 8: What you can
TT40 Damage during 2004 High Intensity SPS Extraction / Goddard, B ; Kain, V ; Mertens, V ; Uythoven, J ; Wenninger, J
During high intensity extraction on 25/10/04 an incident occurred in which the vacuum chamber of the TT40 magnet QTRF4002 was badly damaged.
The beam was a 450 GeV full LHC injection batch of 3.4 1013 p+ in 288 bunches, and was extracted from SPS LSS4 with the wrong trajectory
Or what you can do with 2.9 MJ
= 4.4 e12 at 3.5 TeV

## Slide 9: 450 GeV
Measurement and control of key beam parameters
  Orbit, tune, chromaticity, coupling, dispersion
  Beam loss, Beam size
  Energy matching
  Aperture checks
Experiments’ magnets
  Solenoids & dipole –on and corrected
Two beam operation both with and without bumps
Optics checks
Full program of polarity checks of correctors and BPMs
Performance of hardware, instrumentation and software was impressive
Good preparation – fast problem resolution

## Slide 10: 450 GeV: 8 kHz & the hump
8 kHz line, broad frequency “hump”, and other spectra perturbations:
  Reduction of beam life-time, emittance blow-up, …
Maybe not of direct interest to this audience but this sort of thing can give you a real headache

## Slide 11: Synchrotron light monitor
Vertical emittance blow-up – beam 2

## Slide 12: Aperture
Beam clearance seems to be OK
Some measured bottlenecks agree with model predictions using measured functions.
Aperture is out of budget due to the large beta beating
Correcting beta beating (optics) seems mandatory at 450 GeV

## Slide 13: Beating: 450 & 1180 GeV

## Slide 14: Collisions at 450 GeV
Man was never meant to do collisions at 450 GeV (in the LHC at least)
Full program of machine protection, collimation, aperture and LBDS checks allowed “stable beams” to be declared.
Multi-bunch and higher intensities achieved
  16 bunches – total 1.85 x 1011
Luminosity scans tested successfully
Lots of events collected
  6 reasonably happy experiments

## Slide 15: Collisions at 450 GeV
After 20 days commissioning

## Slide 16: Nominal cycle: ramp
 | Date | Beam | Energy [GeV] | Comment
1 | 24/11/09 | 1 | 560 | Tunes
2 | 29/11/09 | 1 | 1043 | 1/3 integer
3 | 30/11/09 | 1/2 | 1180 | No full precycle No feedback
4 | 8/12/09 | 1/2 | 1180 | B1 lost after 3 minutes at top energy. Feedback on B2. Atlas saw collisions
5 | 13/12/09 | 1/2 | 800 | Feedback on both beams from here Lost B2 – BPM interlock
6 | 14/12/09 | 1/2 | 1180 | 1 hour “quiet beams” – collisions in all 4 experiments
7 | 15/12/09 | 1/2 | 1180 | Beam lost to rogue real-time packet
8 | 16/12/09 | 1/2 | 1180 | Squeeze/collisions
Not bad
8 ramp attempts

## Slide 17: Ramp 7 & 8 – bare tunes
Ramp looked good (and reproducible)
Both tune feedback and feed-forward operational
Encouraging

## Slide 18: Squeeze
First beam tests of betatron squeeze were successful!
  Mechanics of the squeeze works well.
  Good agreement with the expected beta values.
Some issues were identified and are being addressed
  Not the smoothest night shift ever seen in the CCC
Feedbacks:
  Orbit feedback will be needed as expected,
  If simulations are confirmed, tune feedback seem less critical.
One attempt in CMS: from 11 to 7 m.

## Slide 19: Magnet model
The knowledge of the magnetic model of the LHC is remarkable and has been one of the key elements of a very smooth beam commissioning
Huge parameter space, mistakes made, lessons learnt etc but…
Tunes, energy matching, optics close to the model already
Some discrepancies being hunted down (450 GeV particularly)
Bodes very well for the future.
Largest momentum offsets by sector:
  -0.27 per mil in sector 56 / beam1
  +0.32 per mil in sector 78 / beam2

## Slide 20
…in case of asynchronous beam dump
  TCDS (fixed) – 6 m long diluter protects extraction septum
  TCDQ (mobile) – 7 m long diluter kept at about 7-8 s from the beam, at all times
Beam Dump – very briefly

## Slide 21: LHC Beam Dump System
The beam dumping systems worked very well
  Only real failures were the synchronous-asynchronous dumps: solved after firmware upgrade

## Slide 22: Collimation
Full program of beam based positioning
System works as designed.
  Expected cleaning and leakage processes seen.
Possible to verify passive protection: losses at primary collimators.
Hierarchy established and respected in tests
Collimation setup remained valid over 6 days, relying on orbit reproducibility and optics stability
Even the Roman pots got a run out
Excellent initial beam based commissioning following careful preparation and tests
This and the beam dump are what stands between your silicon and 7 TeV protons (eventually).

## Slide 23: Collimation
Ralph Assmann

## Slide 24: Machine Protection System
Mission critical backbone
  Beam Interlock System
  Safe Machine Parameters
  Plus inputs to/from other systems (e.g. timing, BCT)
A large multitude of user inputs
The beam driving a subtle interplay of:
  LBDS, Collimation, protection devices, RF…
  Instrumentation (BLMs, BCT, BPMs…)
  Aperture
  Optics
Careful testing before beam
Full set of beam based tests
Clearly the critical path
Provides the mechanism to dump the beam in around 3 turns if anything out there decides it’s had enough

## Slide 25: Beam Instrumentation
Beam Position Monitors
  Excellent performance
  Very stable orbit (V drift ~ 15µm/h)
Beam Loss Monitors
  BLMs correctly removes the BEAM PERMIT signal if measurements are over threshold. No reliability issues observed.
Profile monitors
  Synchrotron light, wire-scanners operational
Base-Band-Tune (BBQ) system was a work horse from day one giving tune, chromaticity, coupling.
The Enabler
Excellent

## Slide 26: Availability during initial commissioning

## Slide 27: Unavailability

## Slide 28: 2010

## Slide 29: 1st quarter – restart
2nd quarter – physics start-up & LHC

## Slide 30: 3rd quarter – production running
4th quarter – ions

## Slide 31: 2010 overview
Hardware commission to 3.5 TeV
  New quench protection system (nQPS)
  Nearly there…
Beam commissioning continued
  Through to colliding, safe, stable, squeezed beams
Consolidation & pilot physics
Phased intensity increase and associated machine protection qualification
  Establish secure and reproducible operations and fully field test
  Move very, very carefully
Consolidation & physics

## Slide 32: Beam commissioning strategy 2010
Global machine checkout
450 GeV re-commissioning
System/beam commissioning continued Squeeze
Establish stable safe beams at 3.5 TeV
Collisions at 3.5 TeV
Full machine protection qualification
Collisions at 3.5 TeV squeezed
Ramp commissioning
Machine protection commissioning

## Slide 33: Timeline to first collisions - estimate
Phase | Days | 
Circulating beams | 2 | Essential checks
450 GeV re-commissioning | 7 | Injection, tune, Q’, C-, orbit, collimators, LBDS, instrumentation
450 optics checks | 3 | Beating, energy matching optimization
450 two beams | 1 | bumps as standard set-up, adjust TDI etc
450 GeV collisions | 1 | experiments on at 450 GeV
Ramp to 3.5 TeV | 5 | commission essential machine protection, experiments' dipoles on in ramp, orbit and tune feedback
3.5 TeV | 7 | machine protection (beam dumps, collimation etc.) optics
Pilot collisions un-squeezed | 3-5 | Safe beams at 3.5 TeV, test procedures etc.
Commission squeeze | 4 | feedbacks, collimation, aperture, bumps, machine protection checks, beam dumps etc.
Collisions squeezed – safe, stable beams | 7 | Stable beams up to safe beam limit

## Slide 34: 2010 to 2 MJ
Approved steps to 2 MJ
Main challenge will be learning to operate safely with destructive beams
pb-1

## Slide 35: 2010 - 2011
Months!

## Slide 36: 2011
3.5 TeV: run flat out at ~100 pb-1 per month
 | Nb | ppb | Total Intensity | MJ | beta* | Peak Lumi | Int Lumi per month [pb-1]
50 ns | 432 | 7 e10 | 3 e13 | 17 | 2.5 | 7.4 e31 | ~63 (34)
Pushing intensity limit | 796 | 7 e10 | 5.1 e13 | 31 | 2.5 | 1.4 e32 | ~116 (63)
Hope to be able to deliver around 1 fb-1
16% nominal

## Slide 37: LHC – startup 2010
It still works!
Circulating beams re-established last weekend

## Slide 38: Conclusions 1/2
A lot of hard work over the years has enable a truly impressive period of initial commissioning with beam.
Initial indications are that the LHC:
  is reproducible;
  magnetically well understood;
  optically in good shape;
  is armed with a mighty set of instrumentation, software, and hardware systems.
Lots still to sort out, in particular…
Operations, controls, instrumentation etc. have the capability to unnecessarily stress the machine protection system – issues must be resolved.
Long way to go before we are ready to go much beyond the safe beam limit

## Slide 39: Conclusions 2/2
Starting now ~4 weeks to establish stable, safe beams at 3.5 TeV and provide first collisions
Extended running period around the safe beam limit:
  With blocked MD periods as required
A very careful stepwise increase in intensity through the year with each step up in intensity to be followed by an extended running period
Aiming for 1031 - 1032 cm-2s-1 in 2010 and hopefully between 100 – 200 pb-1