## Slide 1: The LHC in Run 2: status and plans
Mike Lamont for the LHC team

## Slide 2
LS1 - descent into the underworld again

## Slide 3
« Old Splice » « Machined Splice » « Consolidated Splice »
« Insulation box »
« Cables » « New Splice »
Total interconnects in the LHC:
  1,695 (10,170 high current splices)
Number of splices redone: ~3,000 (~ 30%)
Number of shunts applied: > 27,000
And a lot more besides…

## Slide 4: Superconducting Magnets and Circuits Consolidation (SMACC)
Collaborations with NTUA (Athens), WUT (Wroclaw) and support of DUBNA
Monumental effort
Over 350 persons involved
Including preparation: ~1,000,000 working hours
No serious accidents!
Jean-Philippe Tock

## Slide 5
Following sector by sector cool-down

## Slide 6: Dipole training 1/2
154 dipoles per sector, powered in series
Ramp the current until single magnet quenches - “training quench”
Usually quench 3 – 4 other dipoles at the same time
Cryogenics recovery time: 6 – 8 hours

## Slide 7: Dipole training 2/2
Campaign summary
All magnets have been trained to well over 7 TeV in SM18 before installation
Extensive re-training in situ was not expected
Training: frictional energy released during conductor motion

## Slide 8: 7 TeV?
Assume all 412 firm 3 dipoles need re-training
  Some will required more than 1 re-training quench
Firm 2 (~5% to 6.5 TeV) and firm 1 (~ 1% to 6.5 TeV) will also play a part
Detailed analysis ongoing
  Clearly hundreds more t-quenches required
  Could type test 1 sector in 2015 YETS…
The essential feeling at the moment is: let’s get the machine running at 6.5 TeV first

## Slide 9: LHC - 2015
Target energy: 6.5 TeV
  looking good
Bunch spacing: 25 ns
  strongly favored by experiments (pile-up limit around 50)
Beta* in ATLAS and CMS: 80 to 40 cm
  Lower quench margins
  Lower tolerance to beam loss
  Hardware closer to maximum (beam dumps, power converters etc.)
Energy
  Electron-cloud
  UFOs
  More long range collisions
  Larger crossing angle, higher beta*
  Higher total beam current
  Higher intensity per injection
25 ns

## Slide 10
LHC bunch structure - 2015
1 SPS batch
(288 bunches)
26.7 km 2800 bunches
Abort gap
1 PS batch
(72 bunches)
25 ns bunch spacing
~2800 bunches
Nominal bunch intensity 1.15 x 1011 protons per bunch
New limits of ~2 PS batches per injection from the injection protection absorbers – will reduce the maximum number of bunches to around 2500

## Slide 11: 25 ns & electron cloud
10 eV
5 eV
200 eV
2 keV
Beam screen
25 ns
Typical e– densities1010–1012 m–3
Possible consequences:
  instabilities, emittance growth, desorption – bad vacuum
  excessive energy deposition in the cold sectors
Electron bombardment of a surface has been proven to reduce drastically the secondary electron yield (SEY) of a material. This technique, known as scrubbing, provides a mean to suppress electron cloud build-up.
Electron cloud significantly worse with 25 ns
SEY

## Slide 12: Squeeze in ATLAS
Image courtesy John Jowett
β* = 15 cm
7 microns
β* = 55 cm
 | βtriplet | Sigma triplet | β* | Sigma*
Nominal | ~4.5 km | 1.5 mm | 55 cm | 17 um
HL-LHC | ~20 km | 2.6 mm | 15 cm | 7 um

## Slide 13: Crossing angle
work with a crossing angle to avoid parasitic collisions.
geometric luminosity
reduction factor:
Separation: 10 -12 s

## Slide 14: 2015: beta* in IPs 1 and 5
Many things have changed. Start carefully and push performance later.
Start-up: β*= 80 cm – (very) relaxed
  2012 collimator settings
  11 sigma long range separation
  Aperture, orbit stability… checks ongoing
Ultimate in 2015: β*= 40 cm
  Possible reduction later in the year

## Slide 15: 2015 commissioning strategy
Low intensity commissioning of full cycle – 8 weeks
Pilot physics – low number of bunches
Special physics run: LHCf and luminosity calibration
Scrubbing for 50 ns
Intensity ramp-up with 50 ns
  Characterize vacuum, heat load, electron cloud, losses, instabilities, UFOs, impedance
Scrubbing for 25 ns
Ramp-up 25 ns operation with relaxed beta*
Possibly commission lower beta*
25 ns operation

## Slide 16: 2015 Q2
FIRST BEAM 5th APRIL
SCRUBBING FOR 50 ns
FIRST STABLE BEAM 3rd JUNE
PILOT PHYSICS
8 weeks beam commissioning
Pilot physics – up to at least 40 bunches per beam
5 days special physics at beta* = 19 m (VdM, LHCf, TOTEM & ALFA)
Start technical stop – 15th June

## Slide 17: Q3/Q4 2015
SCRUBBING FOR 25 ns

## Slide 18: 2015 – latest schedule
Phase | Days
Initial Commissioning | 57
Scrubbing | 23
Special physics run 1 (LHCf/VdM) | 5
Proton physics 50 ns | 9 + 21
Proton physics 25 ns | 70
Special physics run 2 (TOTEM/VdM) | 7
Machine development (MD) | 15
Technical stops | 15
Technical stop recovery | 3
Ion setup/Ion run | 4 + 24
Total | 253 (36 weeks)

## Slide 19: Schedule - comments
Picked up some 4 weeks delay from:
  Powering tests/quench training overrun
  Earth fault resolution
Proton-proton physics down to 70 days
  Decrease in beta*to be reviewed after gaining some experience (although considerable progress made during commissioning)
Ion program unaffected
  Proton-proton reference data will be difficult to squeeze in

## Slide 20: Commissioning
System commissioning with beam
  Collimation
  Beam dump
  Feedbacks
  Beam instrumentation
  Machine protection
  RF
  Transverse damper
  Injection
Machine characterization
  Optics measurement and correction
  Magnetic machine
Operations
  High intensity injection
  Ramp to 6.5 TeV
  Squeeze
Injection - probe
Ramp - probe
Flat-top - probe
Injection - nominal
Squeeze - nominal
Ramp - nominal
Squeeze - probe
Flat-top - nominal
Collide & validation
Complete
Ongoing

## Slide 21: Milestones
Circulating beam | Sunday 5th April
Ramp to 6.5 TeV | Friday 10th April
First 13 TeV collisions | Wednesday 20th May
First Stable beams | Wednesday 3rd June
Working throughout with:
  probes (5e9 protons per bunch) or
  1 or 2 nominals (1.2e11 protons per bunch)
THIS IS NOT BAD!

## Slide 23: 6.5 TeV for the first time
01:03 10th April

## Slide 24
2 nominal bunches per beam
De-squeezed to 19 m

## Slide 25: Of note 1/2
It’s not a new machine – a lot of lessons learnt from Run 1
Excellent and improved system performance
  Beam Instrumentation
  Transverse feedback
  RF
  Collimation
  Injection and beam dump systems
  Vacuum
  Machine protection
Improved software & analysis tools
Experience!

## Slide 26: Of note 2/2
Magnetically reproducible as ever
Optically good, corrected to excellent
Behaving well at 6.5 TeV
  One additional training quench so far
Operationally well under control
  Injection, ramp, squeeze, de-squeeze
Still have to face the intensity ramp-up
  UFOs, e-cloud, vacuum, beam induced heating, instabilities

## Slide 27
Rogelio and OMC team
Optics - 40 cm

## Slide 28: Off momentum loss map 6.5 GeV
Novel features of collimation system – BPM equipped tertiary collimators, automatic beam based set-up

## Slide 29
Of course we’ve had a few issues…

## Slide 30: MUFOs in 15R8
Multiple loss events after a short time at 6.5 TeV compatible with particles falling into the beam
  loss patterns point to a specific position in the middle of a dipole magnet
  Quenched twice, numerous BLM triggered dumps…
Q14
Q15
highest
loss
quench
X

## Slide 31: Aperture restriction in 15R8
Aperture restriction measured at injection and 6.5 TeV
Presently running with orbit bumps
  -3 mm in H, +1 in V, to optimize available aperture
  aperture probably not limiting for operation
Behaviour with higher intensities and bunch trains still unknown
MUFOs went away but last week
D. Mirarchi
ULO (Unidentified Lying Object)

## Slide 32
Somewhat worrying

## Slide 33: 2015: ATLAS and CMS performance
 | Nc | Beta* | ppb | EmitN | Lumi [cm-2s-1] | Days (approx) | Int lumi | Pileup
50 ns | 1300 | 80 | 1.2e11 | 2.5 | 4.8e33 | 21 | ~1 fb-1 | 25
2015.1 | 2448 | 80 | 1.2e11 | 3.1 | 7.1e33 | 35 | ~4 fb-1 | 21
2015.2 | 2448 | 40 | 1.2e11 | 3.1 | 1.2e34 | 30 | ~5 fb-1 | 35
Conservative beta* to start
Nominal bunch population
Reasonable emittance into collisions
Assume same machine availability as 2012
Official GPD luminosity target for the year was 10 fb-1
Now on the challenging side – let’s say 5 to 10 fb-1

## Slide 34: Run 2
EYETS – Extended Year End Technical Stop – 19 weeks – CMS pixel upgrade
Mid-year 2018 stop will be pushed towards year end (not yet official)

## Slide 35: Run 2 performance
Aim to start 2016 in production mode
  6.5 TeV, machine scrubbed for 25 ns operation
  Beta* = 40 cm in ATLAS and CMS
  New injection protection absorbers – full injection
  Peak lumi limited to 1.7e34 by inner triplets
 | Peak lumi E34 cm-2s-1 | Days proton physics | Approx. int lumi [fb-1]
2015 | 1.2 | 70 | 5 - 10
2016 | 1.5 | 160 | 35
2017 | 1.7 | 160 | 45
2018 | 1.7 | 40 | 10

## Slide 36: Conclusions
Looking good at 6.5 TeV
  Impressive progress so far
  Fabulous job done in LS1 and during powering tests
  Lot of lessons learnt in Run 1
Next challenge - higher intensity and e-cloud
Fundamentals look sound, no show stoppers for the moment
  Some irritants – resolution cost time
2015 will be a short year for proton physics but lay foundations for production for the rest of Run 2
It takes a remarkable effort by a large number of teams to prepare and exploit the LHC.