## Slide 1: News from the LHC machine
ATLAS Week: The First 13 TeV Data!
15th June 2015
Mike Lamont for the LHC team

## Slide 2: LHC - 2015
Target energy: 6.5 TeV
  looking good after a major effort
Bunch spacing: 25 ns
  strongly favored by experiments – pile-up
Beta* in ATLAS and CMS: 80 to 40 cm
  Lower quench margins
  Lower tolerance to beam loss
  Hardware closer to maximum (beam dumps, power converters etc.)
Energy
  Electron-cloud
  UFOs
  More long range collisions
  Larger crossing angle, higher beta*
  Higher total beam current
  Higher intensity per injection
25 ns

## Slide 3
Nominal LHC bunch structure
1 SPS batch
(288 bunches)
26.7 km 2800 bunches
Abort gap
1 PS batch
(72 bunches)
25 ns bunch spacing
~2800 bunches
Nominal bunch intensity 1.15 x 1011 protons per bunch

## Slide 4: TDI limitations
Main blocks: h-BN
However during bake-out tests…
TDI: movable vertical absorbers – 4.2 m in length – down stream of injection kickers
SEPTA
KICKERS
TDI

## Slide 5: TDI Limits
TDI hBN block cannot withstand temperatures higher than 450 ◦C (B2O3 reactant melting temperature)  limit the maximum number of bunches which can hit the TDI (maximum allowed temperature = 400 ◦C )
J. Uythoven A. Lechner
New limits of ~2 PS batches per injection from the injection protection absorbers will reduce the maximum number of bunches to around 2400

## Slide 6: TDI limited injection schemes
25 ns nominal
  25ns_2388b_2376_2061_2124_144bpi19inj
BCMS
  25ns_2076b_2064_1690_1768_96bpi23injB
50 ns
  50ns_1230b_1188_51_1083_108bpi13inj
Proposed intensity ramp-up
  50ns: 3-12-48-144-288-480-768-1092-1230
  25 ns: 3-12-48-72-144-288-432-588-1164-1740-2388

## Slide 7: Squeeze in ATLAS
Image courtesy John Jowett
β* = 15 cm
7 microns
β* = 55 cm
 | βtriplet | Sigma triplet | β* | Sigma*
Nominal | ~4.5 km | 1.5 mm | 55 cm | 17 um
HL-LHC | ~20 km | 2.6 mm | 15 cm | 7 um

## Slide 8: 2015: beta* in IPs 1 and 5
Many things have changed. Start carefully and push performance later.
Start-up: β*= 80 cm – (very) relaxed
  2012 collimator settings
  11 sigma long range separation
  Aperture, orbit stability… looking good
Ultimate in 2015: β*= 40 cm
  Possible reduction later in the year

## Slide 9: 2015 commissioning strategy
Low intensity commissioning of full cycle – 8 weeks
Pilot physics – low number of bunches
Special physics run: LHCf (and luminosity calibration)
Scrubbing for 50 ns
Intensity ramp-up with 50 ns
  Characterize vacuum, heat load, electron cloud, losses, instabilities, UFOs, impedance
Scrubbing for 25 ns
Ramp-up 25 ns operation with relaxed beta*
Possibly commission lower beta*
25 ns operation with lower beta*

## Slide 10: 2015 Q2
FIRST BEAM 5th APRIL
SCRUBBING FOR 50 ns
FIRST STABLE BEAM 3rd JUNE
PILOT PHYSICS
8 weeks beam commissioning
Pilot physics – up to ~40 bunches per beam
5 days special physics at beta* = 19 m LHCf, (VdM, TOTEM & ALFA - postponed)
Start technical stop – 15th June

## Slide 11: Commissioning
System commissioning with beam
  Collimation
  Beam dump
  Feedbacks
  Beam instrumentation
  Machine protection
  RF
  Transverse damper
  Injection
Machine characterization
  Optics measurement and correction
  Magnetic machine
  Aperture
Operations
  Inject, ramp, squeeze, collide
Injection - probe
Ramp - probe
Flat-top - probe
Injection - nominal
Squeeze - nominal
Ramp - nominal
Squeeze - probe
Flat-top - nominal
Collide & validation
Huge thanks due to the teams involved

## Slide 12: Milestones
Circulating beam | Sunday 5th April
Ramp to 6.5 TeV | Friday 10th April
First 13 TeV collisions | Wednesday 20th May
First Stable beams | Wednesday 3rd June
Working throughout with:
  probes (5e9 protons per bunch) or
  1 or 2 nominals (1.2e11 protons per bunch)
NOT BAD

## Slide 13: 6.5 TeV for the first time
01:03 10th April

## Slide 14
10:40 3rd June

## Slide 15: LHCf
fill | Stable beams | nb-1 | bun
3846 | 1h55m | 0.1 | 39 pilots
3847 | 2h16m | 0.28 | 39 pilots
3848 | 2h42m | 0.91 | 12 nominal
3850 | 2h49m | 1.95 | 39 nominal
3851 | 11h13m | 6.81 | 39 nominal
3855 | 14h15m | 6.49 | 39 nominal
Target: 10 nb-1

## Slide 16: Last weekend: fills 3857 & 3858
Number of bunches | 50
Number of colliding bunches (ATLAS/CMS) | 38
Peak luminosity | 1.45 x 1032 cm-2s-1
Integrated luminosity | 3.8 + 3.5 pb-1
Peak <Events>/BX | ~27

## Slide 17: Of note 1/2
A lot of lessons learnt from Run 1
Excellent and improved system performance:
  Beam Instrumentation
  Transverse feedback
  RF
  Collimation
  Injection and beam dump systems
  Vacuum
  Machine protection
Improved software & analysis tools
Experience!

## Slide 18: Of note 2/2
Magnetically reproducible as ever
Optically good, corrected to excellent
Aperture
  measurements at top energy, 80cm, before and after collision indicate that the aperture is ok and compatible with the present collimation hierarchy. This is a very good result.
Behaving well at 6.5 TeV
  Two additional training quenches so far
Operationally well under control
  Injection, ramp, squeeze, de-squeeze
Still have to face the intensity ramp-up
  UFOs, e-cloud, vacuum, beam induced heating, instabilities

## Slide 19
OMC team
Optics - 40 cm

## Slide 21: Off momentum loss map 6.5 TeV
Novel features of collimation system – BPM equipped tertiary collimators, automatic beam based set-up

## Slide 22: Aperture

## Slide 23: MUFOs in 15R8
Multiple loss events after a short time at 6.5 TeV compatible with particles falling into the beam
  loss patterns point to a specific position in the middle of a dipole magnet
  Quenched twice, numerous BLM triggered dumps…
Q14
Q15
highest
loss
quench
X
B1
B2

## Slide 24: Aperture restriction in 15R8
Aperture restriction measured at injection and 6.5 TeV
Presently running with orbit bumps
  -3 mm in H, +1 in V, to optimize available aperture
  aperture probably not limiting for operation
Behaviour with higher intensities and bunch trains still unknown
MUFOs went away but 2 weeks ago…
D. Mirarchi
ULO (Unidentified Lying Object)

## Slide 25
This following a 15R8 aperture scan – no more scans!
Concern is that e-cloud could kick things off again

## Slide 26: Q3/Q4 2015
SCRUBBING FOR 25 ns

## Slide 27: 2015 – latest schedule
Phase | Days
Initial Commissioning | 57
Scrubbing | 23
Special physics run 1 (LHCf/VdM) | 5
Proton physics 50 ns | 7 + 21
Proton physics 25 ns | 70
Special physics run 2 (TOTEM/VdM) | 7
Machine development (MD) | 15
Technical stops | 15
Technical stop recovery | 3
Ion setup/Ion run | 4 + 24
Total | 253 (36 weeks)

## Slide 28: Schedule - comments
Picked up some 4 weeks delay from:
  Powering tests/quench training overrun
  Earth fault resolution
Proton-proton physics down to 70 days
  Decrease in beta* to be reviewed after gaining some experience (although considerable progress made during commissioning)
Ion program unaffected
  Proton-proton reference data to be scheduled
Still some commissioning/machine protection stuff to mop up coming out of technical stop and before 50 ns ramp-up

## Slide 29: 2015: ATLAS and CMS performance
 | Nc | Beta* | ppb | EmitN | Lumi [cm-2s-1] | Days (approx) | Int lumi | Pileup
50 ns | 1300 | 80 | 1.2e11 | 2.5 | 4.8e33 | 21 | < 1 fb-1 | 25
2015.1 | 2376 | 80 | 1.2e11 | 3.1 | 7.0e33 | 35 | ~5 fb-1 | 21
2015.2 | 2376 | 40 | 1.2e11 | 3.1 | 1.2e34 | 30 | ~4 fb-1 | 35
Beta* = 80 cm, possible reduction later in year (count 4 days + ramp-up)
Nominal bunch population for 50 and 25 ns
Reasonable emittance into collisions
Assume slightly worse machine availability than in 2012
TDI limit: max colliding bunches 2376
Official GPD luminosity target for the year was 10 fb-1
Now on the challenging side – let’s say 5 to 10 fb-1
Hubner factor = 0.15

## Slide 30: Day by day projection
MD & 25 ns scrubbing
TS2
Special
runs
Possible beta* reduction plus fast ramp-up
Including intensity ramp-ups and steadily increasing physics efficiency
50 ns

## Slide 31
50 ns
Scrubbing
50 ns beam
~1400 bunches
1.7 x 1011 p/b
Scrubbing: Goal and strategy
  Goal: accumulate e- dose on the beam chambers to mitigate e-cloud effects with 50 ns and 25 ns beams
  Strategy: gradually increase the e- flux (50 ns  25 ns  doublets) while keeping under control vacuum, heat loads and beam degradation
Giovanni Iadarola and Giovanni Rumolo

## Slide 32
50 ns
Scrubbing
25 ns Scrubbing
Sufficient mitigation
for 50 ns physics
25 ns beam
~2800 bunches
1.15 x 1011 p/b
50 ns beam
~1400 bunches
1.7 x 1011 p/b
Scrubbing: Goal and strategy
  Goal: accumulate e- dose on the beam chambers to mitigate e-cloud effects with 50 ns and 25 ns beams
  Strategy: gradually increase the e- flux (50 ns  25 ns  doublets) while keeping under control vacuum, heat loads and beam degradation
Giovanni Iadarola and Giovanni Rumolo

## Slide 33
50 ns
Scrubbing
25 ns Scrubbing
Sufficient mitigation
for 50 ns physics
25 ns beam
~2800 bunches
1.15 x 1011 p/b
50 ns beam
~1400 bunches
1.7 x 1011 p/b
Scrubbing: Goal and strategy
  Goal: accumulate e- dose on the beam chambers to mitigate e-cloud effects with 50 ns and 25 ns beams
  Strategy: gradually increase the e- flux (50 ns  25 ns  doublets) while keeping under control vacuum, heat loads and beam degradation
Giovanni Iadarola and Giovanni Rumolo

## Slide 34
50 ns
Scrubbing
25 ns Scrubbing
Doublet Scrubbing
No e-cloud in the dipoles 
Doublet beam
~900 doublets
0.7 x 1011 p/b
25 ns beam
~2800 bunches
1.15 x 1011 p/b
50 ns beam
~1400 bunches
1.7 x 1011 p/b
Scrubbing: Goal and strategy
  Goal: accumulate e- dose on the beam chambers to mitigate e-cloud effects with 50 ns and 25 ns beams
  Strategy: gradually increase the e- flux (50 ns  25 ns  doublets) while keeping under control vacuum, heat loads and beam degradation
Giovanni Iadarola and Giovanni Rumolo

## Slide 36: Conclusions
Looking good at 6.5 TeV
  Great job done in LS1 and during powering tests
  Impressive progress so far, lot of lessons learnt in Run 1 and fed-forward
Fundamentals look sound, no show stoppers for the moment
  Some irritants – resolution cost time
Next challenge - higher intensity and e-cloud
2015 will be a short year for proton physics but lay the foundations for production in the rest of Run 2