## Slide 1: LHC machine status
LHCC 3rd June 2015
Mike Lamont for the LHC team

## Slide 2
In parallel with sector by sector cool-down

## Slide 3: Dipole training 1/2
154 dipoles per sector, powered in series
Ramp the current until single magnet quenches - “training quench”
Usually quench 3 – 4 other dipoles at the same time
Cryogenics recovery time: 6 – 8 hours

## Slide 4: Dipole training 2/2
Campaign summary
All magnets have been trained to well over 7 TeV in SM18 before installation
Extensive re-training in situ was not expected
Training: frictional energy released during conductor motion

## Slide 5: LHC - 2015
Target energy: 6.5 TeV
  looking good
Bunch spacing: 25 ns
  strongly favored by experiments (pile-up limit around 50)
Beta* in ATLAS and CMS: 80 to 40 cm
  Lower quench margins
  Lower tolerance to beam loss
  Hardware closer to maximum (beam dumps, power converters etc.)
Energy
  Electron-cloud
  UFOs
  More long range collisions
  Larger crossing angle, higher beta*
  Higher total beam current
  Higher intensity per injection
25 ns

## Slide 6
LHC bunch structure - 2015
1 SPS batch
(288 bunches)
26.7 km 2800 bunches
Abort gap
1 PS batch
(72 bunches)
25 ns bunch spacing
~2800 bunches
Nominal bunch intensity 1.15 x 1011 protons per bunch
New limits of ~2 PS batches per injection from the injection protection absorbers – will reduce the maximum number of bunches to around 2500

## Slide 7: 2015: beta* in IPs 1 and 5
Many things have changed. Start carefully and push performance later.
Start-up: β*= 80 cm – (very) relaxed
  2012 collimator settings
  11 sigma long range separation
  Aperture, orbit stability… checks ongoing
Ultimate in 2015: β*= 40 cm
  Possible reduction later in the year

## Slide 8: 2015 commissioning strategy
Low intensity commissioning of full cycle – 8 weeks
Pilot physics – low number of bunches
Special physics run: LHCf and luminosity calibration
Scrubbing for 50 ns
Intensity ramp-up with 50 ns
  Characterize vacuum, heat load, electron cloud, losses, instabilities, UFOs, impedance
Scrubbing for 25 ns
Ramp-up 25 ns operation with relaxed beta*
Possibly commission lower beta*
25 ns operation

## Slide 9: 2015 Q2
FIRST BEAM 5th APRIL
SCRUBBING FOR 50 ns
FIRST STABLE BEAM 3rd JUNE
PILOT PHYSICS
8 weeks beam commissioning
Pilot physics – up to at least 40 bunches per beam
5 days special physics at beta* = 19 m (VdM, LHCf, TOTEM & ALFA)
Start technical stop – 15th June

## Slide 10: Q3/Q4 2015
SCRUBBING FOR 25 ns

## Slide 11: 2015 – latest schedule
Phase | Days
Initial Commissioning | 57
Scrubbing | 23
Special physics run 1 (LHCf/VdM) | 5
Proton physics 50 ns | 9 + 21
Proton physics 25 ns | 70
Special physics run 2 (TOTEM/VdM) | 7
Machine development (MD) | 15
Technical stops | 15
Technical stop recovery | 3
Ion setup/Ion run | 4 + 24
Total | 253 (36 weeks)

## Slide 12: Schedule - comments
Picked up some 4 weeks delay from:
  Powering tests/quench training overrun
  Earth fault resolution
Proton-proton physics down to 70 days
  Decrease in beta* to be reviewed after gaining some experience (although considerable progress made during commissioning)
Ion program unaffected
  Proton-proton reference data will be difficult to squeeze in

## Slide 13: Commissioning
System commissioning with beam
  Collimation
  Beam dump
  Feedbacks
  Beam instrumentation
  Machine protection
  RF
  Transverse damper
  Injection
Machine characterization
  Optics measurement and correction
  Magnetic machine
Operations
  High intensity injection
  Ramp to 6.5 TeV
  Squeeze
Injection - probe
Ramp - probe
Flat-top - probe
Injection - nominal
Squeeze - nominal
Ramp - nominal
Squeeze - probe
Flat-top - nominal
Collide & validation
Complete
Ongoing

## Slide 14: Milestones
Circulating beam | Sunday 5th April
Ramp to 6.5 TeV | Friday 10th April
First 13 TeV collisions | Wednesday 20th May
First Stable beams | Wednesday 3rd June
Working throughout with:
  probes (5e9 protons per bunch) or
  1 or 2 nominals (1.2e11 protons per bunch)
THIS IS NOT BAD!

## Slide 16: 6.5 TeV for the first time
01:03 10th April

## Slide 17
2 nominal bunches per beam
De-squeezed to 19 m
21st May

## Slide 18: First Stable Beams
07:00 Injection delayed
  Issue with interlocked BPM
  SPS beam dump kicker fault
08:25 Start ramp
08:38 Beams dump at 4.1 TeV
  Software interlock related to interlock BPM fix!
09:46 Start ramp
10:15 Start squeeze
10:40 Stable beams
This morning

## Slide 20: Of note 1/2
A lot of lessons learnt from Run 1
Excellent and improved system performance:
  Beam Instrumentation
  Transverse feedback
  RF
  Collimation
  Injection and beam dump systems
  Vacuum
  Machine protection
Improved software & analysis tools
Experience!

## Slide 21: Of note 2/2
Magnetically reproducible as ever
Optically good, corrected to excellent
Aperture
  measurements at top energy, 80cm, before and after collision indicate that the aperture is ok and compatible with the present collimation hierarchy. This is a very good result.
Behaving well at 6.5 TeV
  One additional training quench so far
Operationally well under control
  Injection, ramp, squeeze, de-squeeze
Still have to face the intensity ramp-up
  UFOs, e-cloud, vacuum, beam induced heating, instabilities

## Slide 22
OMC team
Optics - 40 cm

## Slide 24: Off momentum loss map 6.5 TeV
Novel features of collimation system – BPM equipped tertiary collimators, automatic beam based set-up

## Slide 25: Aperture

## Slide 26: MUFOs in 15R8
Multiple loss events after a short time at 6.5 TeV compatible with particles falling into the beam
  loss patterns point to a specific position in the middle of a dipole magnet
  Quenched twice, numerous BLM triggered dumps…
Q14
Q15
highest
loss
quench
X
B1
B2

## Slide 27: Aperture restriction in 15R8
Aperture restriction measured at injection and 6.5 TeV
Presently running with orbit bumps
  -3 mm in H, +1 in V, to optimize available aperture
  aperture probably not limiting for operation
Behaviour with higher intensities and bunch trains still unknown
MUFOs went away but last week
D. Mirarchi
ULO (Unidentified Lying Object)

## Slide 28
This following a 15R8 aperture scan. A worry.

## Slide 29: 2015: ATLAS and CMS performance
 | Nc | Beta* | ppb | EmitN | Lumi [cm-2s-1] | Days (approx) | Int lumi | Pileup
50 ns | 1300 | 80 | 1.2e11 | 2.5 | 4.8e33 | 21 | ~1 fb-1 | 25
2015.1 | 2448 | 80 | 1.2e11 | 3.1 | 7.1e33 | 35 | ~4 fb-1 | 21
2015.2 | 2448 | 40 | 1.2e11 | 3.1 | 1.2e34 | 30 | ~5 fb-1 | 35
Conservative beta* to start
Nominal bunch population
Reasonable emittance into collisions
Assume same machine availability as 2012
Official GPD luminosity target for the year was 10 fb-1
Now on the challenging side – let’s say 5 to 10 fb-1

## Slide 30: Special physics runs
First run 5 day run scheduled for next week
  LHCf and luminosity calibration with VdM scans. TOTEM and ALFA to piggy-back.
  De-squeeze to 19-19-19-24 m commissioned (and test collision delivered)
  Roman Pot set-up and validation still to do
  Pilot physics and ~10 pb-1 to be delivered before but in good shape
Second 7 day run for later in year
  VdM and 90 m run for TOTEM and ALFA
  Procedures and tools for set-up in good shape – should allow effective exploitation of scheduled time

## Slide 31
50 ns
Scrubbing
25 ns Scrubbing
Doublet Scrubbing
No e-cloud in the dipoles 
PyECLOUD simulations for the LHC arc dipoles
Doublet beam
~900 doublets
0.7 x 1011 p/b
25 ns beam
~2800 bunches
1.15 x 1011 p/b
50 ns beam
~1400 bunches
1.7 x 1011 p/b
“Doublet” scrubbing beam: PyECLOUD simulation results
  Buildup simulations show a substantial enhancement of the e-cloud with the “doublet” bunch pattern
Cryogenics limit
Giovanni Iadarola and Giovanni Rumolo

## Slide 32: Conclusions
Looking good at 6.5 TeV
  Great job done in LS1 and during powering tests
  Impressive progress so far, lot of lessons learnt in Run 1 and fed-forward
Fundamentals look sound, no show stoppers for the moment
  Some irritants – resolution cost time
Next challenge - higher intensity and e-cloud
2015 will be a short year for proton physics but lay foundations for production for the rest of Run 2