## schedule
Goals:
Commissioning with bunch trains (150 ns)
No contingency: assumed 100% beam time
| Day | Start | Time (h) | Activity | Comments | Beam type
5 | Sun | M | 4 | Transverse feedback setting up: noise reduction (450 GeV - single nominal bunch) |  | INDIV
5 | Sun | A | 1 | Closed oorbit at 450 GeV with crossing angle ON | Non-closuire correction based on measurement done on 4/9/2010 | PROBE, INDIV
5 | Sun | A | 7 | Injection / injection protection: crossing angles ON | TDI/TCLI setup in LHC and protection validation (pilot bunch) | PROBE, INDIV
5 | Sun | A | 1 | Splash events for CMS | Beam 1 only | PROBE
5 | Sun | N | 7 | ramp at 10 A/s with single bunch/beam 1e10 + squeeze and crossing angles ON during the ramp - measurement of non closure during the squeeze | Feedforward from previous measurements should be implemented Chromaticity measurement during the ramp - collimators open. Crossing angles on during the ramp | PROBE
6 | Mon | M | 8 | Injection / injection protection - crossing angles ON | Steering of trajectory in TLs and adjustment of TCDIs | PROBE, INDIV
6 | Mon | A | 8 | Collimation set-up at 450 GeV/c |  | INDIV
6 | Mon | N | 8 | Transverse feedback setting up: noise reduction (450 GeV - single nominal bunch) - crossing angle ON |  | INDIV
7 | Tue | M | 2 | RF set-up with 4 bunches spaced of 150 ns and cavity configuration with all caivites ON |  | LHC3
7 | Tue | M | 8 | Injection / injection protection - crossing angles ON | Steering of trajectory in TLs and adjustment of TCDIs | PROBE, LHC3
7 | Tue | A | 8 | Loss maps at 450 GeV/asynch beam dump | Single nominal bunch | INDIV
7 | Tue | N | 8 | PLL setting-up |  | PROBE, INDIV
8 | Wed | M | 8 | ramp at 10 A/s with single bunch/beam 1e11 - Collimation set-up at 3.5 TeV crossing angle ON - preceed through squeeze according to progress - reference orbit set-up - Transverse ffedback checks during the ramp | Longitudinal blow-up ON? BLM monitor factor reduction at TCTs before ramp | INDIV
8 | Wed | A | 6 | Collimation set-up at 3.5 TeV - ramp as required - up to 2 nominal bunches / beam | Longitudinal blow-up ON? BLM monitor factor reduction at TCTs before ramp | INDIV
8 | Wed | A | 2 | RF set-up with 4 bunches spaced of 150 ns and cavity configuration with all caivites ON |  | LHC3
8 | Wed | N | 8 | Injection / injection protection: crossing angles ON | Study and quantify losses at injection due to RF system | PROBE, LHC3
9 | Thu | M | 8 | Collimation set-up at 3.5 TeV - ramp as required - up to 2 nominal bunches / beam | Longitudinal blow-up ON? BLM monitor factor reduction at TCTs before ramp - Stefano on shift | INDIV
9 | Thu | A | 8 | Collimation set-up at 3.5 TeV - ramp as required - up to 2 nominal bunches / beam | Longitudinal blow-up ON? BLM monitor factor reduction at TCTs before ramp | INDIV
9 | Thu | N | 8 | PLL setting-up |  | PROBE, INDIV
10 | Fri | M | 8 | Injection / injection protection: crossing angles ON | Validation checks of TCDI system (pilot bunch) | PROBE, LHC3
10 | Fri | A | 8 | Loss maps in collision + asynch dump - 2 nominal bunches/beam |  | INDIV
10 | Fri | N | 8 | PLL setting-up |  | PROBE, INDIV
11 | Sat | M | 8 | Reserve
11 | Sat | A | 8 | Loss maps in collision + asynch dump - 2 nominal bunches/beam |  | INDIV
11 | Sat | N | 8 | Reserve
12 | Sun | M | 8 | Injection / injection protection: bunch trains up to 4x12 bunches (150 ns spacing) - crossing angles ON | Validation checks of TCDI system (pilot bunch) CAN INJECT 8 and 12b ONLY AFTER THIS STEP | PROBE, LHC3
12 | Sun | A | 8 | Reserve | No TFB expert available | LHC3
12 | Sun | N | 8 | Reserve
13 | Mon | M | 8 | Injection / injection protection: bunch trains up to nx4x12 bunches (150 ns spacing) - crossing angles ON | Inject trains of 8 and 12 bunches (150 ns) to LHC | PROBE, LHC3
13 | Mon | A | 8 | RF set--up with more batches at injection |  | PROBE, LHC3
13 | Mon | N | 8 | Test of new collimator functions - without beam?
14 | Tue | M | 8 | Collisions - ramp with new functions |  | LHC3
|  |  |  | Collisions and progressive increase of number of batches |  | LHC3
|  |  | parasitic | Check of BSRT (bunch in bucket 1 and possibly bunch in the last bucket before the abort gap) ==> A. Boccardi
|  |  | 8 | Alice spctrometer compensation for different polarities (8 hours)
|  |  | 8 | Setting-up of the 2in 1 collimators