## MD5075ns
|  |  |  | Who | Beam | Comments
Wed | 5:00 | 1 | Beam dump
Wed | 6:00 | 3 | Access (BI interventions) and pre-cycle | BI | No | MAD and RP required
Wed | 9:00 | 4 | Machine interlock checks | MPP (Joerg's alter ego) | Pilot | Check MKI delays - BLM thresholds for the triplets (monitor factors to be changed). Otehr RF parameters to be changed?
Wed | 13:00 | 7 | Injection and damper checks (RF checks) for 75 ns beam up to 2 trains of 24 bunches spaced by 225 ns | OP, ABP, Brennan et al.., Wolfgang, Philippe, Vacuum, Cryo, BI (Federico, Ralph, Rhodri) | 75 ns (8, 24, 2x24 bunches) | BI checks in parallel | Glitch check
Wed | 20:00 | 10 | Injection of trains of 24 or 48 bunches (1.85 microsec separation) (we should have space to inject up to 23 trains of 24 bunches). This must be done in steps with OK from Cryo and Vacuum | OP, ABP, Vacuum, Cryo, BI (Federico, Ralph, Rhodri) | 75 ns (8, 24, 2x24 bunches) | BI checks at the beginning
Thu | 6:00 | 12 | Qualification of the electron cloud build-up with 75 ns | OP, Vacuum, Cryo | 75 ns (8, 24, 2x24 bunches) - variable intensity - variable batch spacing | Variable intensity during working hours
Thu | 18:00 | 4 | Switch to 50 ns - Injection and Damper checks | OP, ABP, Brennan et al.., Wolfgang, Philippe, Vacuum, Cryo, BI (Federico, Ralph, Rhodri) | 50 ns (12, 36 bunches). | BI checks in parallel
Thu | 22:00 | 5 | Stability measurements with 50 and 75 ns beams | OP, ABP, Vacuum Cryo, BI (Federico, Ralph, Rhodri), Wolfgang | 50 (12,36 bunches)/75 ns beams (8, 24 bunches, 2x24 bunches) | BI checks at the beginning | Possibility to switch OFF timings for B1/B2 and H and V independently
Fri | 3:00 | 6 | Test ramp (no squeeze). Chromaticity measurement. In the mean time check of the 50 ns beam in the injectors | OP | pilots
Fri | 9:00 | 8 | Ramp with 108 bunches (no squeeze) - 9x12 bunches - 50 ns beam | OP, ABP, Vacuum, Cryo, BI (Federico) |  | Recording of beam profile with BSRT
Fri | 17:00 | 4 | Interlock checks | MPP (Joerg's alter ego) | single ion bunch | Check MKI delays - BLM thresholds for the triplets (monitor factors to be changed). Otehr RF parameters to be changed?
Fri | 21:00 |  | Ramp for ion physics |  |  | Which filling scheme to start?
64