## Slide 1: Wednesday 28th September
04:35 fill #2165 in Physics, initial lumi’s 3.2e33
10:23 beam dump, loss of RCBCH6.R7B2 causes PIC trigger. Integrated lumi 52 pb-1.
“2 hour access”:
13:50 “The problem with the MAD in UJ83 is finished”
15:25 Start pre-cycle
16:50 Test of new release of XPOC: OK
17:07 Begin abort gap cleaning test @ 3.5 TeV… but problem with OFS
  New software release (interface)… not tested, can’t role back, need to fix…
20:30 Inject for abort gap cleaning test: 36 bunches
20:52 Dumped beam in ramp as orbit feedback not working in ramp
  Abort gap cleaning test postponed to next week
22:00 Roll back OFSU - Inject to check OFS – test ramp 2 pilots
01:26 Fill for physics, during squeeze 60 % UFO, TCLA.A6L7.B2
02:55 Stable Beam: L = 3.2e33
07:02 Beams dump, integrated 40 pb-1, UPS failure, trip S45 and S56 UPS problems UJ56
Need access for UPS

## Slide 2: “2 hour access”
Several accesses:
  EPC intervention on RCBV28.L3B2 (initiater)
  ATLAS ZDC intervention in UJ14 & UJ16
  TOTEM intervention into UXC was cancelled
  CV intervention in UJ56 for a water leak
  Some QPS
With problems of the MAD in UJ83 it actually took 5 hours before the pre-cycle could be started

## Slide 3: The orbit feedback saga
12:17 OFSU updated & restarted with new additional interface fields for the OFC setting
  Not tested as there is no beam….
17:30 Beam back; OFC does not work properly
  Specialist who released new software is not at CERN anymore and difficult to get hold of
  Specialist tries to roll back from home, but this does not work
  Comes into work and tries to fix the new version
20:09 Release new OFSU Server software
  Tested in detail, except functionality during ramp not tested, rest working
20:52 …dumped beam during ramp, OFC not working
21:00 Roll back to old OFSU version – works with default optics
  22:00 inject to check OFS
  OF not working when loading the correct optics…Disable some parts in sequencer loading settings
  23:20 Test ramp two pilots - ok
Presently OK, but still some features to be sorted out

## Slide 4: Plan Produce lumi, except:
Today
  Access for UPS...recover, physics
Friday
  06:00 dump physics fill
  90 m optics until Saturday morning 07:30
Saturday
  Am: VIP visit – machine access
  Close and search before noon
Next week (besides physics)
  Abort gap cleaning at 3.5 TeV
  25 ns MD