## Sheet1
V9, JU, 24/03/09 |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  | Sept |  |  |  | Oct
| wk4 | wk5 | wk6 | wk7 | wk8 | wk9 | wk10 | wk11 | wk12 | wk13 | wk14 | wk15 | wk16 | wk17 | wk18 | wk19 | wk20 | wk21 | wk22 | wk23 | wk24 | wk25 | wk26 | wk27 | wk28 | wk29 | wk30 | wk31 | wk32 | wk33 | wk34 | wk35 | wk36 | wk37 | wk38 | wk39 | wk40 | wk41 | wk42
Cooldown point 6 | bar: Apr wk18 to Sept wk38; Oct wk40 to Oct wk42
Injection Systems:
MKI LSS8 interlock testing etc | bar: Feb wk9 to Mar wk10
MKI LSS8 Automatic Cond | bar: Mar wk11
MKI LSS8 Soft Start tests | bar: Mar wk12 to Mar wk13
MKI LSS8: pre-pulse, timing, etc. | bar: Mar wk14
Remote operation from CCC | bar: Apr wk15 to Sept wk38; Oct wk40 to Oct wk42
Replacement MKI LSS2 installed | bar: wk4
MKI LSS2 interlock testing etc | bar: Mar wk13 to Mar wk14; Oct wk42
MKI LSS2 Automatic Cond | bar: Apr wk15 to Apr wk17; Oct wk42
MKI LSS2 Soft Start tests | bar: Apr wk18; Oct wk42
MKI LSS2 & LSS8: pre-pulse, timing, etc. | bar: May wk19; Oct wk42
Remote operation from CCC | bar: May wk20 to Oct wk42
TL commissioning (MSI, collimators, BPMs) | bar: Mar wk14 to Apr wk16
TT40 beam tests (// MD) | bar: May wk21
TT60 beam tests (// MD) | bar: May wk21
TT40/TT60 interleaved (// MD) | bar: June wk23 to June wk24
TT40/TT60 High Intensity & seq. (dedicated MD) | bar: June wk25
TI8 beam tests, downstream TED | bar: June wk23
TI2 beam tests, downstream TED | bar: June wk26
TI2/TI8 spare data - ions | bar: August wk33
Beam 1 injection tests | bar: Sept wk38
Beam 2 injection tests | bar: Sept wk36
LHC startup with beam | bar: Sept wk39
HV available, pulsing locally | bar: Mar wk10 to Apr wk18
HV available, pulsing remote | bar: May wk19 to Sept wk38; Oct wk40 to Oct wk42
MKQA-AC dipole commissioning | bar: Apr wk18 to May wk19
Beam dumping systems:
Installation cooling UA63 | bar: Apr wk15 to Apr wk16
Installation cooling UA67 | bar: Mar wk13 to Mar wk14
Re-testing of generators UA63 | bar: May wk21 to June wk23
Re-testing of generators UA67 | bar: Apr wk17 to May wk19
Commissioning cooling system UA63 | bar: June wk24 to June wk26
Commissioning cooling system UA67 | bar: May wk21 to May wk22
Commissioning at full voltage UA63 | bar: June wk27 to July wk28
Commissioning at full voltage UA67 | bar: June wk23 to June wk24
Test of mains stability | bar: August wk33
Re-commissioning of BETS/IPOC.. UA63 | bar: July wk29
Re-commissioning of BETS/IPOC.. UA67 | bar: June wk25
Re-calibration -synchro & settings UA63 | bar: July wk30
Re-calibration -synchro & settings UA67 | bar: June wk26
MKB63 new tanks installed | bar: wk4 to Feb wk9
MKB63 vacuum installation & pumping | bar: Mar wk13 to Apr wk15
MKBH67 installed and replaced (spare) | bar: Mar wk11
MKBV67 replaced | bar: Mar wk12
New MKBV67 clean room | bar: Mar wk11
New MKBV67 test air + vacuum | bar: Mar wk12 to Mar wk14
New MKBV67 installed and aligned | bar: Apr wk15
MKB67 vacuum installation & pumping | bar: Apr wk16 to Apr wk18
Re-testing of systems UA67 | bar: May wk21 to June wk23
Re-testing of systems UA63 | bar: Apr wk17 to May wk19
Commissioning at full voltage UA67 | bar: June wk27 to July wk28
Commissioning at full voltage UA63 | bar: June wk23 to June wk24
Test of mains stability | bar: August wk33
Re-commissioning of BETS/IPOC.. UA67 | bar: July wk29
Re-commissioning of BETS/IPOC.. UA63 | bar: June wk25
Re-calibration -synchro & settings UA67 | bar: July wk30
Re-calibration -synchro & settings UA63 | bar: June wk26
LBDS 2: timing, synchronisation & op. CCC | bar: July wk28 to Oct wk41
LBDS 1: timing, synchronisation & op. CCC | bar: August wk32 to Oct wk41
HV available; running in local or BETSsim | bar: Apr wk17 to May wk19; May wk21 to July wk31
HV available, pulsing remote BETSsim | bar: July wk28 to Sept wk38
HV available, pulsing remote BETS | bar: August wk34 to Sept wk38; Oct wk40
Timing system needed | bar: Mar wk14 to Sept wk38; Oct wk40 to Oct wk41
RF F_rev needed | bar: June wk23 to Sept wk38; Oct wk40 to Oct wk41
BIS loop closed needed | bar: June wk23 to June wk24; June wk27 to July wk28; July wk31 to August wk33; August wk35 to Sept wk36; Oct wk40 to Oct wk41
BETSsim needed | bar: June wk23 to Sept wk38; Oct wk40 to Oct wk41
Access strap needed | bar: June wk23 to Sept wk38; Oct wk40 to Oct wk41
Magnet powering and DCCTs needed | bar: August wk33 to Sept wk38; Oct wk40 to Oct wk41
TCDQ/TCSG control SW needed | bar: June wk24 to Sept wk38; Oct wk40 to Oct wk41
Injection Logging needed | bar: Mar wk14 to Sept wk38; Oct wk40 to Oct wk41
Dump logging needed | bar: May wk19 to Sept wk38; Oct wk40 to Oct wk41
XPOC needed | bar: May wk19 to Sept wk38; Oct wk40 to Oct wk41
BI systems needed | bar: June wk24 to Sept wk38; Oct wk40 to Oct wk41
SLP needed | bar: Mar wk14 to Sept wk38; Oct wk40 to Oct wk41
Injection sequences needed | bar: Mar wk14 to Sept wk38; Oct wk40 to Oct wk41
Dump sequences needed | bar: June wk24 to Sept wk38; Oct wk40 to Oct wk41
Always run MKD/MKB per beam.
HV is needed from first test onwards
50 % effecitive,
BIC availability
cabling
Cabling
Cabling