## MD5075ns
|  |  |  | Who | Beam | Comments
Wed | 6:00 | 2 | Beam dump and pre-cycle
|  |  | Switch LHC hypercycle and sequence (back to nominal protons) | OP | No
|  |  | SPS interlocks | OP/MPP | Yes/No | Check extraction BPM interlocks (may require calibration of MOPOS). Update the PC interlock (FEI) settings for TI2/TI8. Check and steer TL
Wed | 8:00 | 4 | Machine interlock checks | MPP (Joerg's alter ego) | Pilot/single nominal bunch | Check MKI delays - BLM thresholds for the triplets (monitor factors to be changed). Scrape down probe to check BPF limit (1-2E9). Check RF frequency interlock limits (approx +- 100 Hz), does not require beam. Check XPOC is behaving correctly. It may be necessary to update BPM and COD interlock settings due to the tight tolerances. Loss maps for collimators to ensure hiarchy is correct. | Check of BPM capture phase-in
Wed | 12:00 | 7 | Injection and damper checks (RF checks) for 75 ns beam up to 2 trains of 24 bunches spaced by 225 ns | OP, ABP, Brennan et al.., Wolfgang, Philippe, Vacuum, Cryo, BI (Federico, Ralph, Rhodri) | 75 ns (8, 24, 2x24 bunches) | BI checks in parallel | Glitch check
Wed | 19:00 | 22 | Injection of trains of 24 or 48 bunches (1.85 microsec separation). This must be done in steps with OK from Cryo and Vacuum | OP, ABP, Vacuum, Cryo, BI (Federico, Ralph, Rhodri), Elena S., Philippe for energy loss measurement | 75 ns (8, 24, 2x24 bunches) with 1.1/1.3/0.9x10^11 p/bunch | BI checks at the beginning
Thu | 17:00 | 4 | Switch to 50 ns - Injection and Damper checks | OP, ABP, Brennan et al.., Wolfgang, Philippe, Vacuum, Cryo, BI (Federico, Ralph, Rhodri) | 50 ns (12, 36 bunches). | BI checks in parallel
Fri | 21:00 | 6 | Test ramp (no squeeze). Chromaticity measurement. In the mean time check of the 50 ns beam in the injectors. Trim chromaticity (at flat-top) according to measurements during the previous ramp. | OP | pilots | Betatron loss maps for collimators. Check RF frequency interlock (+- 100 Hz) - can be done without beam after loss maps.
Fri | 3:00 | 10 | Ramp with 108 bunches (no squeeze) - 9x12 bunches - 50 ns beam. DO NOT SWITCH OFF damper at flat-top. | OP, ABP, Vacuum, Cryo, BI (Federico) |  | Recording of beam profile with BSRT
Thu | 13:00 | 5 | Stability measurements with 50 and 75 ns beams | OP, ABP, Vacuum Cryo, BI (Federico, Ralph, Rhodri), Wolfgang | 50 (12,36 bunches)/75 ns beams (8, 24 bunches, 2x24 bunches) | BI checks at the beginning | Possibility to switch OFF timings for B1/B2 and H and V independently
Fri | 18:00 | 4 | Interlock checks | MPP / JW | single ion bunch | Check MKI delays - BLM thresholds for the triplets (monitor factors to be changed). RF frequency interlock. TI2/8 PC interlocks. Orbit and COD interlocks for LHC.
Fri | 22:00 |  | Ramp for ion physics (121 on 121)
64