## schedule
| Day | Shift | Time (h) | Activity | Key aims
7 | MO | M | 8 | Injection and dump protection at 450 GeV | indiv
7 | MO | A | 8 | Collimator set-up at flat-top (16:00 - 24:00)
7 | MO | N | 8 | Pilot ramp & squeeze & collide & scan
8 | TUE | M | 2 | BLM system updates (8:00)
8 | TUE | M | 6 | Injection and dump protection at 450 GeV continued | 75 ns
8 | TUE | A | 8 | Collimator set-up at flat-top continued & finish. Ramp settings.
8 | TUE | N | 8 | Beta* measurement and correction at 1.5 m
9 | WED | M | 8 | Access for LBDS/TSU followed by tests (pulsing in local/energy scan) [9:00]
9 | WED | A | 8 | Loss maps at flat-top
9 | WED | N | 8 | Aperture in DS/Triplets (Stefano on shift)
10 | THU | M | 8 | Multi-bunch injection, dump protection setup
10 | THU | A | 8 | Nomial through squeeze, collimation set-up end of squeeze, loss map
10 | THU | N | 8 | Aperture in DS/Triplets (Stefano on shift)
11 | FRI | M | 8 | Machine protection continued with beam (Jan)
11 | FRI | A | 8 | Collimation set-up with collisions
11 | FRI | N | 8 | Loss maps at 3.5 TeV
12 | SA | M | 8 | Loss maps at 3.5 TeV
12 | SA | A | 8
12 | SA | N | 8
13 | SU | M | 8
13 | SU | A | 8
13 | SU | N | 8
14 | MO | M | 8

## To be scheduled
RF | To adjust front-end for higher bunch intensity (estimated 1 hour with beam) and get collision point fine-adjusted for the experiments (estimated 1 hour inject&dump or circulate&dump). | 2 hours | Philippe
RF | following the cavity phasing, we should (ideally) fine-adjust phase shifters in the cavity sum located in UX45. This requires an access to UX45 with RF ON. I heard that there will be a stop next Monday-Tuesday. Can we get ~ 1 hour with RF ON (nobody in IP4) with access to UX45? | 4h | Philippe Let Andy know or reply or call me at 75581