## Updated
Date | Day | Shift | Column10 | Column9 | Time (h) | Activity | Breakpoint | System/topic | Beam | Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8
11 | SAT | A | 17:00 | 20:00 | 3 | Loss maps 450 GeV and async. dump test |  |  | Nominal
11 | SAT | A | 20:00 | 24:00 | 3 | First ramp-up with one nominal bunch / beam and tight collimator setting; collimator set-up at flat top |  | Collimation | Nominal
11 | SAT | N | 24:00 | 6:00 | 6 | Pre-cycle or ramp (no beam) - decay measurement at 450 GeV |  | Magnets | Probe
12 | SUN | M | 6:00 | 9:00 | 3 | longitudinal loss maps 450 GeV |  | Collimation | Nominal
12 | SUN | M | 9:00 | 15:00 | 6 | Sort out orbit (feedback) on the ramp. |  |  | Probe
12 | SUN | A | 15:00 | 23:59 | 9 | Injection protection set-up
12 | SUN | N

## Schedule
Date | Day | Shift | start | end | Time (h) | Activity | Breakpoint | System/topic | Beam | Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8
1 | WED | M |  |  | 8 | Injection, first turn B1&B2 | First injections | OP | Probe
1 | WED | A |  |  | 8 | Closed orbit and RF capture B1&B2 |  | OP | Probe
1 | WED | A |  |  |  | Instrumentation - orbit, Q, Q', wire scanner |  | BI | Probe
1 | WED | A |  |  |  | Dispersion, CO, Q, Q',C- measure and correct |  | OP | Probe
1 | WED | N |  |  | 8 | Beta beating measurements and correction @ 450 GeV |  | Optics | Probe
2 | THU | M |  |  | 2 | Reference orbit with probe + OFC set-up |  | OP | Probe
2 | THU | M |  |  | 6 | Injection correction and TI2/8 reference trajectories |  | Injection | Probe
2 | THU | A |  |  | 4 | Injection of nominal bunch |  | Injection | Nominal
2 | THU | A |  |  | 4 | Flat reference orbit at injection with nominal bunch | Nominal bunch | OP | Nominal
2 | THU | N |  |  | 8 | BI shift |  | BI | Probe
3 | FRI | M |  |  | 8 | Damper setup for nominal bunch |  | RF | Nominal
3 | FRI | A |  |  | 4 | Feedbacks - recommissioning at injection (Q, orbit, radial) |  | Feedback | Probe
3 | FRI | A |  |  | 4 | Ramp to 4 TeV - test QFB & OFB | First ramp | Ramp | Probe
3 | FRI | N |  |  | 4 | Setting up of controlled transverse blow-up with TFB |  | RF | Probe
3 | FRI | N |  |  | 4 | Aperture measurements at injection (critical points: TDI2/8 - VVGSH.78.6L7.B - BTVs) |  | Optics | Probe
4 | SAT | M |  |  | 8 | Squeeze to 0.6 m - only one beam | First squeeze | Squeeze | Probe | Column1: No Beam 2 from SPS
4 | SAT | A |  |  | 6 | Optics measurements at 60 cm - only beam 1 |  | Optics | Probe | Column1: No Beam 2 from SPS
4 | SAT | A/N |  |  | 5 | Damper setup for nominal bunch + transverse blow-up |  | RF | Nominal
4 | SAT | N/M |  |  | 13 | Optics measurements |  | Optics | Probe
5 | SUN | A |  |  | 4 | Orbit at injection with nominal bunch and bumps |  | OP | Nominal
5 | SUN | A |  |  | 4 | Experimental magnets ON |  | OP | Nominal
6 | SUN | N |  |  | 4 | Orbit feedback with dynamic reference in the ramp |  | Feedback | Nominal
6 | SUN | N |  |  | 4 | Pre-cycle or ramp (no beam) - decay measurement at 450 GeV |  | Magnets | Probe
6 | MON | M | 2:00 | 14:30 | 10.5 | Ramp and squeeze test - injector stop (9 to 11) |  | OP | Probe
6 | MON | A | 14:30 | 16:00 |  | EDF intervention
6 | MON | A | 16:00 | 23:30 | 7.5 | Aperture measurements at injection (global) (TDI2/8 - VVGSH.78.6L7.B - BTVs, IP6 orbit bump?) |  | Optics | Probe
6 | MON | N | 23:30 | 2:00 | 2.5 | BGI B1 |  | BI | Nominal
6 | MON | N | 2:00 | 6:30 | 4.5 | BLM MPS tests |  | BI | Nominal
| TUE | M | 7:30 | 9:00 | 1.5 | K-modulation test |  | Optics
7 | TUE | M | 9:00 | 14:30 | 5.5 | RF setting-up (long. Blow-up in the ramp), 1 bunch 8E10 p |  | RF | Nominal
| TUE | M | 14:30 | 15:30 | 1 | ramp and squeeze |  |  | Probe
| TUE | A | 15:30 | 16:00 | 0.5 | test streched squeeze function |  | Squeeze | no
7 | TUE | A | 16:00 | 23:00 | 7 | Injection studies |  | INjection
7 | TUE | N | 23:00 | 9:00 | 10 | Squeeze to 0.6 m revisited - optics (beta beat corrections) |  | Squeeze | Probe
8 | WED | M/A | 9:00 | 0:30 | 15.5 | Collimation setting-up 450 GeV | Collimation | Collimation | Nominal
8 | WED | N | 0:30 | 5:30 | 5 | Squeeze to 0.6 m corrected (lengthen squeeze function and correct orbit) |  | Squeeze | Probe
9 | THU | M | 5:30 | 7:00 | 1.5 | TI8 stability check |  | Injection
9 | THU | M | 8:00 | 15:00 | 7 | b* at 0.7 m and 0.6 m |  | Optics | Probe
9 | THU | A | 15:00 | 16:00 |  | Splashes to ATLS
9 | THU | A | 16:00 | 17:00 | 1 | Commission energy feedback |  | BI
9 | THU | A | 17:00 | 21:00 | 4 | Ramp, squeeze with crossing angles and beam separation, collision beam process with LHCb crossing angle tilt |  |  | Probe
9 | THU | N | 21:00 | 7:00 | 10 | TCDQ set-up at 450 GeV (1:30 h no beam from injectors)
10 | FRI | M | 7:00 | 13:00 |  | Access and precycle
10 | FRI | M | 13:00 | 14:00 |  | MPS Verification tests (access and system changes) |  | MPS | Nominal + Probe
10 | FRI | A | 14:00 | 23:30 | 9.5 | Aperture at 4 TeV, 0.6m (ADT) | Aperture 4 TeV |  | Probe
10 | FRI | N | 23:30 | 2:00 | 2.5 | Ramp with flattened functions for Q and Q’ corrections |  |  | Probe
10 | FRI | N | 2:00 | 4:30 | 2.5 | MPS Verification tests (access and system changes) |  | MPS | Nominal + Probe
10 | FRI | N | 4:30 | 6:30 | 2 | Ramp and squeeze with collimator ramp functions |  |  | Probe
11 | SAT | M | 6:30 | 17:00 |  | Access system problem and precycle
11 | SAT | A | 17:00 | 20:00 | 3 | Loss maps 450 GeV and async. dump test |  |  | Nominal
11 | SAT | A | 20:00 | 24:00 | 3 | First ramp-up with one nominal bunch / beam and tight collimator setting; collimator set-up at flat top |  | Collimation | Nominal
11 | SAT | N | 24:00 | 6:00 | 6 | Pre-cycle or ramp (no beam) - decay measurement at 450 GeV |  | Magnets | Probe
12 | SUN | M | 6:00 | 9:00 | 3 | longitudinal loss maps 450 GeV |  | Collimation | Nominal
12 | SUN | M | 9:00 | 15:00 | 6 | Sort out orbit (feedback) on the ramp. |  |  | Probe
12 | SUN | A | 15:00 | 23:59 | 9 | Injection protection set-up
12 | SUN | N | 0:00 | 2:00 | 2 | Damper tests for quench test
12 | SUN | N | 3:00 | 7:00 | 4 | Probe to end of squeeze, k-modulation
13 | MON | M | 7:00 | 12:00 |  | Lost cryo Pt2, Access, precycle
13 | MON | A | 14:00 | 19:00 | 5 | Communication issues with PC, Orbit FB checks - '0' to RT input |  |  | Probe
13 | MON | A | 19:00 | 5:00 | 9 | Injection protection TI8, TDI, TCLIs |  | Injection
14 | TUE | M | 7:00 | 9:00 | 2 | Probe through ramp and squeeze
14 | TUE | M | 9:00 | 16:00 |  | Access problem Pt8, access, precycle
14 | TUE | A | 18:00 | 23:00 | 5 | TCDQ setup, TCDI validation preparation |  | Injection | Nominal
14 | TUE | N | 23:00 | 3:00 |  | 400V problem UA63/67
14 | TUE | N | 3:00 | 6:00 | 3 | Probe through ramp and squeeze, lost on collimators |  |  | Probe
15 | WED | M | 6:00 | 11:00 |  | QPS issues, prcycle
15 | WED | M | 11:00 | 14:00 |  | Controls issues, OFSU
15 | WED | M | 14:00 | 16:00 | 1 | Collimator alignement at 4 TeV - aborted |  | Collimation | Nominal
15 | WED | A | 17:00 | 20:00 | 2 | Ramp with nominal bunches for flow-up check
15 | WED | A | 21:00 | 5:00 | 8 | Injection protection validation |  | Injection
16 | THU | M | 6:00 | 15:00 | 9 | Collimation alignment at 4 TeV, loss maps |  | Collimation | Nominal
16 | THU | A | 19:00 | 2:00 | 7 | Injection protection |  | Injection
16 | THU | N | 4:00 | 10:30 | 6.5 | Optics correction revisited at 0.6 m |  |  | Probe
17 | FRI | M | 13:00 | 14:00 | 1 | Test ramp for RF blowup
17 | FRI | A | 15:00 | 20:00 | 5 | Ramp, squeeze , collide with 2 nominal bunches |  | Collisions | Nominal
17 | FRI | A | 20:00 | 1:00 | 5 | TCT alignment in collision, loss map |  | Collimation | Nominal
17 | FRI | N | 3:00 | 7:00 | 4 | Loss maps and synch dump at 4 TeV |  |  | Nominal
18 | SAT | M | 7:00 | 11:00 | 6 | Loss maps at injection with injection protection |  |  | Nominal
18 | SAT | M | 11:00 | 14:00 | 4 | TCSG6 investigations |  | Collimation | Nominal
18 | SAT | A | 14:00 | 17:00 | 3 | POPS, SPS kicker
18 | SAT | A | 17:00 | 23:00 | 6 | TCT alignment and of squeeze, RP alignment collisions |  | Collimation | Nominal
18 | SAT | N | 1:00 | 11:00 | 10 | RP alignment in collsions, problems with lumi scan |  |  | Nominal
19 | SUN | M | 0:00 |  |  | Injection and dump protection |  | Injection | Nominal
to be scheduled |  |  |  |  | 4 | Loss maps and asynch dump tests at 450 GeV with injection protection |  | Protection validation | Nominal
to be scheduled |  |  |  |  | 8 | Dump checkout (TSM MPS test) |  | dump | Probe/Nominal
to be scheduled |  |  |  |  | 8 | Dump checkout |  | Dump | Probe
To be scheduled |  |  |  |  | 8 | Sector 81 dipole - discharge at 500 - 750 and 1000 kA. |  | Circuits | No beam
7 | TUE | A |  |  | 8 | Dump checkout |  | Dump | Nominal
9 | SU | A |  |  | 8 | RF and damper |  | RF | Nominal
10 | MO | N |  |  | 8 | Pre-cycle or ramp (no beam) - decay measurement at 450 GeV |  | Magnets | Probe
11 | TUE | M |  |  | 8 | BI shift |  | BI | Nominal
12 | WED | N |  |  | 8 | Aperture at 4 TeV squeezed - IR1/5 | Aperture 4 TeV | Aperture | Probe
13 | THU | M |  |  | 8 | Ramp, RF nominal bunch and longitudinal blowup |  | RF | Nominal
14 | FRI | A |  |  | 8 | BI shift |  | BI | Nominal
15 | SAT | M |  |  | 8 | Multi-bunch injection 50 ns |  | Injection | 50 ns
15 | SAT | A |  |  | 8 | Transverse damper for multi-bunch 50 ns |  | ADT | 50 ns
15 | SAT | N |  |  | 8 | Aperture at 4 TeV squeezed - IR1/5 | Aperture 4 TeV | Aperture | Probe
16 | SUN | M |  |  | 8 | ADT : abort gap cleaning |  | ADT | Nominal
16 | SUN | N |  |  | 8 | Aperture at 4 TeV squeezed - IR2/8 |  | Aperture | Probe
17 | MO | A |  |  | 8 | Multi-bunch injection 50 ns |  | Injection | 50 ns
18 | TUE | M |  |  | 8 | ADT : injection and abort gap cleaning |  | ADT | 50 ns
18 | TUE | A |  |  | 8 | BI shift |  | BI | 50 ns
18 | TUE | N |  |  | 8 | Aperture 4 TeV spare |  | Aperture
19 | WED | M |  |  | 8 | Pilot ramp & squeeze & collide , Q/Q' |  | Collisions | Nominal
19 | WED | N |  |  | 8 | Spare
20 | THU | A |  |  | 8 | Collimation setup collisions |  | Collimation | Nominal
21 | FRI | M |  |  | 8 | Loss maps and asynch dump 4 TeV |  | Protection validation | Nominal
22 | SAT | M |  |  | 8 | First stable beams, 3x3 | Stable Beams 3b | Collisions | Nominal
22 | SAT | A |  |  | 8 | Ramp squeeze collide 50 ns | Stable Beams 48b | Collisions | 50 ns

## Master
Date | Day | Shift | Time (h) | Activity | Breakpoint | System/topic | Beam
0 |  |  | 8 | Ramp and squeeze checkout |  | Magnets | No beam
0 |  |  | 16 | TI2 and TI8 tests |  | Injection | Beam to TED
0 |  |  | 8 | BIS loop armed |  | BIS | No beam
0 |  |  | 8 | MKI/injection check |  | Injection | No beam
0 |  |  | 8 | Dump dry run |  | Dump | No beam
0 |  |  | 16 | RP interlock test (also modes) |  | MPS | No beam
1 | SA | M | 8 | Injection, first turn B1&B2 | First injections | OP | Probe
1 | SA | A | 8 | Closed orbit and capture B1&B2 |  | OP | Probe
1 | SA | N | 4 | Instrumentation - orbit, Q, Q', wire scanner |  | BI | Probe
1 | SA | N | 4 | Dispersion, CO, Q, Q',C- measure and correct |  | OP | Probe
2 | SU | M | 8 | RF capture and ADT first setup with probe |  | RF | Probe
2 | SU | A | 4 | Feedbacks - recommissioning at injection (Q, orbit, radial) |  | Feedback | Probe
2 | SU | A | 4 | Beta beating measurements and correction @ 450 GeV |  | Optics | Probe
2 | SU | N | 8 | Pre-cycle or ramp (no beam) - decay measurement at 450 GeV |  | Magnets | Probe
3 | MO | M | 8 | Ramp to 4 TeV - test QFB & OFB - test dump at 4 TeV | First ramp | Ramp | Probe
3 | MO | A | 8 | Squeeze to 0.6 m | First squeeze | Squeeze | Probe
3 | MO | N | 8 | Optics measurements / corrections in squeeze |  | Optics | Probe
4 | TUE | M | 8 | Reference orbit with probe |  | OP | Probe
4 | TUE | A | 8 | Injection correction and TI2/8 reference trajectories |  | Injection | Probe
4 | TUE | N | 8 | Pre-cycle or ramp (no beam) - decay measurement at 450 GeV |  | Magnets | Probe
5 | WED | M | 8 | Dump checkout |  | Dump | Probe
5 | WED | A | 8 | Dump checkout |  | Dump | Probe
5 | WED | N | 8 | BI shift |  | BI | Probe
6 | THU | M | 8 | Injection of nominal bunch |  | Injection | Nominal
6 | THU | A | 4 | Flat reference orbit at injection with nominal bunch | Nominal bunch | OP | Nominal
6 | THU | A | 4 | Damper setup for nominal bunch |  | ADT | Nominal
6 | THU | N | 8 | Squeeze to 0.6 m revisited - OFB and optics |  | Squeeze | Probe
7 | FRI | M | 8 | Orbit at injection with nominal bunch and bumps |  | OP | Nominal
7 | FRI | A | 4 | Experimental magnets ON |  | OP | Nominal
7 | FRI | A | 4 | Orbit feedback with dynamic reference in the ramp |  | Feedback | Nominal
7 | FRI | N | 8 | Aperture at injection | Aperture injection | Aperture | Probe
8 | SA | M | 8 | Dump checkout |  | Dump | Nominal
8 | SA | A | 8 | Dump checkout |  | Dump | Nominal
8 | SA | N | 8 | Pre-cycle or ramp (no beam) - decay measurement at 450 GeV |  | Magnets | Probe
9 | SU | M | 8 | Collimation setting-up 450 GeV | Collimation | Collimation | Nominal
9 | SU | A | 8 | RF and damper |  | RF | Nominal
9 | SU | N | 8 | Aperture at injection |  | Aperture | Probe
10 | MO | M | 8 | Collimation setting-up 450 GeV |  | Collimation | Nominal
10 | MO | A | 8 | TCDI setup |  | Injection | Nominal
10 | MO | N | 8 | Pre-cycle or ramp (no beam) - decay measurement at 450 GeV |  | Magnets | Probe
11 | TUE | M | 8 | BI shift |  | BI | Nominal
11 | TUE | A | 8 | Injection & dump protection 450 GeV |  | Injection | Nominal
11 | TUE | N | 8 | Loss maps and asynch dump tests at 450 GeV |  | Protection validation | Nominal
12 | WED | M | 8 | Injection protection validation |  | Protection validation | Probe
12 | WED | A | 8 | Squeeze to 0.6 m corrected |  | Squeeze | Probe
12 | WED | N | 8 | Aperture at 4 TeV squeezed - IR1/5 | Aperture 4 TeV | Aperture | Probe
13 | THU | M | 8 | Ramp, RF nominal bunch and longitudinal blowup |  | RF | Nominal
13 | THU | A | 8 | Collimation setup on flat top 4 TeV |  | Collimation | Nominal
13 | THU | N | 8 | MPS tests FMCMs |  | MPS | Probe
14 | FRI | M | 8 | Collimation setup on flat top 4 TeV |  | Collimation | Nominal
14 | FRI | A | 8 | BI shift |  | BI | Nominal
14 | FRI | N | 8 | Pre-cycle or ramp (no beam) - decay measurement at 450 GeV |  | Magnets | Nominal
15 | SAT | M | 8 | Multi-bunch injection 50 ns |  | Injection | 50 ns
15 | SAT | A | 8 | Transverse damper for multi-bunch 50 ns |  | ADT | 50 ns
15 | SAT | N | 8 | Aperture at 4 TeV squeezed - IR1/5 | Aperture 4 TeV | Aperture | Probe
16 | SUN | M | 8 | ADT : abort gap cleaning |  | ADT | Nominal
16 | SUN | A | 8 | Collimation / TCT setup squeezed |  | Collimation | Nominal
16 | SUN | N | 8 | Aperture at 4 TeV squeezed - IR2/8 |  | Aperture | Probe
17 | MO | M | 8 | Collimation / TCT setup squeezed |  | Collimation | Nominal
17 | MO | A | 8 | Multi-bunch injection 50 ns |  | Injection | 50 ns
17 | MO | N | 8 | BLM system checks |  | MPS | Nominal
18 | TUE | M | 8 | ADT : injection and abort gap cleaning |  | ADT | 50 ns
18 | TUE | A | 8 | BI shift |  | BI | 50 ns
18 | TUE | N | 8 | Aperture 4 TeV spare |  | Aperture
19 | WED | M | 8 | Pilot ramp & squeeze & collide , Q/Q' |  | Collisions | Nominal
19 | WED | A | 8 | Nominal bunch collisions |  | Collisions | Nominal
19 | WED | N | 8 | Spare
20 | THU | M | 8 | Collimation setup collisions |  | Collimation | Nominal
20 | THU | A | 8 | Collimation setup collisions |  | Collimation | Nominal
20 | THU | N | 8 | Loss maps and asynch dump 4 TeV |  | Protection validation | Nominal
21 | FRI | M | 8 | Loss maps and asynch dump 4 TeV |  | Protection validation | Nominal
21 | FRU | A | 8 | Loss maps and asynch dump 4 TeV |  | Protection validation | Nominal
21 | FRI | N | 8 | Loss maps and asynch dump 4 TeV |  | Protection validation | Nominal
22 | SAT | M | 8 | First stable beams, 3x3 | Stable Beams 3b | Collisions | Nominal
22 | SAT | A | 8 | Ramp squeeze collide 50 ns | Stable Beams 48b | Collisions | 50 ns

## Items
System | Item | Comment
ADT | Adjustments | 50 ns & signle b
ADT | Abort gap cleaning | To be made operational
ADT | Injection cleaning | Re-commission
ADT | Witness bunches for Q/Q'
RF | Cature etc tuning
RF | New longitudinal blowup
RF | Batch bowup | preperation
BI | Emittance devices
BI | OFB references | New system
BI | OFB gain and stability
BI | OFB bad BPM filter
BI | QFB | Re-commission
YASP | BPM quality | Commission
LBDS | TSU firmware
LBDS | AGK delay | Adjust
LBDS | No-dump trigger procedure | Test
LBDS | Beta* limits | Commission
Injection | TCDI automatic setup | Commission
SIS | Orbit & COD reference | Check
SIS | LSS6 BPM | Check
MPS | BPF limit | Check
MPS | FMCM D1 @ 0.6 m | Check
MPS | TOTEM & ALFA interlocks
Injectors | 3+3 injections PSB-PS

## Circuits
Name | Issue
RCO.A12B2 | Leakage current