## Sheet1
V3, JU, 13/02/09 |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  | Sept
| wk4 | wk5 | wk6 | wk7 | wk8 | wk9 | wk10 | wk11 | wk12 | wk13 | wk14 | wk15 | wk16 | wk17 | wk18 | wk19 | wk20 | wk21 | wk22 | wk23 | wk24 | wk25 | wk26 | wk27 | wk28 | wk29 | wk30 | wk31 | wk32 | wk33 | wk34 | wk35 | wk36
Injection Systems:
MKI LSS8 interlock testing etc | bar: Feb wk8 to Feb wk9
MKI LSS8 Automatic Cond | bar: Mar wk10
MKI LSS8 Soft Start tests | bar: Mar wk11
MKI LSS8: pre-pulse, timing, etc. | bar: Mar wk12
Remote operation from CCC | bar: Mar wk13 to Sept wk36
Replacement MKI LSS2 installed | bar: wk4
MKI LSS2 interlock testing etc | bar: Mar wk10 to Mar wk11
MKI LSS2 Automatic Cond | bar: Mar wk12 to Mar wk14
MKI LSS2 Soft Start tests | bar: Apr wk15
MKI LSS2 & LSS8: pre-pulse, timing, etc. | bar: Apr wk16
Remote operation from CCC | bar: Apr wk17 to Sept wk36
TL commissioning (MSI, collimators, BPMs) | bar: Mar wk14 to Apr wk16
TT40 beam tests | bar: May wk20
TT60 beam tests | bar: May wk21
TI8 beam tests | bar: June wk23
TI2 beam tests | bar: June wk26
HV available, pulsing locally | bar: Mar wk10 to Apr wk18
HV available, pulsing remote | bar: May wk19 to June wk23; August wk32 to Sept wk36
Beam dumping systems:
MKD cooling generators installed | bar: wk4 to wk5
Re-testing of generators UA63 | bar: Mar wk14 to Apr wk16
Re-testing of generators UA67 | bar: Apr wk17 to May wk19
Commissioning cooling system UA63 | bar: Apr wk17 to Apr wk18
Commissioning cooling system UA67 | bar: May wk20 to May wk21
Commissioning at full voltage UA63 | bar: May wk19 to May wk20
Commissioning at full voltage UA67 | bar: May wk22
Test of mains stability | bar: June wk23
Re-commissioning of BETS/IPOC.. UA63 | bar: June wk24
Re-commissioning of BETS/IPOC.. UA67 | bar: June wk25
Re-calibration -synchro & settings UA63 | bar: June wk26
Re-calibration -synchro & settings UA67 | bar: June wk27
New MKB tanks installed | bar: wk4 to Feb wk9
Re-testing of systems UA67 | bar: Mar wk14 to Apr wk16
Re-testing of systems UA63 | bar: Apr wk17 to May wk19
Commissioning at full voltage UA67 | bar: May wk19 to May wk20
Commissioning at full voltage UA63 | bar: May wk22
Test of mains stability | bar: June wk23
Re-commissioning of BETS/IPOC.. UA67 | bar: June wk24
Re-commissioning of BETS/IPOC.. UA63 | bar: June wk25
Re-calibration -synchro & settings UA67 | bar: June wk26
Re-calibration -synchro & settings UA63 | bar: June wk27
LBDS 1 & 2: timing, synchronisation etc. | bar: July wk28
Remote operation from CCC | bar: July wk29 to Sept wk36
HV available; running in local or BETSsim | bar: Mar wk14 to June wk27
HV available, pulsing remote BETSsim | bar: June wk24 to August wk33
HV available, pulsing remote BETS | bar: July wk31 to Sept wk36
Always run MKD/MKB per beam.
HV is needed from first test onwards
50 % effecitive,
BIC availability