## Slide 1: LHC operation in week 39
Coordination: Mike Lamont, Jan Uythoven, Malika Meddahi
Thanks to OP crews, HW and SW teams + patient customers
Aims for the week
  Complete 104b operation
  Review MPP criteria to move to 152b operation
  152b operation
  Operation consolidation
Outline
  Where did a week of beam time go? Some stats…
  What was done in terms of operation consolidation?
  Beam commissioning effort
  Vacuum & background levels
  What’s on the list for this week?

## Slide 2: Week 39 in short
Monday 27th September |  | Day : Access and recovery Overnight: Physics fill #1375 – 104 b x 104 b
Tuesday 28th September |  | AM: Physics fill cont’d + Roman Pots in PM: Fixing HW problems + first injection tests of 152 b Physics attempt 1: Beam dump during squeeze - UFO Night : attempt 2: Beam dump during ramp – Undulator trip
Wednesday 29th Sept. |  | AM : Access + recovery PM: Injection optimisation and checks for 16b injection Night: Injection 152b for physics (16b inj) 02:25 – 05:29 : Stable beams #1381 beam dump – UFO
Thursday 30th Sept. |  | AM: Injection and de-bunching tests + AGC tests PM + night: Physics fill attempts (injection checks for increases vacuum pressures around ATLAS) Tests ramp for chromaticity measurements
Friday 1st October |  | Vdm scans – Fill dumped due to electrical perturbation Overnight: machine recovery and Physics fill preparation
Saturday 2nd October |  | Physics fill # 1387: ~2h10 – Dump due to UFO Physics fill # 1388: ~2h15 – Dump due QPS PM: Access for QPS Night: No beams from SPS : Mains PC problems
Sunday 3rd October |  | AM: Injecting 152b x 152b – Tune FBK problems PM: Stable beams # 1389 - Dump on BLM triplet R1 Night: Physics attempt –dump at ramp start on RCBH15L1

## Slide 3: Week 39 in short: not making it to Physics
Date | Fill # | Bunch # | Inj. | What happened?
28 /09 | 1377 1378 | 152 152 | 8b 8b | Dumped during squeeze – UFO#1 with 152 b on BLMQI.4L2B1 Undulator trip during ramp – U_res above threshold
30/09 |  | 152 | 8+8 | Long injection process (MBB TT60) + Q-FB not ON – Decided not to launch the ramp
4/10 | 1390 | 152 | 8+8 | Before ramp launch trip of RCBH15.L6B1

## Slide 4: Week 39 in short: made it to stable beams
Date | Fill # | b # | Inj. | Fill dur. | Peak L | Fill L nb-1 | Dump
27 Sep. | 1375 | 104 | 8b | 9h | 3.5e31 | ~950 | Programmed dump
29 Sep. | 1381 | 152 | 8+8 | 3h | 4.9e31 | ~508 | UFO#11 – UFO #2 with 152b on BLMQI.25R8.B1 ATLAS bckgd higher
1 Oct. | 1386 | 19 | 1 | 3h | 1.3e30 | ~10 | Dump by QPS For van der Meer scans
2 Oct. | 1387 1388 | 152 152 | 8+8 8+8 | 2h10 2h15 | 3.9e31 4.4e31 | ~275 ~360 | UFO#12 – UFO#3 with 152b on BLMQI.04R2.B2 Dump due QPS communication
3 Oct. | 1389 | 152 | 8+8 | 7h10 | 5.1e31 | ~1110 | Dump due to BLMQI.02R1.B1

## Slide 5: Week 39 in numbers
System faults : 25%
Stable beams : 16%
Setting-up without beam ~14%
Setting up with beams : 45%
Beam commissioning: 0.03%
Week 39 delivered luminosity: ~ 3.8 pb-1
LHC total integrated luminosity above 10 pb-1
Mirko Pojer

## Slide 6: Week 39 – Operation consolidation
Tune FB – R. Steinhagen: Tune tracking during ramp and squeeze. Much work done, further analysis required. Urgent to give them dedicated beam time for a robust system!
RF work – P. Baudrenghien – O. Brunner: noise – module trips
Beam preparation in the injectors – OP crews
Injection qualification for 16b – B. Goddard and team
16b injection fine = injecting above SBF limit
Beam 2 chromaticity measurements at flat bottom – M. Pojer

## Slide 7: Friday 1st October – Recovering
.
Mirko Pojer

## Slide 8: Week 39 – Beam commissioning effort cont’d
De-bunching test – Brennan Goddard + Philippe Baudrenghien
  Inject 2.6e10 B1 and B2 3e10
  RF off and leave the beam to de-bunch for an hour
  Preliminary conclusions:
  With present BLM thresholds, can tolerate maximum 1e11p+ un-captured beam, if equally spread around the ring.
  The local density should not exceed
  3e6 p+/m, which is about 2.4e7 p+/25ns,
  or 0.02% of injected intensity (!).
  At present, injecting 154 bunches,
  the un-captured beam level is maybe 0.3%

## Slide 9: Week 39 : Beam commissioning effort Abort gap cleaning tests
Wolfgang Hofle, Daniel Valuch, Andrea Boccardi, Federico Roncarolo, Adam Jeff, Brennan Goddard, Malika Meddahi, Jan Uythoven, Eliana Gianfelice, Elena Shaposhnikova
kick delay between abort gap cleaning pulse and bunch 1 adjusted for all dampers
Injected two nominal bunches in each beam bucket 1 and bucket 1201
Adjustment of the cleaning pulses parameters - saw detrimental effect on beam (emittance increase, lifetime drop at large amplitude excitation)
Reduced pulse length flat top and adjusted position to minimize effect on bunches - better preservation of emittance for hor. than for ver. Cleaning
Switched on cleaning program (20 steps, 0.001 in tune, horizontal beam 1 covering 0.27 to 0.29 in tune, reduced kick amplitude) . No more emittance increases than natural blow-up.
Created losses from bucket by reducing RF voltage in steps (with cleaning on or off). Nicely saw un-bunched beam passing abort gap and being cleaned
If emittance increases are confirmed to be acceptable, go with these settings for a test during a real fill.
Wolfgang Hofle

## Slide 10
Results
time in abort gap
cleaning on
cleaning off
unbunched beam created
by lowering RF voltage
time
Wolfgang Hofle
Andrea Boccardi

## Slide 11
FILL 1: Setup
FILL 2: AGAP cleaning
Federico Roncarolo

## Slide 12: Week 39: Van der Meer scans – Part 1
Long filling process for the 19 single bunches/beam, ~8e10p/bunch.
  TT60 MBB PC tripped due to over temperature.
  Communication between the database and the injection sequencer
3 hrs of stable beams.
  Completed ATLAS vdm scans
  Only ½ of the CMS scans.
  Not done: vdm scans in LHCb and ALICE, and also length scale calibrations, longitudinal scans, etc.
Note : Excellent coordination by Massi and great support and participation from BI and ABP
  online indications that beam current errors are small
More time needed – to be scheduled

## Slide 13: Week 39: vacuum observations – 104b
104 b operation, straight 8b injection: relatively low increase of vacuum pressure at point 1 during ramp – Nothing at injection – Gauges between DFBX & D1 @ ~59m from IP1

## Slide 14: Week 39 – Vacuum observation – 152b
Note spikes during injection tests when b1 AND B2 are injected
Beam 1 only
8+8
Beam 1+2
8+8

## Slide 15: And wider context still
104
104
104
152 attempt
#1381
Beam 1 +2
8b only
Beam 1 +2
8+8b only

## Slide 16: Week 39: vacuum observations – better
Alick Macpherson
G. Schneider

## Slide 17: ATLAS
Witold Kozanecki

## Slide 18: Week 39: vacuum observations – fill 1389
Verena Kain
Thanks to Alexis Vidal
ramping

## Slide 19: Week 39: vacuum observations – fill 1389
Alick Macpherson

## Slide 20: Week 40
Coordination: Roger Bailey, Joerg Wenninger, Jan Uythoven
Goal: 200b operation
Xmas Day
IONS
End ion run
200x200
152x152
248x248
296x296
344x344

## Slide 21: On the list
Checks for 200b operation (Interlocked BPM, 200b injection) – Brennan Goddard
OP consolidation (squeeze & coupling) – S. Redaelli
Q-Fdbck – R. Steinhagen + PLL : Marek Gasior
Intensity effects & vacuum - SVC
Quench test (Wedn. – TBC) – Coord.: Joerg Wenninger
Vdm scans – Coord.: Massi
Transverse damper – 2 h without beam – no access W. Hofle
MKQA & AC-dipole – will need another access – E. Carlier
Voltage rampdown@injection
Lift maintenance – this week.
Test of new beam presence flag system – M. Gasior
CO security intervention to be scheduled - A.Bland
BI – Coord. J. J. Gras

## Slide 22: BI MD - c/o JJG – One Shift
PLL studies
Measure the sensitivity of Marek’s new beam presence detection system
Check the linearity of the fast BCT’s in the new configuration for nominal bunches
Tune the High BW/Low Gain fast BCT calibration for the coming ion run
Measure the High BW/Low Gain fast BCT sensitivity limit and linearity for low intensity bunches (ion run)
Re-check BPM sensitivity limit
Calibrate the abort gap over the whole ramp
Check the abort gap acquisition gate timing resolution and stability
Commission BGI in preparation to ions
Check BSRT/BGI/BWS cross-calibration including corresponding emittance logging
Test and compare bunch/bunch profile measurement via BWS and/or BSRT
For all this, we would need the 2 rings for a few hours at 450 GeV then a ramp and again a few hours at 3.5 TeV.
This would be really difficult to fit in a 4 hour slot. 8 would be perfect but we could try with 6.

## Slide 24: ATLAS

## Slide 25: ALICE

## Slide 26: CMS

## Slide 27: LHCb