## schedule
| Day | Shift | Time (h) | Activity | Key aims
19 | SA | A | 8 | Injection and first turn b1 (All expts. magnets off except Atlas & CMS)
19 | SA | N | 4 | Injection and first turn b2
19 | SA | N | 4 | Dispersion, CO, Q, Q',C- measure and correct - beam2/beam 1
20 | SU | M | 8 | Circulating Pilot and RF capture b1 and b2
20 | SU | A | 2 | MPS checks: BLMs, BPF (scraping)
20 | SU | A | 4 | Feedbacks - recommissioning at injection (Q, orbit, radial)
20 | SU | A | 4 | Beta beating measurements and correction@450 GeV
20 | SU | N | 6 | Normal pre-cycle - decay measurement
21 | MO | M | 3 | Access + D1.R5 problem
21 | MO | A | 8 | Trial ramp to 3.5 TeV - test Q and orbit feedback - test dump
21 | MO | N | 8 | 100 A pre-cycle - decay measurement - collisions at 450 GeV
22 | TUE | M | 4 | Machine protection checks + Access/LBDS check (DSO)
22 | TUE | M | 4 | Reference orbit plus bumps. Injection setting-up | Separation & crossing angles on
22 | TUE | A | 8 | Trial ramp to 3.5 TeV - test Q and orbit feedback - squeeze | plus beating at 3.5 TeV
22 | TUE | N | 8 | Tests dumps on fly in ramp (at least two intermediate energies)
23 | WED | M | 8 | CRYO INTERVENTION POINT 2
23 | WED | A | 2 | Injection of nominal bunch
23 | WED | A | 8 | Switching ON crossing angle and switch on / compensate the experimental magnets
23 | WED | N | 4 | Damper setup for nominal bunch
24 | THU | M | 8 | BPM calibration. Bumps on & compensation. Expt. dipoles on.
24 | THU | M | 2 | Orbit feedback with variable separation and crossing angle through the ramp | pilot
24 | THU | A | 8 | Beta beating correction and measurement through the squeeze | pilot
24 | THU | N | 8 | Ramp and squeeze (pilot) | pilot
25 | FRI | M | 8 | SPS RF intervention in shadow (3 hours - no beam) | nominal bunch
25 | FRI | A | 8 | Collimation setting-up - 450 GeV | nominal bunch
25 | FRI | N | 8 | Aperture at injection | pilot
26 | SA | M | 4 | RF investigation
26 | SA | M | 4 | Ramp and squeeze (pilot) - if time - else SA night
26 | SA | A | 8 | Collimation continued | nominal bunch
26 | SA | N | 8 | Aperture studies | nominal bunch
27 | SU | M | 4 | Transfer line/LHC line matching
27 | SU | A | 8 | Collimation continued
27 | SU | A | 4 | Ramp & squeeze
27 | SU | N | 8 | Cryo maintain lost/bad injection b2, access
28 | MO | M | 8 | Inj. & dump protection - 450 GeV
28 | MO | A | 8 | RF nominal bunch and cavity tuning (plus ramp to check blow-up) | includes longitudinal blow-up (nominal bunch)
28 | MO | N | 8 | Beta beating correction and measurement through the squeeze
29 | TUE | M | 4 | Collimation continued
29 | TUE | M | 6 | Inj. & dump protection - 450 GeV
29 | TUE | A | 6
29 | TUE | N | 8 | Collimation validation at 450 GeV
30 | WED | M | 8 | Trial collimator ramp to 3.5 TeV with beam (nominal bunch)
30 | WED | A | 8

## To be scheduled
RF | To adjust front-end for higher bunch intensity (estimated 1 hour with beam) and get collision point fine-adjusted for the experiments (estimated 1 hour inject&dump or circulate&dump). | 2 hours | Philippe
RF | following the cavity phasing, we should (ideally) fine-adjust phase shifters in the cavity sum located in UX45. This requires an access to UX45 with RF ON. I heard that there will be a stop next Monday-Tuesday. Can we get ~ 1 hour with RF ON (nobody in IP4) with access to UX45? | 4h | Philippe Let Andy know or reply or call me at 75581