## Slide 1: Friday 2nd September & Night
End of Technical Stop #4
17:30 Machine Closed – DSO OK
Outstanding hardware commissioning tests, some 60 A power converter to be fixed, QPS tests and some debugging
19:30 BIS loop closed. Dry dump. XPOC OK.
Pre-cycle the machine, trying to inject
Operations Vistar not working - to be fixed
22:50 Both beams injected, probes (with SIS masked)
  Injection not clean
Several problems: chromaticity measurements, injection handshake (DIP)
02:45 Beam losses during the first ramp
  Orbit feedback not working properly, problems Tune feedback, beams lost in the squeeze....
06:45 No beam SPS due to problems with extraction kicker / vacuum, Expect beam back from SPS later this morning

## Slide 2: Block A : aperture check
Fill 1: 1 probe/beam, checkout cycle.
  b* 1 m and Xing angle 120 mrad.
  Standard collimator settings IR6+7.
  TCTs IR1/5 to be adapted to 120 mrad (setup on 100 mrad).
Fill 2: 2 nominals/beam, TCT alignment, orbit.
  TCTs IR1/5 alignment on 120 mrad, separated and in collision.
  Collision (re-)optimization with 120 mrad, reference orbit.
  End with loss map (H+V) and asynch dump. TCTs are 11.8s.
Fill 3: 1 probe/beam, aperture check @ 1 m.
  Repeat aperture measurement at 1 m.
  End with a loss map H, TCTs at 14s.
Fill 4: 1 probe/beam, aperture check with loss map.
  Loss map with TCTs at Xs, X = 13…14.
4h
6h
8h
5h
 OK
NEXT

## Slide 3: Block A: long range BB check
Fill 5: 84b with highly asymmetric BB filling pattern (also used for 1 m with 100 mrad).
  Bring the beam up to collisions.
  Verify stability and beam-beam effects.
6h

## Slide 4: Block B : ALICE polarity
Step 1: adjust injection, reference.
  ALICE on ‘old’ polarity.
  Injection steering with 12b, then copy to probe and check it.
Step 2: revert ALICE polarity.
  Check/correct orbit.
  Check/steer injection oscillations with probe, repeat with nominal.
Step 2’: re-steer TI2 if necessary.
  TDI coarse
  TL setup, TCDI alignment and verification.
Step 3: TDI/TCLI alignment.
  TDI/TCLI alignment with 1 nominal b.
  Check TDI,TCLI setup.
  Check injection 12b.
2h
4h
12h
8h
If required, ‘alternate’ with TCT alignment (steps 4-6)

## Slide 5: Block B : ALICE polarity continued
Step 4: TCTs IR2 at injection.
  Setup TCTs in IR2 at injection.
Step 5: Checkout cycle, 2 probes/beam.
  Check Xing angle IR2 along the cycle.
  Correct orbit if necessary.
  TCTs IR2 ‘open’.
Step 6: TCT IR2 alignment cycle, 2 nominal b/beam.
  TCT alignment on flat top and in collision.
  Collision orbit, reference.
  Loss map H+V and asynch. dump.
(Step 7: TCT IR2 functions, positions and interlocks )
2h
4h
6h

## Slide 6: Block C
Validations (loss maps, asynch dump checks) – to be confirmed with collimation team (Dp/p)
Condition | Betatron H | Betatron V | Dp/p + | Dp/p - | Dump
Injection | X | X | X | X | X
Flat top | X | X | X | X | X
Squeezed | X | X | X | X | X
Collisions | X | X | X | X | X

## Slide 7: Block D: Intensity ramp up
Proposed ramp up for stable beams:
  48b – short fill
  264 – short fill
  480 – short fill
  912 – long fill
  1380 – finally !!