## Slide 1: Saturday
10:00 Beam back after MKE4 reconditioning.
12:00 Ramp for TCT alignment @ 1m.
14:30 Alignment starting with separated beams.
  Lost time to solve a problem of loss spikes preventing the alignment. Solved when sending of RT packets was disabled for the feedback – seems this actually inducing current changes on some converters.
16:00 Colliding, re-optimizing ATLAS & CMS.
19:00 Alignment finished.
Loss maps, asynch. dump test.
  Unfortunately TCP in IR3 left at 8 sigma (instead 12 sigma).
  Else looking good.

## Slide 2: Example B2 H
No losses at BLMs behind TCTs

## Slide 3: Sunday
22:00 Re-injecting. Some time lost trying to tune the probe for aperture measurements in the SPS.
Functions updated for TCTs in IR1&5.
We accidentally went “too far” to collisions, while we wanted to measure aperture at end of squeeze.
Aperture in collision (with lumi knob) – Xing plane:
  IR1 (V) : 14.8-15.3 sigma
  IR5 (H) : 15.3-15.8 sigma
Loss maps with TCTs at 13.8 sigma – look OK.

## Slide 4: Sunday
04:00: Refill for second aperture check.
Aperture measured in separation plane (with separated beams) - more difficult to find.
  IR1 H: > 16 sigma.
  IR5 V : >16 sigma.
07:30: Loss maps with TCTs at collision setting + 2 sigma (11.8 + 2 sigma).
  Look good at first sight.
  Some losses at Q10 in IR1 to be checked.
Prel. conclusion:
  Aperture confirmed at 1 m – we have enough aperture for 1m & 120 urad Xing angles, with around 2 sigma add. margin,

## Slide 5: TS feed-downs
No HW problems so far – best recovery.
Lot’s of “small” controls issues with LSA (interference with INCA SW), FIDEL, sequencer, XPOC, DB publication (affects Handshakes), machine DIP-CMW servers etc.
  Made a few SW rollbacks.
  Some of the problems are not understood. To be looked at on Monday…

## Slide 6: Tentative plan
Day/afternoon:
  Start with ALICE reversal.
  Schedule such that we make a test ramp before the night – may shift the protection validation to Monday.
Night:
  Aperture with separated beams in Xing plane – systematic.
  Loss maps.

## Slide 7: Block A : aperture check
Fill 1: 1 probe/beam, checkout cycle.
  b* 1 m and Xing angle 120 mrad.
  Standard collimator settings IR6+7.
  TCTs IR1/5 to be adapted to 120 mrad (setup on 100 mrad).
Fill 2: 2 nominals/beam, TCT alignment, orbit.
  TCTs IR1/5 alignment on 120 mrad, separated and in collision.
  Collision (re-)optimization with 120 mrad, reference orbit.
  End with loss map (H+V) and asynch dump. TCTs at 11.8s.
Fill 3: 1 probe/beam, aperture check @ 1 m.
  Repeat aperture measurement at 1 m.
  End with a loss map H, TCTs at 14s.
Fill 4: 1 probe/beam, aperture check with loss map.
  Loss map with TCTs at Xs, X = 13…14.
4h
6h
8h
5h
DONE
~DONE
~DONE
(repeat parts)

## Slide 8: Block A: long range BB check
Fill 5: 84b with highly asymmetric BB filling pattern (also used for 1 m with 100 mrad).
  Bring the beam up to collisions.
  Verify stability and beam-beam effects.
6h

## Slide 9: Block B : ALICE polarity
Step 1: adjust injection, reference.
  ALICE on ‘old’ polarity.
  Injection steering with 12b, then copy to probe and check it.
Step 2: revert ALICE polarity.
  Check/correct orbit.
  Check/steer injection oscillations with probe, repeat with nominal.
Step 2’: re-steer TI2 if necessary.
  TDI coarse
  TL setup, TCDI alignment and verification.
Step 3: TDI/TCLI alignment.
  TDI/TCLI alignment with 1 nominal b.
  Check TDI,TCLI setup.
  Check injection 12b.
2h
4h
12h
8h
If required, ‘alternate’ with TCT alignment (steps 4-6)

## Slide 10: Block B : ALICE polarity continued
Step 4: TCTs IR2 at injection.
  Setup TCTs in IR2 at injection.
Step 5: Checkout cycle, 2 probes/beam.
  Check Xing angle IR2 along the cycle.
  Correct orbit if necessary.
  TCTs IR2 ‘open’.
Step 6: TCT IR2 alignment cycle, 2 nominal b/beam.
  TCT alignment on flat top and in collision.
  Collision orbit, reference.
  Loss map H+V and asynch. dump.
(Step 7: TCT IR2 functions, positions and interlocks )
2h
4h
6h

## Slide 11: Block C
Validations (loss maps, asynch dump checks) – to be confirmed with collimation team (Dp/p)
Condition | Betatron H | Betatron V | Dp/p + | Dp/p - | Dump
Injection | X | X | X | X | X
Flat top | X | X | X | X | X
Squeezed | X | X | X | X | X
Collisions | X | X | X | X | X

## Slide 12: Block D: Intensity ramp up
Proposed ramp up for stable beams:
  48b – short fill
  264 – short fill
  480 – short fill
  912 – long fill
  1380 – finally !!