## Slide 1: Week 35 – Technical Stop and Restart
Monday morning @ 6:00: Begin of Technical Stop #4 after MD period
  Coordination Julie Coupard
Friday afternoon 17:30 Machine Closed – DSO OK
  Coordination Jorg Wenninger, Jan Uythoven
  Very smooth start-up without any significant hardware problems!
  Some controls problems remain to be sorted out – data publication/subscription
  Special at this start-up
    Preparation for * = 1 m at IP1/5
    Alice polarity reversal

## Slide 2: * = 1 m in IPs 1 and 5: The Context
During MD period optics with * = 1 m was tested using
  Tight collimator settings
  Reduced crossing angles from 120 rad to 100 rad
  Beam was unstable during squeeze
During same MD period the physical aperture around the triplets in the IPs was found to be larger than initially assumed
Decision in LMC last week
  Continue running with same collimator settings as before the TS
    TCTs IR1, 5 and 8 @ 11.8 
  Stay with the crossing angle of 120 rad
  Confirm the additional physical aperture
Start-up program after TS based on this

## Slide 3: Start-up: Friday 2nd September & Night
Friday 17:30 Machine Closed – DSO OK
Friday 19:30 BIS loop closed. Dry dump. XPOC OK.
Friday 22:50 Both beams injected, probes
  Injection not clean – later ok without touching the LHC
Friday 02:45 Beam losses during the first ramp after TS
  Orbit feedback not working properly, problems Tune feedback, beams lost in the squeeze....sorted out during the night
  Dump at 3.5 TeV: OK
Saturday 12:00 Ramp and squeeze for TCT alignment with * = 1 m
Sunday morning: Change of Alice Polarity reversal
Start of “Master Plan”

## Slide 4: Conclusions on Aperture so far
  Aperture confirmed at 1 m – there is enough aperture for *=1m & 120 µrad Xing angles, with around 2 sigma additional margin.
We can conclude that for the squeezed/separated case we found >16 sigmas in the separation plane. the crossing plane was only addressed in collision conditions.
IP1 (V): triplet at 14.8 -> 15.3 sigmas (collision and lumi scans IN) IP5 (H): triplet at 15.3 -> 15.8 sigmas (collision and lumi scans IN) IP1 (H): triplet at above 16.0 sigmas (squeezed, separated) IP5 (V): triplet at above 16.0 sigmas (squeezed, separated)
Betatron loss maps with TCTs at collision settings + 2sigma step out: Only small losses on the TCTs, and no losses on the triplets...
Loss maps show a peak in the Q10-R1. To be followed up.

## Slide 5: Probing TCT – Triplet aperture
At the step of TCT gap between 14.8 and 15.3 sigmas, the losses move from the TCT to the MQX (light-orange line).
Corrector = aperture bump
BLM TCT
BLM triplet
TCT position

## Slide 6: The commissioning blocks
Configuration:
  b* =1m, 120 mrad Xing angles.
  IR3+6+7 collimators at standard settings, TCTs 11.8s (IR1+5+8)
Block A: Aperture at 1m and 120 mrad
Block B: ALICE polarity reversal
Block C: Validation = loss maps
Block D: Intensity ramp up

## Slide 7: Block A : aperture check
Fill 1: 1 probe/beam, checkout cycle.
  b* 1 m and Xing angle 120 mrad.
  Standard collimator settings IR6+7.
  TCTs IR1/5 to be adapted to 120 mrad (setup on 100 mrad).
Fill 2: 2 nominals/beam, TCT alignment, orbit.
  TCTs IR1/5 alignment on 120 mrad, separated and in collision.
  Collision (re-)optimization with 120 mrad, reference orbit.
  End with loss map (H+V) and asynch dump. TCTs are 11.8s.
Fill 3: 1 probe/beam, aperture check @ 1 m.
  Repeat aperture measurement at 1 m.
  End with a loss map H, TCTs at 14s.
Fill 4: 1 probe/beam, aperture check with loss map.
  Loss map with TCTs at Xs, X = 13…14.
4h
6h
8h
5h
OK
OK, crossing plane separated beams missing* Q10-R1 ?
OK
* Tried missing aperture measurement during last night: fill was dumped by a trip of an RQTD circuit, most likely triggered by the QFB
NOW

## Slide 8: Block A: long range BB check
Fill 5: 84b with highly asymmetric BB filling pattern (also used for 1 m with 100 mrad).
  Bring the beam up to collisions.
  Verify stability and beam-beam effects.
6h
Foreseen for this afternoon

## Slide 9: Block B : ALICE polarity
Step 1: adjust injection, reference.
  ALICE on ‘old’ polarity.
  Injection steering with 12b, then copy to probe and check it.
Step 2: revert ALICE polarity.
  Check/correct orbit.
  Check/steer injection oscillations with probe, repeat with nominal.
Step 2’: re-steer TI2 if necessary.
  TDI coarse
  TL setup, TCDI alignment and verification.
Step 3: TDI/TCLI alignment.
  TDI/TCLI alignment with 1 nominal b.
  Check TDI,TCLI setup – check protection.
  Check injection 12b. Later
2h
4h
12h
8h
OK
OK
OK

## Slide 10: TDI alignment & angle set-up

## Slide 11: Block B : ALICE polarity continued
Step 4: TCTs IR2 at injection.
  Setup TCTs in IR2 at injection.
Step 5: Checkout cycle, 2 probes/beam.
  Check Xing angle IR2 along the cycle.
  Correct orbit if necessary.
  TCTs IR2 ‘open’.
Step 6: TCT IR2 alignment cycle, 2 nominal b/beam.
  TCT alignment on flat top and in collision.
  Collision orbit, reference.
  Loss map H+V and asynch. dump.
(Step 7: TCT IR2 functions, positions and interlocks )
2h
4h
6h
OK
OK
Setting functions for the whole operational cycle were generated.
OK
OK

## Slide 12: Block C
Validations (loss maps, asynch dump checks) – to be confirmed with collimation team (Dp/p)
Condition | Betatron H | Betatron V | Dp/p + | Dp/p - | Dump
Injection | X | X | X | X | X
Flat top | X | X | ? | ? | X
Squeezed | X | X | ? | ? | X
Collisions | OK | X | OK | X | X
betatron and off-momentum (+500Hz) loss maps were done in physics, at betastar=1m with relaxed collimator settings. Loss maps look good.

## Slide 13: Block D: Intensity ramp up
Proposed ramp up for stable beams:
  48b – short fill
  264 – short fill
  480 – short fill
  912 – long fill
  1380 – finally !!
Coordinators this week: Jorg Wenninger (again) & Bernhard Holzer