## Slide 1: Summary meeting 17/02/2011, 8:30
All dipole circuits have been commissioned with the snubbers without main issues
Two RB converters are presently working without active filter (in S34 it was disconnected yesterday following a second trip during the tests)
Heat run with sector 81 carried out during the night
Circuit | RB comm. with Snubbers | Commissioning | GPM activated
RB.A12 | Yes | Not completed (RQ9.L2) | Yes
RB.A23 | Up to 6 kA | Not completed (1 test missing on RB) | No
RB.A34 | Up to 6 kA | Completed | No
RB.A45 | Yes | Not completed (1 test missing on RQD/F) | Yes
RB.A56 | Yes | Completed | Yes
RB.A67 | Yes | Completed | Yes
RB.A78 | Yes | Completed | Yes
RB.A81 | Yes | Completed | Yes
Notes: 1

## Slide 2: Missing circuits/tests
RB.A23 needs the last commissioning step, with a cycle at 6 kA (2h)
RQ9.L2 and RQ9.R4: problem seems to be understood and identified in the compensation coefficients – access needed
During the night a QHPS discharged in sector 12 - access needed
If the machine will be closed in the late morning, we could imagine to complete the Powering Tests campaign by the beginning of the afternoon
PGC cycles are required and issues need to be addressed
  support by QPS, MP3 and EPC team still required, tbd