## Slide 1: Last night
Lhc closed 19:15
RB 78 tripped at 5800 Amps
Then ready again at 23:00
LBDS energy tracking tests
Heat run 56/67/78

## Slide 2: Lbds

## Slide 3: 78

## Slide 4: 67

## Slide 5: 56

## Slide 6: Progress of the day
BIC BLM
  Ready..
Timing
  Did real injection requests under LHC mastership with injection sequencer double threaded.
    BPMs triggered fine with pre-pulse - concentrators fine with it (picked up by IQC, YASP).
    BT pre-pulses arriving synchronously at MKIs (checked on OASIS).
    IQC reacting fine.
  Potential issues with the BCTs in IQC
    publishing values > 0 without beam extracted (need to check with BI). Will add some more consistency checks in the IQC.
  real dedicated filling tested ok
  Frev distributed
  Machine check out tests started

## Slide 7: Progress of the day
BT
  MKQ MKA AC-DIPOLE tested OK
  MKI pulsing
    Frev present
    Prepulse trigger observed on OASIS
    Impossible to close BIS loop
  LBDS energy tracking
    Q4L6 Q4R6 RMSD.LR6B1 RMSD.LR6B2
    S45,56, 67,78 ramped to 3.5 TeV
    Tested SMD table problem

## Slide 8: Progress of the day
Vacuum interlock test
  Ring and Exp’s ready
  Valves opening today
  Interlock tests Done 1 3 4 5 6 7
  The vacuum valve functionality and interlock logic into the BIS have been tested for Pts 2 and 8. All is OK except for the validation of the interlock logic in and around the MKIs
PC
  56 67 78 heat run
  MSI 2/8 heat run
  Tl’s interlocked element heat run done
  Warm Magnet ON
SMP
  Done ok.

## Slide 9: Open issues & Access
Handshake done
  Few issues found continue on Friday morning
BT
  LBDS MSD Bets table faulty
  Access needed point 6
PC’s
  After first real heat run
  Several pc’s tripped see sector status

## Slide 10: Open issues & Access
Vacuum
  Still an issue in LSS2/8
  To be completed tomorrow
  Validation of TOTEM and ALFA interlock logic need detailed tests and as they use the collimator control system, need to be coordinated with Stefano.
RF
  Prepulse tests Alice and LHCb
  To be tested during Beam test Ti2 Ti8
BIS
  BIC
  BTV-BSRT signal
    interlock fault UA47R4 B1 (mask)
    access

## Slide 11: Planning

## Slide 12: LSA
New LSA functionality
  Tested the incorporation process with the new parameters:
  START-OF_BEAMPROCESS
  END_OF_BEAMPROCESS
  PREVIOUS and NEXT optics for the incorporation rules. Works fine for matched optics and for intermediate stopping points.
  Greg has the green light to release the new functionality
  Laurette modified the sequencer tasks related to the SMP changes(FORCE/UNFORCE SFB and RELAXED THRESHOLD)