## Updated
Date | Day | Shift | Column10 | Column9 | Time (h) | Activity | Breakpoint | System/topic | Beam | Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8

## Schedule
Day | Shift | start | end | Time (h) | Activity | System/topic | Beam | Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7
FRI | M | 8:00 |  |  | Cryo conditions for RF. Start RF conditioning, priority to Sector 34 RF if possible and conditioning of Module1B1 | OP
FRI | M | 8:00 | 22:00 |  | RF conditioning (RF zone closed)+RF loop checks | RF
FRI | A | 18:00 |  |  | Machine Closed - Cryo OK in all sectors (last to come sector 45) | OP | bar: Column2
FRI | A | 18:00 | 20:00 |  | MSI (pt 2) tests | EPC
FRI | A | 18:00 | 20:00 |  | Beams to last TEDs in TI2/8 for trajectory checks after SPS dipole change and stability tests | OP | Probe/Indiv/12 bunches in TL
FRI | A | 18:00 | 22:00 |  | HWC checks of the circuits affected by interventions | OP
FRI | A | 22:00 | 23:00 |  | Injection and beam circulating at 450 GeV | OP | Probe
FRI | N | 23:00 | 0:00 |  | BLM interlock verification - pilot on TCP in point 7 | OP | Probe
FRI | N | 0:00 | 1:00 |  | Tune and orbit feedback checks at injection | BI | Probe
FRI | N | 1:00 | 7:00 |  | Full cycle with beam up to collisions - chromaticity/tune measurement and correction - new b3 correction at flat-top - New LHCb polarity (negative) | OP | Fat Probe
SAT | M | 7:00 | 14:00 |  | Injection setting-up with MSI pre-cycle - TDI checks (cold) - LSS6 BPM chcecks | OP/ABT | Probe/Indiv/50ns
SAT | M/A | 14:00 | 16:00 |  | Cavity phasing B1 | RF | A few indiv - Super Relaxed SBF at 450 GeV - need to mask total voltage control
SAT | A | 16:00 | 23:00 |  | Full cycle with beam up to collisions - TCT alignment checks at flat-top and in collision after getting head-on collisions at IPs and reseparated to nominal settings in IP8 - Loss maps in these conditions (betatron and negative off-momentum loss map) - New LHCb polarity (negative). Variable damper gain (reduced gain on one out of 3 bunches) | OP/ABP | Indiv
SAT | N | 23:00 | 3:00 |  | Full cycle with beam up to flat-top - Loss maps in these conditions (betatron) - New LHCb polarity (negative) | OP | Indiv
SAT | N | 3:00 | 4:00 |  | FMCM checks (RBXWTV.L2, RD34.LR3, RD34.LR7) - Switch OFF at injection with circulating beam | OP | Probe
SAT | N | 4:00 | 9:00 |  | Full cycle with beam - chromaticity/tune measurement after correction | OP | Fat Probe
SUN | M |  |  |  | Physics with 84 bunches - length scale calibration (~3 hours) | OP | 50 ns
SUN | A |  |  |  | Physics 480 bunches after LHCb polarity inversion - - different gains for the damper - low pile-up for CMS | OP/RF | 50 ns
SUN | N |  |  |  | Physics with 840 bunches | OP | 50 ns
MON | M |  |  |  | Re-check the phasing of the cavity sum B1 (maybe access to UX45) | RF
MON | M |  |  |  | Physics with 1380 bunches | OP | 50 ns

## Nottoforget
Change the strength of the landau damping octupoles due to the recovery of the ROF.A81.B2
Invert polarity in LHCb (negative)
Insert ROF.A81.B2 in the soc and RCBV17
Test RD34 in 3 and 7