## Slide 1: Mon 13/8
09:50 Beams dumped by an interlock on TCTs in point 1. Integrated lumi 152 pb-1 in ~10 h
Filling delayed by: BLM crate, QPS controller reset (main circuits in sector 45), RF cavity in the PS
14:30 Finally injected pilot and nominal bunch for orbit reference measurement
14:50 Ramp ALICE solenoid and dipole down for polarity switch
Problems to switch the polarity of ALICE solenoid  PO piquet intervention
18:00 ALICE solenoid and dipoles ramped at nominal current with NEGATIVE polarity
18:00-20:00 orbit measurement and correction

## Slide 2: Mon 13/8 – Tue 14/8
20:00 – 02:00 Collimator alignment:
  450 GeV: TCTV + TCTH
  Flat-top: TCTV + TCTH
  Squeezed, separated: TCTV + TCTH
  Colliding: TCTV + TCTH (to be done)
02:00 – 03:30 Find collision

## Slide 3: Tue 14/8
06:00 - ongoing Loss Maps:
  450 GeV: injection protection IN and OUT + off-mom (+/-)
  Flat-top: betatron (done but to be checked – in particular V-plane)
  Squeeze, separated: betatron (done but to be checked - in particular V)
  Colliding: betatron, off-momentum - / + and synch dump (with roman pots)

## Slide 4: Plan
08:30-17:00
  Injection and injection protection setting-up in point 2
  Verification of TDI alignment in point 8
  In the shadow CMS solenoid ramp-up (from 10 AM)
  Loss maps at injection (with injection protection in)
Evening – Night
  Alignment in collision
  Loss maps in collision with roman pots
Night
  Full cycle with low intensity (78/84 bunches) up to collision to verify quality of the orbit. Orbit in the squeeze might have to be optimized with additional test ramp
Tomorrow: intensity ramp-up and stable beams if everything OK (480 bunches/1374 bunches)

## Slide 5: Pending
Oscilloscope for diamond detector (during working hours, in UA87 for ~30 min). C. Zamantas
Moving of the spare MKD generator from gallery to the surface. N. Magnin