## Slide 1: Tue 23/10
09:44 MKBV-B2 ion pump tripped. Vacuum spike leading to beam dump system internal fault and beam dump. Happened already few times. Follow-up by ABT+VSC. End of physics #3210. 66 pb-1 in 3.1 h.
10:19 – 14:46 – Faulty sensor on a turbine of a warm compressor in point 8 tripping twice and leading to loss of cryo start/maintain of the matching section R8 (Sector 81). Sensor disabled (SW-wise and HW-wise). Had to pre-cycle twice.
15:00 – 16:30 Commissioning of batch by batch longitudinal blow-up

## Slide 2: Batch by batch longitudinal blow-up (Ph. Baudrenghien et al.)
We first optimized the strength of excitation: 0.07 rad rms , leading to a two minutes time constant (length blown to 1.4 ns). We then refilled for physics. No unusual losses on momentum collimator, good lifetime. Plans: We found an issue with the treatment of the gaps between PS batches. The software will be upgraded on Wednesday. Then we will install it for normal operation on Thursday.

## Slide 3: Tue 23/10
17:00 Fill for physics #3212
  Batch by batch longitudinal blow-up
  Gated tune measurement and feedback on B1
  High bandwidth damper during the squeeze up to collision than back to lower bandwidth
  Emittances at injection: B1H/V = 1.43/1.38, B2H/V=1.49/1.57

## Slide 4: Tue 23/10
Reasonable losses at the beginning of ramp
No chirp: lost QV-B1 signal on gated BBQ above 2 TeV in spite of the reduction of the gain of the feedback on first 6 bunches done yesterday  further reduction required

## Slide 5: Tue 23/10
Batch by batch blow-up
Initial luminosity ~7x1033 cm-2s-1
18:23 Stable beams #3212
19:19 Trip of power converter RQT12.R1B2. End of fill 3212. 22 pb-1 in ~1 h
Access required for power converter replacement.
Problem with PAD UJ16 (pending?). Intervention of access piquet
22:49 Intervention on RQT12.R1B2 and on PAD completed. Patrol.
23:29 Machine closed.

## Slide 6: Tue 23/10 – Wed 24/10
Ready for injection at 01:00
Steering TI8
01:35 Injection Fill #3214:
  Gated tune measurement and feedback on B1 (after further reduction of the gain on first 6 bunches by 6 dB)
  High bandwidth damper during the squeeze up to collision than back to lower bandwidth
Still problems for tune feedback to lock on B1 from ~2 TeV
03:40 Stable beams #3214. Initial luminosity 6.5x1033 cm-2s-1

## Slide 7: Plan
09:00 Beam dump
10:00 Beta*=1 km until tomorrow morning
  PS intervention required on kicker (4 hours – during beta*=1 km fill)
Tomorrow:
  LHCb polarity switch and low intensity ramp (2x6 bunches/beam)
  Physics fill (with controlled longitudinal blow-up at injection)
  During the day PS/SPS increasing satellite population for ALICE

## Slide 8: Pending
Pending Accesses:
  LVDT TDI Pt2. Tunnel, 2 hours
  LBDS MKD-F-B1: check PC and generator. UA63
  Radmon installation between Q5 and Q6 at IP1. 1 hour access, few hours pre-warning. Impact 21253 / D. Macina
  Gated BBQ installation for B2 (2 hours) in point 4