## Slide 1: Controls Planning
E. Hatziangeli – LHC Beam Commissioning meeting - 3rd March 2009

## Slide 2: FESA-CMW-RBAC
FESA
  Pro ver. 2.10 operational
CMW
  Two areas going on in parallel:
    Deployment of the new directory server DS
    Deployment of the new RBAC features
  New directory server DS
    pro ver. RDA is 2.7 (C++ &Java) rel. Dec 2008
      This version provides support for the new DS, with transparent failover to the old service (transition ver.)
      All users should have upgraded to this till end April
    Final pro RDA: 2.8 (C++ &Java) + RBAC 3.0 (C++) – Monday 16th Mar
    End Apr: Switch off old directory service
  Issues: Clients using older versions should update
  Need two ½ day slots in the CCC schedule to test [RDA 2.8 and RBAC 3.0]
    CO will organize the test with Eq. Groups (FESA) and OP (applications)
MCS Functional tests due to new RBAC ver=> wk 12
Notes: RBAC: new serialization, split of client & server parts, several bug fixes, etc.

## Slide 3: LHC Central Timing
Timing will be available for wk 14
CO dedicated testing for ½ day to
  Install and test the last modifications requested by OP (telegram layout)
  Make internal checks of the timing chain
  Verify the behavior of the central timing with the LHC timing application
Pending Issues
  Energy distribution works

## Slide 4: Logging system
Logging & SDDS
  FESA changes identified
    RF all low level parameters
    BT: MK direct + XPOC: complete refactoring of FE SW organization (Verena)
    MUGEF migration to FESA by S. Page
    BI tune + beam orbit
    Collimators
  SDDS space required 40GB/day => for 10m continuous operation with all data online => 12TB close to our SLC5/64bit CPUs limits
    Problematic similar to LHC experiments -> IT
Concentrators
  BLM concentrators
    New features requested by BI people + internal system ameliorations done – testing now and.
    Next: expand the set of running sums (now 8/12) and test the MDB throughput
    The system is working 24/7 as BI often perform test
  BPM concentrators
    No changes from 2008 version
    Need to test the whole chain (along with Verena's app) + verify how passing big chunks of data over in SDDS works in long period of time (Verena will trigger this)

## Slide 5: PM & XPOC
PM and XPOC integration
  Dec 2008: proof-of-concept prototype of moving the XPOC analysis modules into the PM framework
  W12: ready to demo the first “real” version of the XPOC server based on the PM framework
    in play-back-mode with data recorded last year
  Start April: up-and-running operationally when the Kicker people will start pulsing again

## Slide 6: AC Dipole
HWC of the MKQA and AC dipole systems is planned in wk18-19 (just after SPS startup)
  Meeting this week – actions are in place (J.Uythoven our link)