## Slide 1: Wednesday 8.9
External crossing angles:
  IR1: -170 mrad at inj./ramp and -100 mrad in squeeze/collision
  IR2: +170 mrad at inj./ramp and +110 mrad squeeze+collision
  IR5: +170 mrad at inj./ramp and +100 mrad in squeeze/collision
  IR8: -170 mrad at inj./ramp and -100 mrad in squeeze/collision
Good for beam-beam (do we need it for 150ns ?)
Bad for aperture and MP (are we ready to do this ?)
Strategy (Wednesday)
  Work with nominal angles at injection
  See if we can run like this
  Measure IR apertures
  Test parasitic beam-beam with lower angles
  Decide (Friday?)

## Slide 2: Wednesday 8.9
07h00: Scheduled access for QPS*3, RF, CMS, ALICE
12h00: Recover but then problems
  RF module. We now work with 2B2 klystron off.
  Lost sector 81 due to electrical problem (access needed)
14h00: Started injection work in TL to TEDS
  Centering checks of 5 TCDIs with trains of 4 ~nominal
  Some offsets of up to 0.5 sigma found and corrected
  Gaps at +- 4.5 sigma

## Slide 3: Wednesday 8.9
19h00: Continuation commissioning of injection of bunch trains
  Centering of collimators with trains of 4 ~nominal
  Started with interleaved B1 and B2, but a lot of uncaptured beam, B1
  We had 7 batches in B1 and 6 in B2
    Both beams dumped with unbunched beam on TDI giving losses B1
    Partial data taken for both beams

## Slide 4: Wednesday 8.9
21h00: Continuation commissioning of injection of bunch trains
  Beam 2 only
    Losses increase at +1.5 sigma, no increase out to -2.5 sigma
    13 * 4 trains of ~nominal
    Clean beam dump
  Beam 1 only …
  SPS off at 22h
    BA1 transformer

## Slide 5: Wednesday 8.9
23h00: Continuation commissioning of injection of bunch trains
  Beam 1 only
  SPS off at 23.30
    BA1 transformer again
***SUMMARY of INJECTION STUDIES*** Checking TL collimators with bunch train injections (4 nominal bunches):
moved the gap, recorded losses in TL and LHC injection region
centered the following collimators: TCDIV.20607 TCDIH.29050 TCDIV.29012 TCDIH.29205 TCDIH.87441 TCDIV.87645 Stopped centering of TCDIH.29645 due to SPS injection transformer problem. All new settings are trimmed into LSA and thresholds adjusted.

## Slide 6: Wednesday 8.9
Night
  Ramp, but beam lost protection interlock
    Had to mask collimator position interlocks, one was missed
  Ramp OK
    Trimmed Xing angles 1 and 2 to 100 and 110 and corrected closure
      Lost B1 with a corrector trip when doing IR5
      Continued with B2, Xing angles 5 and 8 to 100 and 100
  Squeeze B2
  Brief optics studies on B2
    Global correction
    Impressive results !
IP1 3.22 0.22 3.62 0.40 IP2 3.83 0.61 3.43 0.26 IP5 3.67 0.07 3.28 0.25 IP8 3.26 0.10 3.51 0.09

## Slide 7: Thursday 9.9
Aperture studies (until ~ midday)
Continuation commissioning of injection of bunch trains
  Still 2 shifts needed
Beam 1 capture issues
Orbit cleaning

## Slide 8: Week Planning
9 | Thu | M | 5 | IR aperture measurement at 450GeV
9 | Thu | A | 11 | Injection / injection protection - crossing angles ON, injection protection
9 | Thu | N | 8 | Ramp test with new collimator functions (1e10 the 1e11). PLL in parallel ?
10 | Fri | M | 8 | Injection / injection protection: crossing angles ON - injection of trains of 12
10 | Fri | A | 3 | First look at beam-beam with trains of 12
10 | Fri | A | 5 | Ramp of 1e11. RF longitudinal blowup. V reduction at injection.
10 | Fri | N | 8 | Reserve
11 | Sat | M | 8 | RF set up with 4 bunches of 150ns spacing. Transverse feedback.
11 | Sat | A | 8 | Collimation set up at 3.5TeV. End of ramp and after Xing angle change.
11 | Sat | N | 8 | Loss maps.
12 | Sun | M | 8 | Reserve
12 | Sun | A | 8 | Collimation set up at 3.5TeV. End of squeeze and collision settings.
12 | Sun | N | 8 | Loss maps.
13 | Mon | M | 8 | Injection / injection protection: crossing angles ON - injection of trains of 4
13 | Mon | A | 8 | RF set-up with more batches at injection
13 | Mon | N | 8 | Collimation set up at 3.5TeV and loss maps.
14 | Tue | M | 8 | Collisions ?