## Slide 1: BI cont.
*** Summary Matching Monitor test *** We only had ~15minutes of inject and dump, but managed to see a profile with ~9e9 p (!)

## Slide 2: ATS optics
Squeezed down to 40 cm

## Slide 3: ATS optics
Measurements were conducted at b* 1m and 40cm. The beta-beat is increasing from 30% to 50% for beam 1 horizontal and from 20% to 40% for beam 2 vertical. A correction was calculated and implemented for beam 1 at 40cm, this reduced the peak beta-beat from 50% to 20%. For beam 2 a correction will need to be calculated off-line, it is expected that because of the missing BPMs global correction could not calculate and effective correction. For the correction only ~20 correctors around IP1 and IP5 were used.

## Slide 4: ATS optics
R. Tomas et al.

## Slide 5: ATS optics
Premature end of the ATS MD due to trip of trim quadrupoles when re-distributing the strength among sectors before telescopic squeezing
R. Tomas et al.

## Slide 6: Ion commissoning
17:30 Beams to last TEDs to adjust kicker timing
Problem with the SPS Rephasing for Pb:
  The rephasing would often not work. We notice a systematic 3 Hz error between the LHC/2 frequency and the one sent to the SPS through the FESA class AllPhaseSynchroSPS. We trim the FESA class manually. In the meantime best not to trim the injection frequency  To be followed-up with experts
21:30  both beams circulating
23:40  Flat-top
01:30  Collision in ALICE
02:00  Collisions in ATLAS and CMS (large trims required)
Quiet beams until 03:00

## Slide 7: Ion commissoning
Still some problems with re-synchronization (not catched by BQM)
QPS problems for RCD-RCS in Sector 12
05:30 – 06:30 Loss maps at injection
Preparing for injection and ramp to 3.5 TeV  Lost communication with TCTs in point 1

## Slide 8
Issues:
  Run configuration still set to protons  CO
  Wire scanner signal quite noisy for B1
  SPS-LHC synchronization
  BQM not stopping injections in case of bad synchronization

## Slide 9: Plan
Access ongoing
Afternoon - evening:
  Setting-up of collimators (TCTs in point 2)
  Loss maps + Asynch dumps (verifications of tune and orbit feedback during the cycle)
  ALFA: if loss maps at 7 mm is required people from ALFA should be around
  Definition of the functions for the TCTs during ALICE squeeze
Night: chance to go for stable beams if all conditions (machine protection) are met and OK from rMPP.
Monday 6 AM beam dump