## Slide 1: Tue/Wed 1-2.11.11
Lot’s of time lost due to cryo problem in IR8.
Major impact, therefore review of MD program…
Start discussion here, please let us know your input.
Will probably decide in LMC meeting this afternoon.

## Slide 2: MD Planning Sun – Mon (30. – 31.10.)
Day | Time | MD | MP
Sun | 16:00 | Ramp down, cycle | 
 | 18:00 | 450 GeV  3.5 TeV: Dry run ATS optics | A
 | 21:00 | Ramp down, cycle | 
 | 23:00 | 450 GeV: Tune working points – half integer WP, more space for tune footprint, lower crossing angle, lower beta*, … | A
Mon | 07:00 | 450 GeV  3.5 TeV: Proton-Lead – feasibility of new physics scenario | A/B
 | 23:00 | Ramp down, cycle | 

## Slide 3: MD Planning Tue (1.11.)
Day | Time | MD | MP
Tue | 01:00 | 450 GeV: TDI Vacuum – understand source of heating, check for HOM’s. Parasitically: UFO studies | C
 | 09:00 | 450 GeV: UFO studies - Understanding UFO’s and possible limitations. Parasitically: scraping setup & first tests (on other beam?) | C
 | 11:00 | 450 GeV: Scraping for beam shape - More accurate beam models for machine protection studies and beam loss simulations (high intensity tails) | 
 | 13:00 | 450 GeV  3.5 TeV: LR beam-beam with 25ns – Assess required crossing angle and achievable beta* (performance) with 25ns | C
 | 21:00 | Ramp down, cycle | 
 | 23:00 | 450 GeV  3.5 TeV: Beam instrumentation – Improvements of LHC beam measurements. One goal: calibrated BSRT emittance data for beam1 and beam2 at 3.5TeV | B
Wed | 07:00 | Ramp down, cycle | 

## Slide 4: MD Planning Wed (2.11.)
Day | Time | MD | MP
Wed | 07:00 | Ramp down, cycle | 
 | 09:00 | 450 GeV  3.5 TeV: ATS and tight collimation settings – Squeeze in IR1&5 to 40cm beta*. Optics correction. Collide (no crossing angle). Show adequate protection with tight collimation settings. Show full protection. Provides 2.5 times higher pile-up potential… | A
 | 19:00 | Ramp down, cycle | 
 | 21:00 | 450 GeV  3.5 TeV: Combined ramp & squeeze - Feasibility of changing the LHC optics during the ramp. Gain ~7min (400s) per ramp initially. Higher efficiency for physics | B
Thu | 05:00 | Ramp down, cycle | 

## Slide 5: MD Planning Thu (3.11.)
Day | Time | MD | MP
Thu | 05:00 | Ramp down, cycle | 
 | 07:00 | 450 GeV: Injection stability and losses – check steering constraints, define limits for correctors, operational procedure for more stable injection line steering | B
 | 15:00 | 450 GeV: Quench margin at injection – BLM thresholds required at injection, room for optimization | C
 | 19:00 | 450 GeV  3.5 TeV: Quench margin at 3.5 TeV – apply transverse damper method, confirm May result, longer sustained losses, identify other possible limitations (know already about BLM power supplies); If any beam left Wire Scanner Quench Test | C
Fri | 03:00 | Ramp down, cycle. Access for MKA (preparation non-linear MD). | 

## Slide 6: MD Planning Fri (4.11.)
Day | Time | MD | MP
Fri | 03:00 | Ramp down, cycle. Access for MKA (preparation non-linear MD). | 
 | 05:00 | 450 GeV: Non-linear dynamics – understand dynamic aperture in LHC, compare to models, experimental reference case for upgrade studies | B
 | 13:00 | 450 GeV  3.5 TeV: Longitudinal beam stability – Explore single and multi-bunch stability in longitudinal phase space, instability thresholds, optimal and required RF parameters | B
 | 21:00 | Ramp down, cycle. | 
 | 23:00 | 450 GeV  3.5 TeV: ATS – Simultaneous squeeze to 0.1m in IR1 and IR5 with pilot beam, test of possible future upgrade optics for LHC | A
Sat | 05:00 | Ramp down, cycle. | 
 | 06:00 | End of MD #4 | 

## Slide 7
# | MD | Length [h] | Result
1 | Dry run ATS optics | 3 | success
2 | Tune working points | 8 | success
3 | Proton – Lead | 16 | success
4 | TDI vacuum; UFO | 10 | success
5 | Beam shape scraping | 2 | lost
6 | LR beam-beam 25ns | 8 | lost
7 | Beam instrumentation | 8 | lost
8 | ATS and tight collimator settings | 10 | lost
9 | Combined ramp and squeeze | 8 | cryo back?
10 | Injection stability and losses | 8 | 
11 | Quench margin at injection | 4 | 
12 | Quench margin at 3.5 TeV | 8 | 
13 | Non-linear dynamics | 8 | 
14 | Longitudinal beam stability | 8 | 
15 | ATS | 6 | 
x | IR2 aperture | 8 | to be done?
Scenario 1

## Slide 8: Should we re-schedule? For discussion...
25ns LR beam-beam MD delayed to 2012 after likely 25 ns scrubbing run. CMS solenoid is off (e-cloud effects).
Lost MD‘s with impact on decisions/performance for 2012 running:
  Tight collimation settings for achievable beta* (combined with ATS to 40 cm)
  Beam instrumentation MD  needed for fine tuning of LHC performance
  IR2 aperture  needed for feasibility of 1m beta* in ion run
  45 degree crossing in IR8
Lost MD‘s with impact for required upgrade studies:
  Beam shape scraping  coll & machine protection studies
Lost MD‘s for commissioning / testing new techniques:
  Quench margin at 3.5 TeV  beam blow-up with ADT
Upcoming MD‘s that can be delayed to beginning of 2012 run without direct impact on decisions for 2012 running:
  Quench margins at 450 GeV and 3.5 TeV
  Non-linear dynamics
  ATS to 10cm
  Combined ramp and squeeze

## Slide 9: Should we re-schedule? For discussion...
Must decide on whether we want to re-prioritize MD program.
Possibility to schedule IR2 aperture check early (ion commissioning study). Gain time back on Saturday morning from ion commissioning (ion beam worked very well during proton – lead MD).
Can we schedule an early MD in 2012 to perform the delayed MD‘s and to feed results into the 2012 commissioning of the machine?

## Slide 10
# | MD | Length [h] | Result
1 | Dry run ATS optics | 3 | success
2 | Tune working points | 8 | success
3 | Proton – Lead | 16 | success
4 | TDI vacuum; UFO | 10 | success
5 | Beam shape scraping | 2 | reschedule ?
6 | LR beam-beam 25ns | 8 | lost
7 | Beam instrumentation | 8 | reschedule ?
8 | ATS and tight collimator settings | 10 | reschedule ?
9 | Combined ramp and squeeze | 8 | cryo back?
10 | Injection stability and losses | 8 | 
11 | Quench margin at injection | 4 |  2012 ?
12 | Quench margin at 3.5 TeV | 8 |  6 h
13 | Non-linear dynamics | 8 |  2012 ?
14 | Longitudinal beam stability | 8 | 
15 | ATS | 6 | 
x | IR2 aperture | 8 | Introduce
x | 45 degree crossing in IR8 | 8 | was 25ns…
Scenario 2