## Updated
Date | Day | Shift | Column10 | Column9 | Time (h) | Activity | Breakpoint | System/topic | Beam | Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8

## Schedule
Day | Shift | start | end | Activity | System/topic | Beam | Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7
SUN | M | 7:00 | 15:00 | Re-commissioning of RQF.A12 - TI2/8 stability tests in parallel
SUN | A | 15:00 | 16:00 | BLM interlock verification - pilot on TCP in point 7 | OP | Probe | Column1: Call Christos Zamantas 1 hour in advance
SUN | A | 16:00 | 19:00 | Damper checks | RF | A few indiv - Super Relaxed SBF at 450 GeV - need to mask total voltage control
SUN | A | 20:00 | 21:00 | Tune and orbit feedback checks at injection | BI | Probe
SUN | A/N | 21:00 | 2:00 | Full cycle with beam up to collisions - chromaticity/tune measurement and correction - new b3 correction at flat-top - New LHCb polarity (negative) - dump beam by inducing a FGC fault on RD34 in point 3 | OP | Fat Probe
SUN | N | 2:00 | 3:00 | FMCM checks (RBXWTV.L2, RBXWTV.R2, RD34.LR3, RD34.LR7) - Induce FGC fault with circulating beam at injection | OP | Probe
SUN | N | 3:00 | 5:00 | LSS6 BPM checks | OP | Probe
MON | M | 5:00 | 10:00 | Full cycle with beam up to collisions - TCT alignment checks in collision after getting head-on collisions at IPs and reseparated to nominal settings in IP8 - Loss maps in these conditions (betatron and negative off-momentum loss map) - New LHCb polarity (negative). | OP/ABP | Indiv
MON | M | 10:00 | 15:00 | Full cycle with beam up to flat-top - Loss maps in these conditions (betatron) - New LHCb polarity (negative) | OP | Indiv
MON | A | 15:00 | 18:00 | Injection kicker synchronization and kick length checks | BT | Probe/Indiv/50ns
MON | A | 18:00 | 20:00 | Cavity phasing B1 | RF | A few indiv - Super Relaxed SBF at 450 GeV - need to mask total voltage control
MON | A |  |  | Physics with 84 bunches - length scale calibration (~3 hours) - low pile-up for CMS | OP | 50 ns
MON | N |  |  | Physics 480 bunches after LHCb polarity inversion (tbc) - low pile-up for CMS | OP/RF | 50 ns
TUE | M |  |  | Re-check the phasing of the cavity sum B1 (maybe access to UX45) - 1 hour | RF |  | Column1: 1 hour requested
TUE | A |  |  | Physics with 840 bunches - variable gain for the damper | OP | 50 ns
TUE | N |  |  | Physics with 1380 bunches | OP | 50 ns
|  |  |  | Full cycle with beam - chromaticity/tune measurement after correction - dump beam by inducing a FGC fault on RD34 in point 7 | OP | Fat Probe
|  |  |  | TDI checks (cold) - 3 hours | OP/ABT | Probe/Indiv

## Nottoforget
Change the strength of the landau damping octupoles due to the recovery of the ROF.A81.B2
Invert polarity in LHCb (negative)
Insert ROF.A81.B2 in the soc and RCBV17
Test RD34 in 3 and 7