## Slide 1: Plan for start-up with beam
Friday
  19:00 Machine closed. Ramp for powering tests & pre-cycle
  22:00 Pilots through nominal cycle up to collisions. Measure chroma during squeeze. Check dump of pilots
  If time left over night: second ramp with pilots. Open primary collimators at flat top for manual chroma measure at collision
Saturday
  08:00 Check BPMS.
    3 nominals. Interlocking with bump and scraping
    BPMS – TCSG. Measure beam position w 12 nominals. Call Jorg. If position changed, check TCSG alignment
  10:00 Ramp into collision 2 – 3 nominals (< 3e11) for Roman Pot alignment. In principle only Totem alignment, max 5 hours alignment. Finish fill with
    Betatron loss maps with resonance crossing
    Asynch dump tests

## Slide 2: Plan for start-up with beam
Saturday continued
  19:00 Fill with 3 nominal bunches for loss maps (<3e11 p)
    Betatron loss maps at the end of the squeeze with separated beams (using the ADT on bunch 1 and 2)
    Possibly repeat betatron loss maps in physics (resonance) if not enough beam was left in the alignment fill.
    Negative off-momentum in physics (Roman pots IN)
Sunday
  02:00 No beam in the machines for the leap second
  02:05 Repeat another fill for asynch dump tests with Roman Pots in if there was not enough beam left after RP set-up
  06:00 injection loss maps with ADT method at injection – can also be done during the intensity ramp up
  If things go extremely well already start the intensity ramp up

## Slide 3: Intensity ramp-up
If all goes well: Sunday daytime
  84 bunches: 2 hours Stable Beams
  480 bunches: 6 hours Stable Beams for ATLAS (but don’t refill)
  840 bunches + 12 non colliding: Production fill
  1380 bunches: Production fill