## Slide 1: Plans
Machine closed by 19:00
  MKI point 8, Cryo conditions, vacuum expected to be OK by that time (Katy)
  RF should be ready in the late evening
What might delay the start-up:
  Switch on of Point 2 compensator this morning  watch out for cryogenics and ALICE (should be off)
  Electrical Network intervention planned at 17:00. Injectors in stand by and LHC off at that moment. Effects?

## Slide 2: In the best case…
19:00 – 23:00: Powering tests
23:00 – 24:00 Pre-cycle
19:00 – 24:00 Beams to last TED for Q20 optics extraction verification

## Slide 3: Plans (Saturday)
  00:00-05:00 Go through the whole cycle (with new collision process) with pilot beam for validation and chromaticity measurement (BBQ and BSRT verification in parallel).
  Switch off Active filters of main circuits and warm dipoles one by one for mains line perturbation observations.
05:00–09:00 Loss map in collision (betatron and -500 Hz).
  Wire scans for BSRT calibration
09:00–14:00 Setting-up of injection with Q20 optics
14:00-19:00 First step of the intensity ramp-up: very short fill with 78 bunches with new collision process.
19:00–23:00 Damper setting-up with larger bandwidth
23:00–03:00. Loss maps squeezed/separated: betatron and asynch.dump.
  Wire scans for BSRT calibration

## Slide 4: Plans (Sunday)
Intensity ramp-up:
  474 bunches
  834 bunches
  1374 bunches
Experiment requests:
  CMS request for period at low pile-up (~1)?
  ATLAS request for VdM scan?
  With 480 or 840 bunches?

## Slide 5
To be followed-up:
  Kicker (Pt.8) vacuum
  BSRT temperatures
Abort gap calibration will be done during one of the ramp with nominal bunches