## Slide 1: Saturday 19.1.2013
8:40 – 9:30 access for MKB (dilution kicker) LBDS B2 – PLC exchange
Pre-cycle
11:17 – 12:50 RF problem with ion injection (re-phasing), due to a disabled timing
Ions injected in wrong bucket
13:22 ion injection OK
Injection, ramp squeeze and collide; some TCT interlock limits needed correction
16:56 start set-up of vertical roman pots
18:07 ALFA pots at 13 sigma
18:20 TOTEM pots at 13 sigma
18:45 start loss maps
  B1H, B1V, B2H, B2V, and negative off-momentum (+500 Hz)
19:17 BLM dump by off-momentum loss map

## Slide 2: Saturday Night
Dry-run and correction of the sequence for driving RPs to physics settings
21:45 start injecting
23:30 betatron loss maps at flat top after cogging
0:06 betatron loss maps squeezed and separated
0:30 collisions and all experiments optimized, moving in RP
Fixing a problem with the abort gap monitor
1:49 asynchronous dump in collision with RPs in
2:50 start injection
4:54 positive off-momentum loss map in collision with RP in (dump by BLMs)
5:50 start injection
7:20 cogging done after squeeze (had been forgotten before)  BLM at 38% of dump threshold
7:33 negative off-momentum loss map squeezed separated

## Slide 3: Loss maps for Collimation validation
tbd=to be done
 | Injection (Inj. Prot. IN) | Injection (Inj. Prot. OUT) | Flat-top | Squeezed, separated | Squeezed Collision with RP IN
Betatronic-H | B1 DONE | B1 DONE | DONE | DONE | DONE
Betatronic-V | B1 DONE | B1 DONE | DONE | DONE | DONE
Neg. off-mom | B1 DONE | -- | -- | DONE (+500Hz) | DONE (+500Hz)
Pos. off-mom | B1 DONE | -- | -- | -- | DONE (-500Hz)
Asynch dump | B1 DONE – validated OK | -- | -- | tbd | DONE

## Slide 4: Plans
Loss maps:
  Asynchronous dump squeezed separated (1 ramp). Roman pots out.
  Complete injection loss maps (betatron, positive and negative off momentum, asynch dump) (~2-3 hours).
If OK from MPP:
  STABLE BEAMS Single_13b_8_8_8_pPb (1 hour of STABLE BEAMS)
  Then: Injection of trains of p and Pb for the intermediate filling scheme: 200ns_96p_120Pb_4inj24bpi (2 hours of STABLE BEAMS)
No Roman pot insertion in STABLE BEAMS before Monday.

## Slide 5: Pending
For the time being the gain of the damper is not gated as well as the BBQ reading
Extraction conditions and transfer line trajectory for ions to be checked
Margin for 1 cavity trip for RF HW interlock (1 hour during ramp down) could be re-introduced
Damper setting optimization