## schedule
Goals:
Commissioning with bunch trains (150 ns)
No contingency: assumed 100% beam time
| Day | Start | Time (h) | Activity | Comments
3 | Sun | N | 7 | ramp at 10 A/s with single bunch/beam 1e10 + squeeze and crossing angles ON during the ramp - measurement of non closure during the squeeze | Feedforward from previous measurements should be implemented Chromaticity measurement during the ramp - collimators open. Crossing angles on during the ramp
4 | Mon | M | 4 | Measurement of non-closure during the squeeze - almost finished - IR 8 to redo
4 | Mon | M | 4 | Injection / injection protection - crossing angles ON - TDI setup | Steering of trajectory in TLs and adjustment of TCDIs
4 | Mon | A | 4 | Injection / injection protection - crossing angles ON - Transfer lines and inject
4 | Mon | A | 4 | Transverse feedback setting up: noise reduction (450 GeV - single nominal bunch) - Beam 2 - crossing angle ON
4 | Mon | N | 8 | PLL setting-up / K modulation at 450GeV
5 | Tue | M | 8 | Collimation in IR at 450GeV
5 | Tue | A | 5 | Collimation in IR at 450GeV | Steering of trajectory in TLs and adjustment of TCDIs
5 | Tue | A | 3 | Tranverse feedback - not quite finished
5 | Tue | N | 8 | Test ramp 1e10, crossing angle, beat-beat, k-mod - didn't manage this
6 | Wed | M | 5 | Scheduled access for QPS, RF, CMS, ALICE, recovery
6 | Wed | M | 6 | Time lost to technical problems
6 | Wed | A | 5 | Injection / injection protection - lot of time lost (above), only 3 h of beam time | Needs collimation at 450GeV to be done
6 | Wed | N | 2 | Orbit cleaning - not done
6 | Wed | N | 6 | Test ramp 1e10, crossing angle, beat-beat
7 | Thu | M | 5 | IR aperture measurement at 450GeV - not done..cryo problems
7 | Thu | A | 9 | Injection / injection protection
7 | Thu | N | 8 | Ramp test with new collimator functions (1e10 the 1e11)
8 | Fri | M | 8 | Time lost to technical problems (6h). Injection of trains.
8 | Fri | A | 4 | First look at beam-beam with trains of 8 | Need this to decide if OK with 170urad
8 | Fri | A | 4 | Aperture IR
8 | Fri | N | 8 | Aperture IR continued. Test ramp.
9 | Sat | M | 8 | RF set up. Energy matching, voltage at injection, injection of many trains of 4
9 | Sat | A | 8 | Collimation set up at 450GeV with wider TCTs | Nominal bunch
9 | Sat | N | 8 | Loss maps at 450 GeV
10 | Sun | M | 8 | Ramp commissioning, longitudinal blowup, ramp nominal
10 | Sun | A | 8 | Collimation set up at 3.5TeV (IR3 and TCTs) | Nominal bunch
10 | Sun | N | 8 | Loss maps at 3.5TeV (end of ramp)
11 | Mon | M | 8 | Injection protection qualification for injection of unsafe beam part 1 | Inject trains of 8 and 12 bunches (150 ns) to LHC
11 | Mon | A | 8 | Loss maps at 3.5TeV (end of ramp)
11 | Mon | N | 8 | Collimation set up at 3.5TeV (TCTs at end of ramp and with reduced Xing)
12 | Tue | M | 8 | Injection protection qualification for injection of unsafe beam part 2
12 | Tue | A | 8 | RF set up with multibuch injection, transverse feedback
12 | Tue | N | 8 | Collimation set up at 3.5TeV (TCTs at end of squeeze and collision)
13 | Wed | M | 8 | Loss maps at 3.5TeV (end of squeeze)
13 | Wed | A | 8 | Ramp and squeeze bunch trains
13 | Wed | N | 8 | Loss maps at 3.5TeV (collision)
14 | Thu | M | 8 | Collimation integration into sequencer and tests
14 | Thu | A | 8 | Ramp and squeeze bunch trains - collisions with 3 trains of 8
14 | Thu | N | 8
15 | Fri | M | 8
15 | Fri | A | 8
15 | Fri | N | 8
|  |  | parasitic | Check of BSRT (bunch in bucket 1 and possibly bunch in the last bucket before the abort gap) ==> A. Boccardi
|  |  | 8 | Alice spctrometer compensation for different polarities (8 hours)
|  |  | 8 | Setting-up of the 2in 1 collimators