## Slide 1: Friday 23.7
Morning: struggling to get back from Technical Stop
  Problems related to function generation for 10 A/s pre-cycle.
  Problems related to Inner Triplet magnets in IR8  change optical fiber
  Problems with QHPS in sector 45  needed to change the switch.
10:00: Starting pre-cycle of all circuits:
  Problems closing the switches in S78 (arc magnets tripped): S78 had been switched off at the end of the pre-cycle directly without going through standby by the previous shift crew  ca 200 A left in the circuit.
  Problems closing the switches for the RQTF circuits (worked after several attempts).
  ATLAS solenoid ramping up
  Problems with orbit in SPS: studies ongoing all morning
  Triplet in IR2 left tripped during pre-cycle
  FMCM fault in Q5 IR3 -> repair requires magnet to be switched off.
  Still some problems when loading pre-cycle functions (RQD-RQF).

## Slide 2: Friday 23.7
11:00: Problem in the SPS traced to magnet short  repair implies no beam for the LHC over the next 24 hours.
  Will precycle and run Dry runs in the LHC until Saturday noon.
12:00: Start Dry runs in the machine
  Pre-cycle with 10 A/s is OK (IT L2 needed some tune-up).
  Dry-run went though first time without problems (4 in total).
  New ramp-down combo gave some problems for triplets, some RCBW and some RCD circuits.
  Short access for repair of CMS short.
  BPM System Upgraded to include temperature correction.

## Slide 3: Saturday 24.6
SPS magnet repaired but have potential issue with vacuum at extraction kicker (piquet called)
RF problem in the PS  requires access (couple hours).
Plan for the day and weekend once beam becomes available:
  Beam dump and IR6 BPM tests at 450 Gev.
  Ramp of single pilot bunch per beam with beam dump test at 3.5 TeV.
  test ramp of single nominal (0.9 1011) bunch per beam; SMP; full cycle, optic verification (AC dipole); loss maps for collimation verification.
  Saturday-Sunday night: Fill with 13 bunches per beam with stable physics.
  Sunday morning: multi bunch injection studies.
  Sunday evening: Fill and ramp with 25 bunches per beam with stable beams if possible.