## Slide 1: 02/09/2010
Access conditions for test of the RB.A23 at 17:30. Splice mapping.
Complete machine closed by ~18:00.Problems in getting TI2 ready for injection (some PC still blocked-out) + ALICE inj. permit
19:30 – 20:00 verification of the beam trajectory in TI2 and TI8 in order to check for any potential effect of magnet replacement in SPS with pilot beam. Only minor (H) corrections applied (Jörg): not yet copied to the other cycles. To be verified once we move to trains.
Accesses in points 5 – 6 and 8 to solve problems with QPS and completion of re-commissioning of circuits affected by interventions during the technical stop

## Slide 2: 02/09/2010
01:30: all circuits tests completed. OK from MP3 to power RB.A23. Machine closed and ready for pre-cycle
04:00 Machine ready for injection for B2 at ~04:00. Issue with interlock coming from TI2 collimators for injection of B1
Corrections for B2 orbit
06:30 Access in point 2 for interlock issue. Problem with a cable connection.
07:30 End of access start pre-cycle

## Slide 3: Plan
3 | Fri | M | 8 | Ramp/squeeze/collision test with single bunch/beam 1e10 at 2 A/s for qualification of the status of the machine + dump qualification\
3 | Fri | A | 4 | Transverse feedback setting up: noise reduction (450 GeV - single nominal bunch)
3 | Fri | A/N | 8 | ramp at 10 A/s with single bunch/beam 1e10 + squeeze: measure - correct - re-measure beta beating @3.5 m- K-modulation + dump qualification
4 | Sat | M | 8 | Injection / injection protection: bunch trains up to 12 bunches (150 ns spacing) - crossing angles ON
4 | Sat | A | 4 | Injection / injection protection: bunch trains up to 12 bunches (150 ns spacing) - crossing angles ON
4 | Sat | A | 4 | Check whether 100 murad half-angle OK with 12 nominal bunches
4 | Sat | N | 8 | ramp at 10 A/s with single bunch/beam 1e10 + squeeze: measure beta beating@3.5 m
5 | Sun | M | 8 | Transverse feedback setting up: noise reduction (450 GeV - single nominal bunch) - crossing angle ON
5 | Sun | A | 8 | Injection / injection protection: bunch trains up to 4x12 bunches (150 ns spacing) - crossing angles ON
5 | Sun | N | 6 | ramp at 10 A/s with single bunch/beam 1e10 + squeeze and crossing angles ON
6 | Mon | M | 8 | Injection / injection protection: bunch trains up to 4x12 bunches (150 ns spacing) - crossing angles ON
6 | Mon | A | 8 | Collimation set-up at 450 GeV/c
6 | Mon | N | 8 | Transverse feedback setting up: noise reduction (450 GeV - single nominal bunch) - crossing angle ON

## Slide 4: 02/09/2010
Polarities for ALICE solenoid/spectrometer: + +
Polarity for LHCb spectrometer: -
External crossing angles:
  IR1: -100 mrad at inj./ramp/squeeze/collision
  IR2: ±170 mrad at inj./ramp and ±110 mrad squeeze+collision
  IR5: +100 mrad at inj./ramp/squeeze/collision
  IR8: -100 mrad at inj./ramp/squeeze/collision
  To be finalized crossing angle for injection/ramp: 170 mrad at inj./ramp for all IPs?