## Slide 1: Tuesday
Fill 1494 dumped by operations at 09.00 (~ 0.25 ub-1 in ~6.5 h): LSS6 BPM interlock test
13:00 Fill 1495 dumped by RF dump (cavity quench)
14:00-17:30 Access for flooding alarm in point 4. In parallel:
  BI
  Vacuum to replace controller for 2 vacuum gauges for injection kicker
18:30 Power converter problem during pre-cycle (RQT13.L2B2), already occurred several times  Access
20:00 Pre-cycling
21:30 injection
00:30 STABLE BEAMS #1496
06:00 Beam dump and Start preparation proton MD

## Slide 2: Fill 1494
End of physics 1494: 0.25 mb-1 in 6.5 hours

## Slide 3: Fill #1495
Injection starting at 10:00
Large emittance in the V-plane B2 particularly  correlated with V- injection oscillations B2  Corrected 
B1-H: 2.4 mm B1-V: 2.9 mm
B2-H: 3.0 mm B2-V: 4.0 mm
B2V: 7.0 (!) mm
B1V: 3.2 mm
B2H: 3.7 mm
B1H: 3.2 mm

## Slide 4: Fill #1495
13:00 RF beam dump due: ACSModuleM1B2 :: He tank Pressure interlock Level 2 exceeded (Quench)
Decided to give access for flooding alarm at the bottom of PZ45 appeared at ~12:30 and after verification by TI and CV  Problem was real (water level in the sump reached high level because the water pump did not start - float was stuck) but no flooding.

## Slide 5: Fill #1496
00:30 Stable Beams #1496
Intensities on Fast BCT displayed in Page 1 underestimated after installation of the attenuators and expert intervention  to be followed up today
06:15 Beams dumped to start switch-over to protons: ~0.3 mb-1 delivered in ~6 h. In total ~2 mb-1

## Slide 6: Proton MD program
 | Start time | Duration [h] | 
Wed 17 | 06:00 |  | Dump and precycle – Switch to protons
 | 08:00 | 4 | Interlock checks
 | 12:00 | 7 | Injection and damper checks for 75ns
 | 19:00 | 22 | Injection of trains of 24/48 bunches and e-cloud measurements
Thu 18 | 17:00 | 4 | Switch to 50ns, injection and damper checks
 | 21:00 | 6 | Test ramp with pilots
Fri 19 | 03:00 | 10 | Ramp 9x12 50ns bunches
 | 13:00 | 5 | Stability measurements, 50ns and 75ns beams
 | 18:00 | 4 | Interlock checks
 | 22:00 |  | Back to ion physics
Total MD time |  | 64 |