## schedule
| Day | Shift | Time (h) | Activity | Key aims
2 | WED | 15:30 | 5 | Access
2 | WED | 21:00 | 5 | Ramp and squeeze to 3.5 TeV: MP and test collisions (2 pilots per beam)
3 | THU | 2:00 | 7 | Beta beating & coupling correction and measurement through the squeeze
3 | THU | 9:00 | 8 | Trial ramp to 3.5 TeV with 1 nominal bunch (RF blowup, orbit, emittance, damper, ...)
3 | THU | 17:00 | 4 | Transverse damper for multi-bunch
3 | THU | 21:00 | 6 | 2nd ramp to 3.5 TeV with 1 nominal bunch, no squeeze or BPM check vs intensity
4 | FRI | 3:00 | 5 | Collimation qualification (loss maps) at 450 GeV
4 | FRI | 8:00 | 1 | BLM tests of new software
4 | FRI | 9:00 | 8 | Injection and dump setup (higher intensity, MP, …)
4 | FRI | 17:00 | 8 | Collimation setup 3.5 TeV before squeeze, 1 nominal bunch
4 | SAT | 1:00 | 6 | Qualification dump protection, injection protection, collimation
4 | SAT | 7:00 | 8 | Injection and dump setup (higher intensity, MP, …)
4 | SAT | 15:00 | 8 | Collimation setup 3.5 TeV before squeeze, 1 nominal bunch
4 | SAT | 23:00 | 8 | tbd
5 | SUN | 7:00 | 8 | Collimation setup 3.5 TeV before squeeze, 1 nominal bunch
5 | SUN | 15:00 | 8 | tbd

## To be scheduled
RF | To adjust front-end for higher bunch intensity (estimated 1 hour with beam) and get collision point fine-adjusted for the experiments (estimated 1 hour inject&dump or circulate&dump). | 2 hours | Philippe
RF | following the cavity phasing, we should (ideally) fine-adjust phase shifters in the cavity sum located in UX45. This requires an access to UX45 with RF ON. I heard that there will be a stop next Monday-Tuesday. Can we get ~ 1 hour with RF ON (nobody in IP4) with access to UX45? | 4h | Philippe Let Andy know or reply or call me at 75581