## Slide 1: Technical Stop #4 29th August - 2nd September 2011
Day 3
Julie Coupard
Schedule and Coordination

## Slide 2: Summary after Day 3
Cryogenics
    Done Intervention on oil pipes @Pt6 on surface
Cabling
    Ongoing BLM @Pt3
    Ongoing NG18 replacement @Pt3
    Ongoing Thermo-switch @Pt1&2
    Ongoing Monitoring cryo @Pt4
Beam Instrumentation
    Ongoing BLM: Direct beam dump connection to dump system
    BPM: New firmware and SW to increase IIR filter order
Kickers
    Done Change of generator pos K @Pt6 – revalidation tests ongoing
    Done Change of generator HV switch @Pt2 – revalidation tests ongoing
Machine Protection
    Done Adjustment of 600 A Energy Extraction Switches
      DQEMC.UA63.RQTD.A56B1 – test to perform
      DQEMC.UA43.RCS.A34B1 – test to perform

## Slide 3: Powering Tests
Circuit | Test | Current | Length | Constraints | UPS | DFB concerned | Patrol | CRYO OK | Lock | When
RCBCV9.R3B2 | R meas (MP3) |  |  | These tests will be done during the day with very low current and presence of people | P3 P4 |  | NO | A34 | NO | Mon
RCBCH7.R3B1 | R meas (MP3) |  |  |  | P3 P4 |  | NO | A34 | NO | Mon
RD3.R4 | ISRM meas (MP3) | ~3000 A | 2h | ElQA after PXI inst | P4 | DFBMK | P 4 5 6 | MR4 | NO | Wed
RD4.R4, RQ5.R4 | ISRM meas (MP3) | ~3000 A | 2h | ElQA after PXI inst | P4 | DFBML | P 4 5 6 | MR4 | NO | Wed
RQ6.R4 | ISRM meas (MP3) | ~3000 A | 2h | ElQA after PXI inst | P6 | DFBMG | P 6 7 8 | MR4 | NO | Thu
RQD/F.A56 | Quench propagation test | I_nom | tbd | Powering phase II | P5 P6 | DFBAJ DFBAK | P4 P5 P6 | A56 | NO | Wed (& Thu ???)
RQD/F.A45 | Multiple FPA | see below | 6h | Powering phase II | P4 P5 | DFBAH DFBAI | P4 P5 P6 | A45 | NO | Thu
RU.L4 | Test on zero-offset reset | 400 A | 2h |  | P4 | DFBME | NO | ML4 | NO | Thu

## Slide 4: Status of patrol
Pt2
Friday 7h30
Pt1
Friday 17h
Pt8
Thursday 17h

## Slide 5: Program for Friday
Deconsignation of injection lines (Ti2, Ti8) on Friday afternoon
  Steve Hutchins will take the SPS keys for LHC extraction so the LHC will remain safe during the Patrols on Friday evening
Last patrols at 17h
  Point 1
End of the Technical Stop around 18h30 (if no more patrols)
People in CCC to give the green light for beam : S.Hutchins
EIC : L.Ponce