## Slide 1: Technical Stop #4 29th August - 2nd September 2011
Summary
Julie Coupard
Schedule and Coordination

## Slide 2: First feedback
RP surveys
  RP teams need more and more time to do the survey  increase the length of RP survey till 10:30 and 12:00 on MON morning
Access
  Badge of access  access service @build.55
  Problems with some PAD and/or MAD (ODM asked directly)
  Access system // Access authorization
Patrols lost
  Door forced @Pt1 and @Pt5
  PAD @Pt4 and @Pt7
Safety
  Pulling of cables @Pt4  no VIC and no cryo lock-out asked
CRYO
  Stop of the Compressor @Pt8 THU afternoon but cryo conditions recovered on FRI afternoon
Closing of the LHC machine on FRI 16:30

## Slide 3: Interventions pointed out before the TS
Cryogenics
    Done Intervention on oil pipes @Pt6 on surface
Cabling
    Done BLM @Pt3
    Done NG18 replacement @Pt3
    Done Thermo-switch @Pt1&2
    Done Monitoring cryo @Pt4
Beam Instrumentation
    Done BLM: Direct beam dump connection to dump system
    Done BPM: New firmware and SW to increase IIR filter order
Kickers
    Done Change of generator pos K @Pt6
    Done Change of generator HV switch @Pt2
Machine Protection
    Done Adjustment of 600 A Energy Extraction Switches
    Done Quench Propagation Tests in the sector 56

## Slide 4: Change of the optical fibers
Intervention on MON
  Inhibition of the BIW  locking-out of the injection lines Ti2 and Ti8 (coordination with the DSO)
  No patrol dropped
LASS – GS/ASE feedback
  a very positive exercise for our team and a rare opportunity of testing a degraded network mode of operation:
    The LASS network loop connecting the PLCs works as designed - it can withstand a single network failure without consequences for operation; the associated diagnostics functions correctly.
    If possible, using the exact cable/fiber identifiers in the initial presentation of an intervention scope would be beneficial for a more precise estimation of the intervention’s impact.
    The LASS loop and the BIS fibers today share the same cable between UJ76 and RE78.
BIS – TE/MPE feedback
  The attenuation values for the new fibers were a little bit higher than the previous ones (when they have been initially installed); however, within the standard limits.
  The additional measurements done, in order to know the new noise margins, validated again the values
  Some additional tests have been performed in setting the LHC Beam Permit Loops in test mode. Everything was fine

## Slide 5: MANY THANKS TO..
.. EN/EL and GS/ASE for their fast reactivity and flexibility to identify and solve the problem on the optical fibers
.. All groups and Experiments for their collaborations
Thanks for your attention