## Slide 1: Plan for 1 m b*
J. Uythoven & J. Wenninger
With input from rMPP, W. Herr, R. Bruce, M. Giovannozzi, S. Redaelli

## Slide 2: Startup with beam
This evening between 19-20 if all goes well.
In the SPS a quadrupole was exchanged (H foc.). There is a slight orbit perturbation (too small for the surveyors to correct, < 0.1 mm) that we will have to steer back some time over the WE.

## Slide 3: Aperture @ 1 m
Simple scaling – just to check if it even makes sense…
  Just about right for 18s, s = nom. Emittance.
Aperture @ 1.5 m (sigma) | 18 | 20
Beam size ratio 1.5/1 m | 0.80 | 0.80
Raw scaling to 1 m by beam size (sigma) | 14.4 | 16
Xing angle change (mm) for 120 urad* | 0.25 | 0.25
Aperture @ 1 m, 120 urad (sigma) | 14.2 | 15.8
* @ the BPMs
Peak s @ triplet = 1.42 mm (3.5 mm emit)

## Slide 4: Beam-beam separation
Beam-beam separation down below 6s for 100 mrad
  With 120 mrad ~ equivalent to nominal (b* 0.55 m)
W. Herr
Triplet
Triplet

## Slide 5: The commissioning blocks
Configuration:
  b* 1m, 120 mrad Xing angles.
  IR6+7 collimators at standard settings, TCTs 11.8s (IR1+5+8)
Block A: aperture at 1m and 120 mrad
  This block may change depending on the results !
Block B: ALICE polarity reversal
Block C: Validation
Block D: Intensity ramp up

## Slide 6: Block A : aperture check
Fill 1: 1 probe/beam, checkout cycle.
  b* 1 m and Xing angle 120 mrad.
  Standard collimator settings IR6+7.
  TCTs IR1/5 to be adapted to 120 mrad (setup on 100 mrad).
Fill 2: 2 nominals/beam, TCT alignment, orbit.
  TCTs IR1/5 alignment on 120 mrad, separated and in collision.
  Collision (re-)optimization with 120 mrad, reference orbit.
  End with loss map (H+V) and asynch dump. TCTs are 11.8s.
Fill 3: 1 probe/beam, aperture check @ 1 m.
  Repeat aperture measurement at 1 m.
  End with a loss map H, TCTs at 14s.
Fill 4: 1 probe/beam, aperture check with loss map.
  Loss map with TCTs at Xs, X = 13…14.
4h
6h
8h
5h

## Slide 7: Block A: long range BB check
Fill 5: 84b with highly asymmetric BB filling pattern (also used for 1 m with 100 mrad).
  Bring the beam up to collisions.
  Verify stability and beam-beam effects.
6h

## Slide 8: Block B : ALICE polarity
Step 1: adjust injection, reference.
  ALICE on ‘old’ polarity.
  Injection steering with 12b, then copy to probe and check it.
Step 2: revert ALICE polarity.
  Check/correct orbit.
  Check/steer injection oscillations with probe, repeat with nominal.
Step 2’: re-steer TI2 if necessary.
  TDI coarse
  TL setup, TCDI alignment and verification.
Step 3: TDI/TCLI alignment.
  TDI/TCLI alignment with 1 nominal b.
  Check TDI,TCLI setup.
  Check injection 12b.
2h
4h
12h
8h
If required, ‘alternate’ with TCT alignment (steps 4-6)

## Slide 9: Block B : ALICE polarity continued
Step 4: TCTs IR2 at injection.
  Setup TCTs in IR2 at injection.
Step 5: Checkout cycle, 2 probes/beam.
  Check Xing angle IR2 along the cycle.
  Correct orbit if necessary.
  TCTs IR2 ‘open’.
Step 6: TCT IR2 alignment cycle, 2 nominal b/beam.
  TCT alignment on flat top and in collision.
  Collision orbit, reference.
  Loss map H+V and asynch. dump.
(Step 7: TCT IR2 functions, positions and interlocks )
2h
4h
6h

## Slide 10: Block C
Validations (loss maps, asynch dump checks) – to be confirmed with collimation team (Dp/p)
Condition | Betatron H | Betatron V | Dp/p + | Dp/p - | Dump
Injection | X | X | X | X | X
Flat top | X | X | X | X | X
Squeezed | X | X | X | X | X
Collisions | X | X | X | X | X

## Slide 11: Block D: Intensity ramp up
Proposed ramp up for stable beams:
  48b – short fill
  264 – short fill
  480 – short fill
  912 – long fill
  1380 – finally !!