## Slide 1: Week 36 plan
Todo’s:
  12+b injection.
  Special fill 84b for LR BB.
  Loss maps ‘a gogo’.
  Intensity ramp up.
And also:
  Define ALFA and TOTEM RP settings, prepare them in LSA.

## Slide 2: Part1: work with 50 ns
Injection of 50 ns.
  Injection of 12b, steering if needed.
  Injection of 36,72,144 to checkout injection.
Special fill for LR beam-beam.
  12 + 2x36 bunches, Scheme 50ns_84b_36_36_36_BBMD3.
  Ramp, squeeze, collide: stability, lifetime.
  In collisions for ~1 hour.
Done
Done – to be checked

## Slide 3: Part 2: validation / loss maps
Loss maps injection.
  Betatron H + V, off-momentum +/-, asynch dump.
  Fresh beams for each test.
  Swap H and V tunes for H loss map.
Loss maps at flat top (unsqueezed) – 1 fill.
  Betatron H + V, asynch dump.
Loss maps end of squeeze to 1m (separated !) – 1 fill.
  Betatron H + V, asynch dump.
Loss maps with collisions – 1 fill.
  ALFA and TOTEM RPs in beam.
  Betatron H + V, asynch dump.
Loss maps with collisions – 1 fill.
  ALFA and TOTEM RPs in beam –1-2 hours (data taking test)
  Off-momentum test dp/p + (RF frequency trim -500 Hz).
Almost done
½ Done
Done

## Slide 4: Part 3: intensity ramp up
Ramp up for stable beams:
  264 – few hours
  480 – short fill
  912 – long fill
  1380 – finally !!

## Slide 5: Monday
10:30 Fill for loss map with TCTs @ 14 sigma (end of squeeze, separated) lost just before starting the loss maps.
  Sector 56 tripped – network communication was cut by accident during an intervention…
Retry…
14:30 Loss map and asynch. dump test with TCTs @ 14 sigma (end of squeeze, separated).
  Good results – confirm that triplet in shadow with 14 sigma.

## Slide 6: Validations with TCTs at 14 sigma
Asynch. dump test OK (C. Bracco).
Collimation - preliminary analysis (D. Wollmann):
  All loss maps look ok:
    Leakage into the TCTs below 1e-3.
    Leakage into cold magnets in IR1/IR5 ~ 1 order of magnitude below the corresponding TCT.
    No un-expected losses into cold magnets.
    Couldn't reproduce the leakage into the Q10R1 (as reported Saturday night).
    Highest leakage into cold magnets found in Q8 of IR7: - B1-H: ~3.5e-4 - B1-V: ~2.5e-4 - B2-H: ~5e-4 - B2-V: ~2.5e-4

## Slide 7
B1 H

## Slide 8
B1 V

## Slide 9
B2 H

## Slide 10
B2 V

## Slide 11
Asynch dump, TCTs @ 14 sigma.
  No losses visible in triplets.

## Slide 12: Monday continued
16:00 Injection setup.
  Verification of the magnet synchronization of B1 (E. Carlier)
    Kick delay - MAIN-D : no change (reference magnet for synchronisation) - MAIN-C : -75ns (old delay: 1100ns - new delay: 1025ns) - MAIN-B : +10ns (old delay: 1140ns - new delay: 1150ns) - MAIN-A : no change
    Kick length - DUMP-D : no change - DUMP-C : +95ns (old delay: 1000ns - new delay: 1095ns) - DUMP-B : +50ns (old delay: 1090ns - new delay: 1140ns) - DUMP-A : +100ns (old delay: 1000ns - new delay: 1100ns)
17:00 Injection check 12b.
  OK – no problems.

## Slide 13: Monday continued
18:15 Lost the cryogenics conditions for MSL2 and ITL2.
  Worldfip communication problem.
18:50 Vacuum valves in LSS2.
  Gauge switched off.
21:00 Back to injection.
  Injection of up to 144b – worked but not at its best.
  Losses from circulating beam (tbc), and some injection oscillations.
00:00 Loss maps at injection.
  Injection protection out.
  H and V were not done with separate beams  repeat.

## Slide 14
Off-momentum loss map at injection.
  HV problem? Re-cabled BLM?

## Slide 15: Night
00:20 Loss maps at flat top.
  Betatron H + V.
  B1 lost before asynch. dump test by spurious SIS interlock.
  Asynch. dump to be repeated.
Lot’s of CMW errors… including SIS interlock.
05:30 Loss maps at end of squeeze.
  Betatron H+V ansd asynch dump test.

## Slide 16
Validation matrix
  Injection to be done also with injection protection (betatron)
Condition | Betatron H | Betatron V | Dp/p + | Dp/p - | Dump
Injection | DONE | REPEAT | DONE | DONE | DONE
Flat top | DONE | DONE | --- | --- | REPEAT
Squeezed | DONE | DONE | --- | --- | DONE
Collisions | OK | X | X | OK | X

## Slide 17: Today
Finishing injection loss maps now.
Long range BB test with 84b.
Injection checkout to 144b.
Continue loss maps / repeat if not good.
  IR3 R-side BLMs.
  Collision maps with RPs.

## Slide 18: Accelerator Mode
Name in the database & over DIP 
PROTON-NUCLEUS PHYSICS
Name in the timing telegram = AMODE 
Line = PAPHYS, value=16
Particle Type
New groups! With name in the timing telegram 
PARTY1 (= particle type for B1)
PARTY2 (= particle type for B2)
PARTY1(2) is group number=23(24)
Lines 
      Proton (Proton), value=1
      Pb82 (Lead 82+), value=2
      Ar18 (Argon 18+), value=3
      D (Deuteron), value=4
      Xe54 (Xenon 54+), value=5
The bold names are used in the database
(what you see over DIP)
Over DIP you see them under RunControl/RunConfiguration:
PARTICLE_TYPE_B1 & PARTICLE_TYPE_B2

## Slide 19: The following telegram groups have been suppressed
23 | C1BNCH | Circulating number of bunches - Ring 1
24 | C1BSP | Circulating bunch spacing - Ring 1
25 | C1BIN | Circulating bunch intensity - Ring 1
26 | CPTY | Circulating particle type - Ring 1 and 2
27 | C2BNCH | Circulating number of bunches - Ring 2
28 | C2BSP | Circulating bunch spacing - Ring 2
29 | C2BIN | Circulating bunch intensity - Ring 2