## Slide 1: Week 25 Summary
Coordinators: Mike Lamont and Barbara Holzer
MD Coordination: Ralph Assmann, Giulia Papotti, Frank Zimmermann

## Slide 2: Program of Week 25
 | Scheduled | Actual | 
Monday 18.6. | till 13:00 | till 13:00 | Luminosity production
 | 13:00 – 18:00 | 13:00 – 18:00 | Access followed by test of TETRA impact on beam
 | 18:00 | 20:00 | 90 m beta* un-squeeze validation
Tuesday 19.6. | 6:00 | 12:30 | Start MD Block #2
Monday 25.6. | 6:00 |  | Start Technical Stop

## Slide 3: Closed books for ICHEP on Monday 18 June 13:00
Atlas: 6.6/6.3 fb-1 delivered/recorded
CMS: 6.8/6.3 fb-1 delivered/recorded
LHCb: 0.65/0.62 fb-1 delivered/recorded
Alice: a little over 1 pb-1

## Slide 4: Faults, Accesses and Recovery Time
Excellent availability: ~ 14% of time spent in fault, access or recovery (e.g. pre-cycle)
Monday 5:00 hours – 2 separate accesses:
  LBDS Check/repair Ethernet connection on FEC cfc-ua63-mkdtspm
  Collimator cooling check TCT IR8
  BI BBQ: UA43 – remote communication with a controls front-end
  BI Head-Tail monitor: Q7R4 - install attenuators
  ATLAS
  2nd access: RF module M2B2 broken crowbar (diagnosis), UX45
Tuesday total of 9:15 hours
  No beam Tuesday morning 8:15 hours:
      4:15 – 9:00 fault of 400 V distributor:
        S12+S23 triped, vacuum valves closed
        access for TI services and vacuum valve controls
      11:35 finished the repair of crowbar RF module 2 beam 2
      10:30 – 12:30 no beam from PS: 10 MHz cavity intervention
    Tuesday night 1 hour: BLM SEM not recognized by sanity check

## Slide 5: Faults, Accesses and Recovery Time cont.
Wednesday afternoon 1 hour
  PS septum
Thursday 3:30 hours (1:30 + 0:30+1:30)
  access:
    AC Dipole repair
    Diamond BLMs: change dynamic range for UFO MD
    Install temperature probes for Head-Tail monitor
  RF L8B2 fast abort, and PS
  ventilation door opened in UL26
Friday 1 hour: access system, communication lost between LASS and TIM. SIS didn't get information on the door status and the powering interlock was sent to all sectors.
Saturday 1:30 hour: RQTL11L2.b2 went faulty during re-cycling
Sunday 2 hours
  Oracle DB (LSA, Inca, …): a node in the DB cluster partially crashed, and connections were not automatically transferred to the other nodes in the cluster.
  RF line 8B2