## Slide 1: Friday
11:24 electrical cut at Pt 2 (before the re-start of the compensator) caused loss of cryogenics at point 2 including cold compressor
12:00 Compensator in point 2 restarted
14:00 MKI 8 ready for operation.
16:00 trip of cryogenics in point 8: 24 V power supply causing an emergency stop of the cryogenics
17:00 SIG informed that the intervention on the electrical network is postponed to next week
18:20 Machine patrolled. Pressures in the BSRTs in the 10-9 – 10-8 mbar range. RF available.
18:00 – 20:30 Beams to last TED for Q20 optics extraction verification  successful
20:20 LHC closed after intervention on 60 A power converter
23:00 Problems with heaters controls of the cryogenics cold box in point 8.

## Slide 2: Tentative Plans (Saturday)
  Cryogenics in Point 2 almost recovered
  Cryogenics in point 8. Connection of the cold compressor ongoing. Better estimate possible only after connection is completed.
  In the best case cryo OK in the night.
  ALICE in access.
Powering tests (RB.A78/RB/A81) (3 hours)
Pre-cycle (1 hour)
  Go through the whole cycle (with new collision process) with pilot beam for validation and chromaticity measurement (BBQ and BSRT verification in parallel). (5 hours)
  Switch off Active filters of main circuits and warm dipoles one by one for mains line perturbation observations.

## Slide 3: Plans
Setting-up of injection with Q20 optics (5 hours)
Loss maps in collision (betatron and +500 Hz) (5 hours).
  Wire scans for BSRT calibration
Loss maps squeezed/separated: betatron and asynch.dump in collision. (5 hours)
  Wire scans for BSRT calibration
First step of the intensity ramp-up: very short fill with 78 bunches with new collision process (5 hours)
Damper setting-up with larger bandwidth (5 hours)

## Slide 4: Plans
Intensity ramp-up:
  456 bunches (50ns_456b_447_0_432_72bpi12inj)
    CMS request for period at low pile-up (~1) – 2 h
    ATLAS request for VdM scan – 2 h
  840 bunches with additional train of 6 bunches (no collision and no long-range). Standard fill length.
  1374 bunches

## Slide 5
To be followed-up:
  Kicker (Pt.8) vacuum
  BSRT temperatures
Abort gap calibration will be done during one of the ramp with nominal bunches