## Slide 1: Wednesday 16.1.2013
4:14 lost cryo conditions in Sector 34/45 due to communication problem
  6:30 Faulty IT network switch identified  access needed
  BIW siren problem being investigated in parallel
  9:30 access for cryo network switch replacement
  11:30 a second network switch needs replacement  access
  12:30 Cryo communication problem in point 4 fixed
13:17 Trip of the cold compressor in point 4 (related to previous exchange of network switches)
16:38 problem with BIW (Beam Imminent Warning) sirens has been solved. There was a broken fuse on a 48V power supply for the access interface card in Point 5.
Afternoon / Evening: Ongoing problems reconnecting the cryo in point 4
6:00 cryo back – start pre-cycle. Fault duration 25h45’

## Slide 2: Planning
p,p beams:
  Loss maps at flat-top and LSS7 collimator alignment checks – go through the squeeze in single step, on momentum (4-5 hours)
  IR2 aperture measurement (4 hours)
Switch to p,Pb:
  Ramp, cogging, frequency lock (13 bunches) + TCT alignment and loss maps end of squeeze and collision. Try to find collisions. Roman pot alignment (TOTEM and ALFA vertical) (>1 shift).
  If problems to find collision inject p,p nominal bunches and find collisions (4-6 hours). Set-up TCT and RP with p,Pb.
To be scheduled:
Loss maps and asynchronous dump tests at top energy and at injection (2 shifts)
Possibly: Injection of trains of 24 bunches (protons and ions) (2 hours)
Possibly: beta-beating through off momentum squeeze (4 hours)
Notes: Cryogenics available at 6:00
Precycle completed by 7:00
Flat-top and start of loss maps at 8:00
Loss maps and collimator alignment completed by 12:00
Squeeze in one go finished by 13:00
Aperture checks in IR2 from 13:00 to17:00
pPb injection, ramp, cogging, starting at 18:00 – 19:00. TCT alignment and loss maps (betatronic) at the end of the squeeze and in collision (TOTEM and ALFA presence required at the end for ALFA and TOTEM vertical roman pot alignment.
If problem to find collisions with proton and ions dump and refill with 3 “nominal” (8x10^10) proton bunches to find collisions

## Slide 3: Loss maps for Collimation validation
 | Injection (Inj. Prot. IN) | Injection (Inj. Prot. OUT) | Flat-top | Squeezed, separated | Squeezed Collision
Betatronic-H | tbd | tbd | tbd | tbd | tbd
Betatronic-V | tbd | tbd | tbd | tbd | tbd
Neg. off-mom | tbd | tbd | -- | tbd | tbd (+500 Hz)
Pos. off-mom | tbd | tbd | -- | -- | tbd (-500 Hz)
Asynch dump | tbd | -- | -- | tbd | tbd
tbd=to be done