## Slide 1: LHC status & 2009/2010 operations
Mike Lamont
for the extended LHC team

## Slide 2: Contents
Consolidation – brief recall
Splices
Operational energies
Potential performance
Present status
Plans for 2009-2010

## Slide 3: Consolidation 1/2
Besides the major effort required to repair sector 34…
Major upgrade of the quench protection system
  Protection of all main quadrupole and dipole joints (0.3 mV threshold).
  High statistics measurement accuracy to < 1 nΩ.
  Installation of > 200 km of cables, production of thousands of electronic boards. >> protection against similar issues in the future.
Massive measurement campaign to identify bad splices
  Calorimetric methods (~ 40 nΩ) to identify possible bad cells
  High precision voltage meas. (~ 1 nΩ) to identify problematic splices
Improved active protection
Diagnostics

## Slide 4: Consolidation 2/2
Mitigation of collateral effects in case of problems:
Additional release valves (“DN200”)
  Improvement of the pressure relief system to eventually cope with maximum He flow of 40 kg/s in the arcs (maximum conceivable flow)
  Installation completed in 4 sectors (1-2, 3-4, 5-6, 6-7)
  Also done for Inner triplets, Standalone Magnets and DFBs:
Reinforcement of the quadrupole supports
  Arc quadrupoles (total 104 with vacuum barrier)
  Semi-stand alone magnets
  Inner triplet and DFBAs
Energy extraction times lowered
  Faster discharge of the energy from circuits
  Possible because of lower energy running
Mitigation of damage

## Slide 5: Additional splice problem
The enhanced quality assurance introduced during sector 3-4 repair has revealed new facts concerning the copper bus bar in which the superconductor is embedded.
The process of soldering the superconductor in the interconnecting high-current splices can cause discontinuity of the copper part of the bus-bars and voids which prevent contact between the super-conducting cable and the copper.
Danger occurs only in case of a quench

## Slide 6: Stablizer problem
Bad electrical contact between wedge and U-profile with the bus on at least 1 side of the joint
Bad contact at joint with the U-profile and the wedge

## Slide 7: Splices - summary
Bad splices
  Resolution: calorimetry → 40 nΩ; electric → 1 nΩ
  Two bad cases found in 6 sectors: 50 nΩ (1-2) and 100 nΩ (6-7); repaired.
  Two sectors still to be measured cold (4-5, 3-4)
Copper stabilizer problem
  Measurements done in 6 sectors, missing 7-8 and 8-1
  10 dipole (> 35 µΩ) and 10 quadrupole (> 80 µΩ) joints repaired
  Lot of effort has gone into modeling the problem…

## Slide 10: Initial operating energy of the LHC
Operating at 3.5 TeV with a dipole energy extraction time of 50 s.
  Simulations show that resistances of 120 micro-ohm are safe from thermal runaway under conservative assumed conditions of worst case conditions for the copper quality (RRR) and no cooling to the copper stabilizer from the gaseous helium
Decision:
  Operation initially at 3.5 TeV (energy extraction time of 50 s) with a safety factor or more than 2 for the worst stabilizers.
Then operate at 4 – 5 TeV

## Slide 11: Higher than 3.5 TeV?
Operating at 5 TeV com with a dipole energy extraction time of 68s
  Simulations show that resistances of 67 µΩ are safe from thermal runaway under conservative assumed conditions of worst case conditions for the copper quality (RRR), and with estimated cooling to the stabilizer from the gaseous helium
  Warm local measurements of the joint resistances in sector 45 (so-called local R16 measurement) revealed record surplus joint resistance of about 60 µΩ, caused by double joint fault on both sides of the SC splice
  Conservative estimates based on statistical analysis and the worse joints estimate a conservative maximum of ~ 90 µΩ
We have 2 sectors which have not been measured warm.
The essential question is “what is the maximum resistance we can “reasonably” expect in the unmeasured sectors?”

## Slide 12: Higher than 3.5 TeV?
FRESCA
  Validation of splice model in the lab
  Testing fully instrumented bad splice in 1.9 K Helium
Full re-analysis of previous measurements
  Analysis of warm non-invasive dipole measurements
  Statistical analysis of invasive warm “R16” measurements
  Analysis of failure modes and of worse joints found in the six sectors measured
Monitor carefully all quenches to gain additional information.
  Behaviour (nQPS) – propagation times, current levels…
  Likelihood with beam, confirmation of simulations
Experiments’ interest in increasing the energy is noted.
The jury is definitely out on this one - but we have some time.

## Slide 13: 3.5 TeV running - recall
Emittance goes down with increasing :
And so beam size:
And thus luminosity increases with increasing  IF we can hold other parameters constant:
However, because beam size goes as:
  Lower energy:
     increased beam size – less aperture  higher *
     separation of beams in interaction regions drops – long range beam-beam

## Slide 14: 3.5 TeV limits
Parameter | Limit | Reason(s)
Beam Intensity | ~6 e13 | collimation cleaning efficiency
* - crossing angle off | 1 m | aperture
* - with crossing angle | 2 – 3 m | aperture, long range beam-beam
Crossing angle [50 ns] | ~300 µrad | *, aperture, long range beam-beam
Peak luminosity | ~1 e32 | 
Ralph Assmann
Werner Herr
6 e13

## Slide 15: Operation - assumptions
Fill length: 8 hours
Turnaround time: 5 hours
20 hours luminosity lifetime
30 day months.
40% machine availability
Nominal crossing angle assumed for 50 ns.
Nominal transverse emittance
Total intensity limited to around 12% of nominal
No squeeze beyond 2 m. with 156 bunches, crossing angle off - conservative
Given these constraints what can we do?

## Slide 16: Plugging in the numbers – 3.5 TeV
Month | OP scenario | Max number bunch | Protons per bunch | Min beta* | Peak Lumi | Integrated | % nominal | events/X
1 | Beam commissioning |  |  |  |  |  |  | 
2 | Pilot physics combined with commissioning | 43 | 3 x 1010 | 4 | 8.6 x 1029 | ~200 nb-1 |  | 
3 |  | 43 | 5 x 1010 | 4 | 2.4 x 1030 | ~1 pb-1 |  | 
4 |  | 156 | 5 x 1010 | 2 | 1.7 x 1031 | ~9 pb-1 | 2.5 | 
5a | No crossing angle | 156 | 7 x 1010 | 2 | 3.4 x 1031 | ~18 pb-1 | 3.4 | 
5b | No crossing angle – pushing bunch intensity | 156 | 1 x 1011 | 2 | 6.9 x 1031 | ~36 pb-1 | 4.8 | 1.6
6 | partial 50 ns – nominal crossing angle | 144 | 7 x 1010 | 2-3 | 3.1 x 1031 | ~16 pb-1 | 3.1 | 0.8
7 |  | 288 | 7 x 1010 | 2-3 | 8.6 x 1031 | ~32 pb-1 | 6.2 | 
8 |  | 432 | 7 x 1010 | 2-3 | 9.2 x 1031 | ~48 pb-1 | 9.4 | 
9 |  | 432 | 9 x 1010 | 2-3 | 1.5 x 1032 | ~80 pb-1 | 12 | 
10 |  | 432 | 9 x 1010 | 2-3 | 1.5 x 1032 | ~80 pb-1 | 12 | 
11 |  | 432 | 9 x 1010 | 2-3 | 1.5 x 1032 | ~80 pb-1 | 12 | 

## Slide 17: Possible evolution
Ramp, squeeze at 4-5 TeV beta* = 2 m crossing angle, 50 ns
Ramp, squeeze, ramp to 4-5 TeV beta* = 2 m no crossing angle, 156 bunches
Step up in energy
Physics at 3.5 TeV beta* = 2 m no crossing angle, 156 bunches

## Slide 18: Step up in energy
Task | Comment | Time
Hardware commissioning of main circuits | Modification and testing of dump resistors Installation of snubbing circuits Calorimetry and QPS measurements | ~ 2 weeks
Qualification of machine protection without beam | FMCMs, PIC, Collimators, TCDQ, BLMs, BPM interlocks, SMPs, RF, LBDS | In parallel with HWC
Operation dry runs of re-qualified sectors |  | After hand over from HWC
Re-commissioning of ramp and associated machine protection | Safe beam: LBDS, BLMs, RF | ~ 1 week
Re-commissioning of squeeze | Could possibly ramp-squeeze-ramp (avoiding the need to re-com the 3.5 TeV squeeze) | 
Optics and operations’ checks at high energy |  | ~ 2 days
Collimator re-optimization |  | ~4 days
Estimate: 4 weeks to re-establish physics

## Slide 19: Plugging in the numbers with a step in energy
Month | OP scenario | Max number bunch | Protons per bunch | Min beta* | Peak Lumi |  | Integrated |  | % nominal
1 | Beam commissioning |  |  |  |  |  |  |  | 
2 | Pilot physics combined with commissioning | 43 | 3 x 1010 | 4 | 8.6 x 1029 |  | ~200 nb-1 |  | 
3 |  | 43 | 5 x 1010 | 4 | 2.4 x 1030 |  | ~1 pb-1 |  | 
4 |  | 156 | 5 x 1010 | 2 | 1.7 x 1031 |  | ~9 pb-1 |  | 2.5
5a | No crossing angle | 156 | 7 x 1010 | 2 | 3.4 x 1031 |  | ~18 pb-1 |  | 3.4
5b | No crossing angle – pushing bunch intensity | 156 | 1 x 1011 | 2 | 6.9 x 1031 |  | ~36 pb-1 |  | 4.8
6 | Shift to higher energy: approx 4 weeks | Would aim for physics without crossing angle in the first instance with a gentle ramp back up in intensity |  |  |  |  |  |  | 
7 | 4 – 5 TeV (5 TeV luminosity numbers quoted) | 156 | 7 x 1010 | 2 |  | 4.9 x 1031 |  | ~26 pb-1 | 3.4
8 | 50 ns – nominal Xing angle | 144 | 7 x 1010 | 2 |  | 4.4 x 1031 |  | ~23 pb-1 | 3.1
9 | 50 ns | 288 | 7 x 1010 | 2 |  | 8.8 x 1031 |  | ~46 pb-1 | 6.2
10 | 50 ns | 432 | 7 x 1010 | 2 |  | 1.3 x 1032 |  | ~69 pb-1 | 9.4
11 | 50 ns | 432 | 9 x 1010 | 2 |  | 2.1 x 1032 |  | ~110 pb-1 | 12

## Slide 20: Caveats
Big error bars on these numbers
Bunch intensity/ Beam intensity
  quench limit, beam lifetimes, parameter tolerances & control, emittance conservation through the cycle…
Cleaning efficiency of collimation versus quench limits
  Note: we have already proved that we can quench a dipole with only ~2-3 e9 at 450 GeV
Operability:
  reproducibility, ramp, squeeze, beam lifetime, background, critical feedback systems
Machine availability:
  just about everything… include the injectors
Machine Protection
  has to work perfectly

## Slide 21: LHC status - today
Sector | Status | Temp | 
12 | PO PHASE 1 | 1.9 K | Phase 2 powering starts this week, following installation of new QPS.
23 | COOLDOWN | ~4 K | 
34 | COOLDOWN | ~175 K | 
45 | COOLDOWN | ~13 K | 
56 | COOLDOWN | ~2 K | 1 w delay due to cryo-preparation;
67 | COOLDOWN | ~250 K | Cool-down of 6-7 started few days earlier than foreseen
78 | COOLDOWN | 1.9 K | 1 w delay due to cryo-preparation;
81 | COOLDOWN | ~75 K | 
A lot still going on out there: ELQA, access doors, QPS…

## Slide 22
General Schedule 24th, August 09
no shifts
2 shifts, 5 days
2 shifts, 7 days
2 shifts, 7 days
3 shifts, starting from Friday 18/9

## Slide 23: Hardware commissioning - NB
HWC phase 1
  Limited current – no powering of main circuits – restricted access
HWC phase 2
  Individual system tests of new QPS
  Power main circuits to 6000 A (just over 3.5 TeV)
  No access during powering in sector concerned and adjacent access zones
New Quench Protection System still to be installed and tested just about everywhere
  First 54 crates finished testing last Saturday

## Slide 24: 2009 - injectors
± first LHC beam
Injection test Sector 23 as first priority Sector 78 if part of 81 required is ready
Ions in the lines

## Slide 25: Beam commissioning
Global machine checkout
Essential 450 GeV commissioning
System/beam commissioning
Machine protection commissioning 2
3.5 TeV beam & first collisions
450 GeV collisions
Ramp commissioning to 1 TeV
Full machine protection qualification
Pilot physics
System/beam commissioning
Machine protection commissioning 1
Energy | Safe | Very Safe
450 | 1 e12 | 1 e11
1 TeV | 2.5 e11 | 2.5 e10
3.5 TeV | 2.4 e10 | probe
One month to first collisions

## Slide 26: 450 GeV collisions
Time limited: 3-4 shifts
No squeeze
Low intensity – machine protection commissioning unlikely to be very advanced.
~1 week after first beam
Number of bunches | 1 | 4 | 12
Particles per bunch | 4 | 4 | 4
Beam intensity | 4 x 1010 | 1.6 x 1011 | 4.8 x 1011
beta* [m] | 11 | 11 | 11
Luminosity [cm-2s-1] | 1.7 x 1027 | 6.6 x 1027 | 2 x 1028
Integrated lumi/24 hours [nb-1] | 0.06 | 0.24 | 0.7

## Slide 27: LHC 2009
All dates approximate…
Reasonable machine availability assumed
Stop LHC with beam ~19th December 2009, restart ~ 4th January 2010

## Slide 28: LHC 2010 – very draft
2009:
  1 month commissioning
2010:
  1 month pilot & commissioning
  3 month 3.5 TeV
  1 month step-up
  5 month 4 - 5 TeV
  1 month ions

## Slide 29: Conclusions
Splices remain an issue
Constraints of 3.5 TeV enumerated
Potential performance shown
  200 – 300 pb-1 seem reasonable
Step up in energy would take ~4 weeks – increase to be decided
Would start with a flat machine at the higher energy… before bringing on crossing angle and exploiting 50 ns.
LHC well into cool-down and on schedule for mid-November start with beam
With a bit of luck, first high energy collisions before Christmas