## schedule
Goals:
1 - complete the longitudinal emittance blow up commissioning
2 - continue the transverse damper commissioning
3- robust ramp for 1e10
4- commission the squeeze with separated beams , squeeze to 3.5 m
5- OFB, BPM, reference orbit
6- Collimator setting-up
| Day | Start | Time (h) | Activity
7 | Mon | M | 8 | Inject, ramp, squeeze and collide at 3.5 TeV, 2m, 13b of 2e10
7 | Mon | A | 8 | Controlled longitudinal emittance at 450 GeV
7 | Mon | N | 8 | ABT Injection studies
8 | Tues | M | 8 | BI high intensity tests, 1 to few bunches, pilot to nominal intensity
8 | Tues | A | 8 | Hump investigation
8 | Tues | N | 8 | ADT commissioning
9 | Wed | M | 8 | Controlled longitudinal emittance- on ramp
9 | Wed | A | 8 | Ramp optimisation, 2e10 (tune, chrom, OFB on…)
9 | Wed | N | 8 | Ramp optimisation, 7e10, 1e11 (tune, chrom…)
10 | Thur | M | 8 | Controlled longitudinal emittance blow up in ramp- 1e11
10 | Thur | A | 8 | Transverse feedback system commissioning
10 | Thur | N | 8 | Squeeze commissioning, 1e10
11 | Fri | M | 8 | Collimator setting up at 3.5 TeV, with separation on, 1e11/beam
11 | Fri | A | 8 | Controlled longitudinal emittance- on ramp - 1e11
11 | Fri | N | 8 | Transverse feedback system commissioning
12 | Sat | M | 8 | Collimator setting up at 3.5 TeV, with separation on, 1e11/beam
12 | Sat | A | 8 | Squeeze commissioning, with separated beams, 1e10
12 | Sat | N | 8 | Transverse feedback system commissioning
13 | Sun | M | 8 | Collimator setting up at 3.5 TeV, with separation on, 1e11/beam
13 | Sun | A | 8 | Squeeze commissioning, with separated beams, 1e10
13 | Sun | N | 8 | Collimator qualification at 3.5 TeV, with separation on, 1e11/beam
14 | Mon | M | 8 | Injection system qualification
14 | Mon | A | 8 | Collimator setting up at 3.5 TeV, squeezed, with separation off, 1e11/beam
14 | Mon | N | 8 | Collimator qualification at 3.5 TeV, squeezed, with separation off, 1e11/beam
15 | Tues | M | 8 | Transverse feedback system commissioning
15 | Tues | A | 8 | Beam dumping system qualification
15 | Tues | N | 8 | Collimator qualification at 3.5 TeV, squeezed, with separation off, 1e11/beam
16 | Wed | M | 8 | Transverse feedback system commissioning
16 | Wed | A | 8 | Controlled longitudinal emittance blow up in ramp- 1e11
16 | Wed | N | 8 | Collimator qualification at 3.5 TeV, squeezed, with separation off, 1e11/beam
17 | Thur | M | 8 | Transverse feedback system commissioning
17 | Thur | A | 8 | Beam dumping system qualification
17 | Thur | N | 8 | Ramp-squeeze operational qualification
18 | Fri | M | 8 | Transverse feedback system commissioning
18 | Fri | A | 8 | Test run for high intensity fills with collisions- NO STABLE BEAMS
18 | Fri | N | 8 | Test run for high intensity fills with collisions- NO STABLE BEAMS
19 | Sat | M | 8 | Test run for high intensity fills with collisions- NO STABLE BEAMS
19 | Sat | A | 8 | Test run for high intensity fills with collisions- NO STABLE BEAMS
19 | Sat | N | 8 | Test run for high intensity fills with collisions- NO STABLE BEAMS
20 | Sun | M | 8 | Test run for high intensity fills with collisions- NO STABLE BEAMS
20 | Sun | A | 8 | Test run for high intensity fills with collisions- NO STABLE BEAMS
20 | Sun | N | 8 | Test run for high intensity fills with collisions- NO STABLE BEAMS
21 | Mon | M | 8
21 | Mon | A | 8
21 | Mon | N | 8
22 | Tues | M | 8
22 | Tues | A | 8
22 | Tues | N | 8
23 | Wed | M | 8
23 | Wed | A | 8
23 | Wed | N | 8
24 | Thur | M | 8
24 | Thur | A | 8
24 | Thur | N | 8
25 | Fri | M | 8
25 | Fri | A | 8
25 | Fri | N | 8
26 | Sat | M | 8
26 | Sat | A | 8
26 | Sat | N | 8
27 | Sun | M | 8
27 | Sun | A | 8
27 | Sun | N | 8