## Slide 1: Friday 23 October
All TS work done as scheduled. THANKS Katy Foraz for the excellent coordination
18:30: Machine closed
Summary MP3: Nuria Catalan Lasheras and team Re-commissioning of the IPQs -Individually Powered Quad- in R5 and L1 after technical stop and HV tests ready by 22:00. - PIC2 –Power Interlock Controller- test to verify QPS-Interlock connections - PNO.a7 splice tests to verify the water cooled cable connection to the leads. IPQ bus-bar resistance measurements done in RQ7, RQ8, RQ9 and RQ10 in points R5 and L1
Sectors being cycled one by one as soon as cryo cdts O.K.

## Slide 2: Friday 23 October
Controls problem:
  interlocked BPM reset and arm BIC commands were not accepted by the new proxies, quickly solved by Wojtek
  SMP energy lim MCS checks failed, solved by re-driving the settings
  one BLM failed the sanity check, monitor need to be changed but cannot be done this evening; so the monitor on Q17.R5 has been disabled from the PIC.
  CMW command to open/close vacuum valves did not work, neither from the PVSS application, we had to use the global command from application.

## Slide 3: Saturday 23 October
02:20 : Cryo condition ready for the last sector S23
Cycle S23 – preparing injection
04:30 : Pilots injected – moving to 4b/injection – done for B1
06:55 : Lost sector 23 due to a trip of RQ9.R2B2: U_RES beyond the threshold (+/- 100 mV) for ~ 8 ms - quench heaters fired correctly. Not a real quench but probably some pick-up / electrical disturbance. To note: similar event in same magnet occurred on 27/7/2010, also showing a few points above 100 mV, and also with unknown origin
08:30: Cycling S23

## Slide 4: Next days
AM: Injection – 8hrs
PM: Test ramp 1bx1b - squeeze – collide - for checks only– 3h
Late PM : Test ramp 4x4, squeeze – 4 hrs collisions tbc – 3h to 7h
Overnight: Fill for Physics 312 bunches
Sunday - Fill for Physics 360 bunches