## Slide 1: Status 01/04
Pending issues from the technical stop:
  Cryo recovery in Sector 45:
    Cryo RF OK at 09:00 + RF conditioning + Access in UX45
    Sector 45 OK by midday  pre-cycle
  LBDS: issues with generator MKB.B2. Seems now OK. Access this morning in UA. LBDS should be OK by mid-morning
  SPS: after installation of scraper vacuum recovering and possibility to pulse kickers in the area by midday.
Over night test of the circuits where power converters have been replaced, pre-cycle etc.
This morning will continue with the tests
Hoping for beam at the beginning of the afternoon (low intensity)

## Slide 2: Preliminary plan
Fri | AM | RF conditioning + pre-cycle and circuit tests in Sector 45
Fri | 12:00 | Beam presence flag at injection
 |  | Test dump with pilot at 450 GeV after change of MKD generators
Fri | 14:00 | Aperture check at injection+effect of shielding at the end of TI8
Fri | 20:00 | Abort gap cleaning - verification of the excitation window: nominal bunches
 |  | Injection gap cleaning
Sat | 02:00 | Ramp/squeeze/collision with pilot intensities (Single_2b_1_1_1) - chromaticity measurement without tune feedback
Sat | M | Collimator alignment (nominal bunch intensity) at injection and loss maps
Sat | A | LSS6 BPM tests and injection setting-up with 75 ns beams
Sat | N | Injection gap cleaning (Delphine is on shift) - part of the night
Sun | M | Ramp/squeeze/collision with pilot intensities (Single_2b_1_1_1) - chromaticity measurement without tune feedback after feedforward
Sun | A | Injection setting-up
Sun | N |