## Slide 1: Wednesday 5.10.
05:31 Beam dump due to QPS trigger in sector 78.
  Quench heaters discharged in MB10.L8.
07:28 Quench heaters charged ok again in cell B10L8.
  Was a EN/EL circuit breaker (cell 32, EOJ106/78.32R7). nr. Q3.
08:29 Cryo back.
08:20 RF tests without beam.
  Check for problem of debunching observed during fill #2182.
09:51 Vacuum leak in TI2 TED bellows. Access breaks patrol. Initial estimate for repair and recovery: 48h.
15:16 Open LHC for access.
  ELQA access in P8.
  Planning for beam 2 program over night: abort gap cleaning and 25ns setup.

## Slide 2: RF Summary I (P. Baudrenghien)
On Tuesday 4th from 12:15 to 14:30 we prepared the upgrade of the LHC tuner loops needed for the 25 ns MD scheduled Thursday 6th.
  The “old” algorithm needed a 1 microsec long beam segment to converge to the optimal tune. The new one needs 300 ns so that the tune will be OK after the injection of the first 12bunches batch.
  We first installed the upgrade on all 16 cavities but could not get it to lock after RF ON around 13:30. We struggled a bit. As we were under pressure from CCC, we made a roll-back and reverted to the old algorithm . RF was back ON OK at 14:30.
Then we worked off-line and found the problem with the new algo and corrected it.
  As the LHC was down, we installed it on one cavity (1B1) at 17:00 and it worked OK. As the next fill was high-intensity physics, we did not leave it overnight (Machine Protection issue) and reverted 1B1 to the old algo at 18:00
RESULT: the new algo is tested, ready for installation on all cavities at the very start of the 25 ns MD on Thursday (~8:00, 30 min needed).

## Slide 3: RF Summary II (P. Baudrenghien)
Next fill (physics) showed large debunching, beam 1, ~ 1 hour after start physics, clearly due to RF noise.
  John Molendijk and me came in ~ 23:00 and found noise on 1B1, caused by a so-called Klystron Polar Loop that reduces the RF noise and gain/phase changes due to klystron HV ripples and droop.
  We switched loop off and physics fill continued till 6:00 on Wednesday. We made a series of observations with beam but could not “touch” the hdw until the end of the fill.
  On Wednesday morning we went in the cavern, replaced the VME modulator card and found one SMC connector loose. The klystron loop is back on now.
Strong debunching beam 1 had already been observed for a short time on Sept 14th but not explained. It had disappeared since.
On Sept 20-21 we had another RF noise B1 episode that was traced to an intervention on 1B1 following change of a bad cable on Sept 9th….
Cables and loose connectors are the weak points of the LHC RF….
  We will replace ALL SMC cables during shutdown 2011-2012. Our observations last night also suggest a potential problem with the loop in presence of strong power spikes (needed to compensate transient beam loading with high beam current). John will investigate off-line. All cavities are back, ready for beam.
The above two events (new tuner algo - RF noise 1B1) are unrelated.

## Slide 4: Wednesday 5.10.
18:09 Vacuum group identifies correct spare part.
  Recovery time revised to Thursday morning.
  TED repair starting.
  Beam 2 program for the night cancelled. Plan TI8 stability checks overnight (during pump down of TI2).
18:32 Starting the PNO.a7 on RQ5.L8 and RQ6.L8.
19:03 Going through access list to check who wants to go into LHC over night and during early morning.
20:10 Access in P8 (vac expert + RP) for preventive check of the TED bellows in TI8.

## Slide 5: Access List I
Access Requests =============== we contacted most of the access request this is the summary: ------------------------------------------------------------------------------ Group: EL Location: Various points Duration: 2hrs per point during normal hrs Contact: D Ricci (16 5371) Reason: Optical fibres: measurement of attenuation factor contacted no answer ------------------------------------------------------------------------------ Group: BI Location: RR47/43 Duration: 15 min/side Contact: M. Gasior 16 3104 Reason:tune no answer ------------------------------------------------------------------------------

## Slide 6: Access List II
------------------------------------------------------------------------------ Group: BLM Location: IP7/tunnel Duration: 2 hours Contact: E. Effinger, J. Emery, I. Savu Reason: Replacement of BLM Diamond monitor Request date: 29/09/2011
------------------------------------------------------------------------------ Group: EN/EL Location: All REs (tunnel) Duration: 2hrs per point Contact: Antonio Gonzalez (160454) Reason: Optic fiber measurements Request date: 28/09/2011 contacted only available during working hrs. ---------------------------------------------------------------------

## Slide 7: Access List III
------------------------------------------------------------------------------ Group: ALICE Location: Duration: 2h + 1h notifications Contact: Reason: Request date: 4.10.2011 on access today ----------------------------------------------------------------------------- Group: CS/CV, RP needed Location: UJ32 Duration: 1h30 (in the tunnel) Contact: Frederic Juban (165669) Reason: verification de drain - as soon as possible Request date: 4.10.2011 No answer ------------------------------------------------------------------------------

## Slide 8: Access List IV
------------------------------------------------------------------------------ Group: BT Location: UA87 Duration: 2h (during normal working hours) Contact: Etienne Carlier (160093) Reason: measurement of "no trigger clock" of MKI-B2 Request date: 4.10.2011 done today ------------------------------------------------------------------------------ Group: kicker Location: Pt4 Duration 1H Contact: Barlow (164831) Reason Aperture kicker intervention Request Date: 5.10.2011-- no answer ---------------------------------------------------------------------

## Slide 9: Access List V
------------------------------------------------------------------------------ Group: EN/EL Location: US15 and UJ56 Duration: 1hr Contact: Consuelo Goncalves (168896) or Jean-Claude Guillaume (163194) Reason: Inspection prior to technical stop they will go IN tomorrow morning at 7:30 ------------------------------------------------------------------------------ Group: Access Location: PM45 Duration: 1hr Contact: Serge di Luca (164000) Reason: Door closer removal done today ---------------------------------------------------------------------

## Slide 10: Access List VI
------------------------------------------------------------------------------ Group: EN/EL Location: US15 and UJ56 Duration: 1hr Contact: Consuelo Goncalves (168896) or Jean-Claude Guillaume (163194) Reason: Inspection prior to technical stop they will go IN tomorrow morning at 7:30 ------------------------------------------------------------------------------ Group: Access Location: PM45 Duration: 1hr Contact: Serge di Luca (164000) Reason: Door closer removal done today ---------------------------------------------------------------------

## Slide 11: Access List VII
------------------------------------------------------------------------------ Group: BLM Location: IP7/tunnel Duration: 2 hours Contact: E. Effinger, J. Emery, I. Savu Reason: Replacement of BLM Diamond monitor Request date: 29/09/2011 closed untill tomorrow ---------------------------------------------------------------------------------------------------------- Group: Vacuum Location: point 8 Duration: 4 hours (normal working hours) Contact: Vacuum piquet Reason: Modify cabling at A4L8 and A4R8, to have a clearer view of pressure increases. Request Date: 26/09/2011 ------------------------------------------------------------------------------

## Slide 12: Access List VIII
------------------------------------------------------------------------------ Group: CS/CV, RP needed Location: UJ32 Duration: 1h30 (in the tunnel) Contact: Frederic Juban (165669) Reason: verification de drain - as soon as possible Request date: 4.10.2011 will access tomorrow morning at 8:00 ---------------------------------------------------------------------

## Slide 13: Ahead
Recovery from accesses, TED repair. Patrol. Change back of RF system.
Switch LHCb polarity.
25 ns MD (estimate ~ 10h00).
Thursday night: Physics
Friday day: Abort gap cleaning.
Friday pm/Sat/Sun: Physics
Monday day: High pile-up MD.