## Slide 1: Planning
Beam expected in the afternoon
PM:
  Establish first-turn
  Establish closed orbit
  Rough correction of machine parameters
Evening:
  RF capture
Night:
  Beta-beating measurements and correction

## Slide 2: First turn(s)
Close one (at least) collimator / IR.
Injection to TDI with MKI off, then MKI on – TDI closed.
  Trajectory check.
  Then TDI opened and into the ring…
Inject beam and stop on collimator.
Move from one IR to the next – threading.
  Correct trajectory if required (> ~ 2 mm amplitude). Was not needed in 2011.
  If trajectory OK: open collimator and move on.
There will be some free splashes on the way.
  Propose to deliver the desired splash events another time.
When we have some 100’s of turns  RF team with Philippe in IR4 for capture.

## Slide 3: Circulating beam
When we have circulating beam:
  RF capture tuning (if desired by RF).
  BI checkout with beam.
  Then optics measurements.
Need some ‘coarse’ collimator settings to limit phase space for the first few days.
  IR3 and IR7.
  Injection protection (TDI, TCDI, TCLI).

## Slide 4: Preliminary plan for the week
Day | Shift | hours | Activity |  | Beam
THU | M | 2 | Reference orbit with probe |  | Probe
THU | M | 6 | Injection correction and TI2/8 reference trajectories |  | Probe
THU | A | 4 | Injection of nominal bunch |  | Nominal
THU | A | 4 | Flat reference orbit at injection with nominal bunch | Nominal bunch | Nominal
THU | N | 8 | BI shift |  | Probe
FRI | M | 8 | RF and Damper setup for nominal bunch |  | Nominal
FRI | A | 4 | Feedbacks - recommissioning at injection (Q, orbit, radial) |  | Probe
FRI | A | 4 | Ramp to 4 TeV - test QFB & OFB | First ramp | Probe
FRI | N | 8 | Aperture measurements at injection (global, critical areas) |  | Probe
SAT | M | 8 | Squeeze to 0.6 m | First squeeze | Probe
SAT | A | 8 | Optics measurements - test dump at 4 TeV |  | Probe
SAT | N | 8 | Pre-cycle or ramp (no beam) - decay measurement at 450 GeV |  | Probe

## Slide 5: Preliminary plan for the week
Day | Shift | hours | Activity |  | Beam
SUN | M | 8 | Dump checkout |  | Probe
SUN | A | 8 | Dump checkout |  | Probe
SUN | N | 8 | Pre-cycle or ramp (no beam) - decay measurement at 450 GeV |  | Probe
MON | M | 8 | Orbit at injection with nominal bunch and bumps |  | Nominal
MON | A | 4 | Experimental magnets ON |  | Nominal
MON | A | 4 | RF setting-up (long. Blow-up in the ramp) |  | Nominal
MON | N | 4 | Orbit feedback with dynamic reference in the ramp |  | Nominal
TUE | N/M | 8 | BI shift |  | Nominal
TUE | M | 4 | Dump checkout |  | Nominal
TUE | A | 8 | Dump checkout |  | Nominal
TUE | N | 8 | Collimation setting-up 450 GeV | Collimation | Nominal
WED | M | 8 | Squeeze to 0.6 m revisited - OFB and optics |  | Probe